## ENROUTE SITE
CLIENT PO | CARGO DETAILS | CLIENT | MUMI PO NUMBER | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | BV RECEIVED | BV INSPECTION COMPLETE | PN ISSUE DATE (BV RELEASE) | CRF ISSUE DATE | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKEY ARR | WHISKEY DISPATCH | LUBUMBASHI ARR | LUBUMBASHI DSP | KOLWEZI ARR | OFFLOADED | COMMENTS 10-12-2025 | COMMENTS 11-12-2025 | COMMENTS 12-12-2025 | COMMENTS 15-12-2025 | COMMENTS 17-12-2025 | COMMENTS 18-12-2025 | COMMENTS 19-12-2025 | COMMENTS 22-12-2025 | COMMENTS 23-12-2025 | COMMENTS 24-12-2025 | COMMENTS 29-12-2025 | COMMENTS 30-12-2025 | COMMENTS 31-12-2025 | COMMENTS 02-01-2026 | COMMENTS 05-01-2026 | COMMENTS 06-01-2026 | COMMENTS 07-01-2026 | COMMENTS 08-01-2026 | COMMENTS 09-01-2026 | COMMENTS 12-01-2026 | COMMENTS 13-01-2026 | COMMENTS 14-01-2026 | COMMENTS 15-01-2026 | COMMENTS 16-01-2026 | COMMENTS 19-01-2026 | COMMENTS 20-01-2026 | COMMENTS 21-01-2026 | COMMENTS 22-01-2026 | COMMENTS 23-01-2026 | COMMENTS 26-01-2026 | COMMENTS 27-01-2026 | COMMENTS 29-01-2026 | COMMENTS 30-01-2026 | COMMENTS 02-02-2026 | COMMENTS 03-02-2026 | COMMENTS 04-02-2026 | COMMENTS 05-02-2026 | COMMENTS 06-02-2026 | COMMENTS 09-02-2026 | COMMENTS 09-02-2026 | COMMENTS 10-02-2026 | COMMENTS 11-02-2026 | COMMENTS 12-02-2026 | COMMENTS 13-02-2026 | COMMENTS 16-02-2026
BA3008 | CAT333 BUCKET | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003389591 | N/A | N/A | N/A | FML2512DSI2742 | COD 2025 346488 | BCH 8449 ZM | BCG 2604 ZM / BCG 2605 ZM | 2502DSI2674 | VESSEL: HOEGH SUNLIGHT Voy. 06 - ETA DURBAN PORT : 02-01-2026 | OFFLOADED 15-02-2026 | 23-12-2025 | 07-01-2026 | 08-01-2026 | 12-01-2026 | CRF ISSUE DATE 12-01-2026 | 04-01-2026 | 12-01-2026 | 13-01-2026 | 13-01-2026 | 13-01-2026 | GRB 13-01-2026 | GRB 15-01-2026 | FRANCISTOWN 16-01-2026 | KAZUNGULA 16-01-2026 | 25-01-2026 | 25-01-2026 | 27-01-2026 | 2026-02-02 | 2026-02-02 | 2026-02-03 | 2026-02-11 | 12-02-2026 | 12-02-2026 | 13-02-2026 | 15-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 31-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 31-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 31-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 31-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 01-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 01-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 01-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 01-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 01-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 01-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 02-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 02-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 02-01-2026 | VESSEL IN AND WORKING | TO BE COLLECTED FROM PORT | COLLECTING FORM PORT TODAY - BV INSPECTION PLANNED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | BV ISNPECTION COMPLETED | LOADING MONDAY 12-01-2026 | LOADING TODAY | LOADED ENROUTE GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CLEARING | GROBLERS BRIDGE BORDER CLEARING | DUKWI ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | NDOLA UNDER ROUTINE CHECKS | DSP NDOLA - CHAMBISHI EN ROUTE KASUMBULESA | CHAMBISHI IN QUEUE DRC | CHAMBISHI STILL IN QUEUE TO KASUMBALESA BORDER | CHINGOLA IN QUEUE TO KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY AWAITING RELEASE - DAY 5 | WHISKEY AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE - DAY 6 - DOCUMENTS TO BE COLLECTED FROM CONNEX OFFICE | DISPATCH FROM WHISKEY - EN ROUTE TO LUBUMBASHI | IN THE QUEUE TO DISPATCH FROM WHISKEY | PASSING FUNGURUME ENROUTE KOLWEZI | OFFLOADED 15-02-2026

## OFFLOADED
CLIENT PO | CARGO DETAILS | CLIENT | MUMI PO NUMBER | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | BV RECEIVED | BV INSPECTION COMPLETE | PN ISSUE DATE (BV RELEASE) | CRF ISSUE DATE | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKEY ARR | WHISKEY DISPATCH | LUBUMBASHI ARR | LUBUMBASHI DSP | KOLWEZI ARR | OFFLOADED | COMMENTS 13-07-2023 | COMMENTS 14-07-2023 | COMMENTS 17-07-2023 | COMMENTS 18-07-2023 | COMMENTS 19-07-2023 | COMMENTS 20-07-2023 | COMMENTS 21-07-2023 | COMMENTS 24-07-2023 | COMMENTS 25-07-2023 | COMMENTS 26-07-2023 | COMMENTS 27-07-2023 | COMMENTS 28-07-2023 | COMMENTS 31-07-2023 | COMMENTS 01-08-2023 | COMMENTS 02-08-2023 | COMMENTS 03-08-2023 | COMMENTS 04-08-2023 | COMMENTS 07-08-2023 | COMMENTS 08-08-2023 | COMMENTS 10-08-2023 | COMMENTS 11-08-2023 | COMMENTS 14-08-2023 | COMMENTS 15-08-2023 | COMMENTS 16-08-2023 | COMMENTS 17-08-2023 | COMMENTS 18-08-2023 | COMMENTS 21-08-2023 | COMMENTS 22-08-2023 | COMMENTS 23-08-2023 | COMMENTS 24-08-2023 | COMMENTS 25-08-2023 | COMMENTS 28-08-2023 | COMMENTS 29-08-2023 | COMMENTS 30-08-2023 | COMMENTS 31-08-2023 | COMMENTS 01-09-2023 | COMMENTS 04-09-2023 | COMMENTS 05-09-2023 | COMMENTS 06-09-2023 | COMMENTS 07-09-2023 | COMMENTS 11-09-2023 | COMMENTS 12-09-2023 | COMMENTS 13-09-2023 | COMMENTS 14-09-2023 | COMMENTS 15-09-2023 | COMMENTS 18-09-2023 | COMMENTS 19-09-2023 | COMMENTS 20-09-2023
BA2542 | CAT CP12GC VIBRATORY COMPACTOR | BARTRAC EQUIPMENT / MUTANDA MINING SARP | PO 7500042923 | M3K00179 | CATCP122PM3K00179 | MFX13853 | 2307DSI2156 | COD 2023 268658 | ND919955 | ND140841 | 131589 | VESSEL: BANGKOK HIGHWAY Voy. 148 -ETA DURBAN: 03-09-2023 | OFFLOADED 19-09-2023 | 15-08-2023 | 05-09-2023 |  |  | BV NUMBER RECEIVED | 03-09-2023 | 05-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 08-09-2023 | 09-09-2023 | 11-09-2023 | 13-09-2023 | 13-09-2023 | 13-09-2023 | MOKAMBO 14-09-2023 | MOKAMBO 14-09-2023 | 15-09-2023 | 16-09-2023 | 16-09-2023 | 17-09-2023 | 18-09-2023 | 19-09-2023 | [26 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | VESSEL CURRENLTY IN AND WORKING | BV INSPECTION BOOKED FOR TODAY | VEHICLE AT VILLIERS ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAMBIA SIDE CLEARING | VEHICLE CURRENTLY AT CHIRUNDU ZAMBIA SIDE CLEARING | VEHICLE CURRENTLY AT CHIRUNDU ZAMBIA SIDE CLEARING | VEHICLE CURRENTLY AT MASAITI ZAMBIA ENROUTE MOKAMBO | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-09-2023 | OFFLOADED 19-09-2023
BA2594 | CAT16GC-01A MOTOR GRADER | BARTRAC EQUIPMENT / MUTANDA MINING SARP | PO 7500042926 | EB900202 | CAT00016PEB900202 | P4E05804 | 2306DSI2129 | COD 2023 262005 | AGJ0082 | AF9435 | ND60444 | VESSEL: GRAND PAVO Voy. 114 - ETA DURBAN: 04-08-2023 | OFFLOADED 19-09-2023 | 07-08-2023 | 10-08-2023 |  |  | BV INSPECTION COMPLETE | 05-08-2023 | 17-08-2023 | MIDDELBURG 24-08-2023 | MIDDELBURG 24-08-2023 | 25-08-2023 | 28-08-2023 | 02-09-2023 | 05-09-2023 | 07-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 13-09-2023 | 15-09-2023 | 15-09-2023 | 16-09-2023 | 16-09-2023 | 17-06-2023 | 18-06-2023 | 19-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-08-2023 - AWAITING BV NUMBER | BV NUMBER RECEIVED - LOADING DATE TO BE CONFIRMED | BV NUMBER RECEIVED - INSPECTION BOOKED FOR THURSDAY 10-08-2023 | BV INSPECTION BOOKED FOR TODAY 10-08-2023 | UNIT LOADED - AWAITING PERMITS IN ORDER TO DISPATCH | UNIT LOADED - AWAITING PERMITS IN ORDER TO DISPATCH | UNIT LOADED - AWAITING PERMITS IN ORDER TO DISPATCH | UNIT LOADED - AWAITING PERMITS IN ORDER TO DISPATCH-PERMITS SHOULD BE OUT TODAY | TRUCK DISPATCHED EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MARIAN HILL TOLL EN-ROUTE TO BEITBRIDGE BORDER | CAMPERDOWN EN-ROUTE TO BEITBRIDGE BORDER | COLENSO EN-ROUTE TO BEITBRIDGE BORDER | NEWCASTLE WAIING ESCORT TO PROCEED TO BEITBRIDGE BORDER | ERMELO ENROUTE BEITBRIDGE BORDER | POLOKWANE ENROUTE BEITBRIDGE BORDER | BEITBRIDGE BORDER RSA SIDE CLEARING | BEITBRIDGE BORDER RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | BEITBRIDGE BORDER RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | BEITBRIDGE BORDER RSA SIDE WAITING RELEASE TO PROCEED TO ZIM SIDE | BEITBRIDGE BORDER RSA SIDE WAITING RELEASE TO PROCEED TO ZIM SIDE | VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT HARARE UNDERGOING VEHICLE CHECK | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE DISPATCHING CHIRUNDU EN-ROUTE TO KASUMBALESA BORDER | VEHICLE AT NDOLA EN-ROUTE TO KASUMBALESA BORDER | VEHICLE AT KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-09-2023
BA2595 | CAT16GC-01A MOTOR GRADER | BARTRAC EQUIPMENT / MUTANDA MINING SARP | PO 7500042926 | EB900201 | CAT00016TEB900201 | P4E05806 | 2306DSI2130 | COD 2023 262002 | AFJ2968 | AFQ6073 | ND60445 | VESSEL: GRAND PAVO Voy. 114 - ETA DURBAN: 04-08-2023 | OFFLOADED 19-09-2023 | 07-08-2023 | 10-08-2023 |  |  | BV INSPECTION COMPLETE | 05-08-2023 | 17-08-2023 | MIDDELBURG 24-08-2023 | MIDDELBURG 24-08-2023 | 25-08-2023 | 28-08-2023 | 02-09-2023 | 05-09-2023 | 07-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 13-09-2023 | 15-09-2023 | 15-09-2023 | 16-09-2023 | 16-09-2023 | 17-06-2023 | 18-06-2023 | 19-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-08-2023 - AWAITING BV NUMBER | BV NUMBER RECEIVED - LOADING DATE TO BE CONFIRMED | BV NUMBER RECEIVED - INSPECTION BOOKED FOR THURSDAY 10-08-2023 | BV INSPECTION BOOKED FOR TODAY 10-08-2023 | UNIT LOADED - AWAITING PERMITS IN ORDER TO DISPATCH | UNIT LOADED - AWAITING PERMITS IN ORDER TO DISPATCH | UNIT LOADED - AWAITING PERMITS IN ORDER TO DISPATCH | UNIT LOADED - AWAITING PERMITS IN ORDER TO DISPATCH-PERMITS SHOULD BE OUT TODAY | TRUCK DISPATCHED EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MARIAN HILL TOLL EN-ROUTE TO BEITBRIDGE BORDER | CAMPERDOWN EN-ROUTE TO BEITBRIDGE BORDER | COLENSO EN-ROUTE TO BEITBRIDGE BORDER | NEWCASTLE WAIING ESCORT TO PROCEED TO BEITBRIDGE BORDER | ERMELO ENROUTE BEITBRIDGE BORDER | POLOKWANE ENROUTE BEITBRIDGE BORDER | BEITBRIDGE BORDER RSA SIDE CLEARING | BEITBRIDGE BORDER RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | BEITBRIDGE BORDER RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | BEITBRIDGE BORDER RSA SIDE WAITING RELEASE TO PROCEED TO ZIM SIDE | BEITBRIDGE BORDER RSA SIDE WAITING RELEASE TO PROCEED TO ZIM SIDE | VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT HARARE UNDERGOING VEHICLE CHECK | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE DISPATCHING CHIRUNDU EN-ROUTE TO KASUMBALESA BORDER | VEHICLE AT NDOLA EN-ROUTE TO KASUMBALESA BORDER | VEHICLE AT KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-09-2023
BA2526 | CAT D9 TRACK TYPE TRACTOR - PARTS | BARTRAC EQUIPMENT / MUTANDA MINING SARP | 7500042924 | AK400898 | CAT000D9CAK400898 | TNR00763 | 2311DSI2280 | COD 2023 341720 | KT 12 MT GP | KT 53 PB GP / KT 53 PF GP | 2311DSI2280 | VESSEL: GENUINE ACE V. 0087A - ETA 22-11-2023 | OFFLOADED 13-12-2023 | 20-11-2023 | 24-11-2023 |  |  | BV NUMBER RECEIVED | 20-11-2023 | 22-11-2023 | 23-11-2023 | 24-11-2023 | 24-11-2023 | 25-11-2023 | 27-11-2023 | 27-11-2023 | 28-11-2023 | 29-11-2023 | 30-11-2023 | 30-11-2023 | 05-12-2023 | 06-12-2023 | 06-12-2023 | 07-12-2023 | 07-12-2023 | 08-12-2023 | 08-12-2023 | 13-12-2023 | AWAITING VESSEL ARRIVAL ON THE 22-11-2023 | AWAITING VESSEL ARRIVAL ON THE 22-11-2023 | AWAITING VESSEL ARRIVAL ON THE 22-11-2023 | AWAITING VESSEL ARRIVAL ON THE 20-11-2023 | AWAITING VESSEL ARRIVAL ON THE 20-11-2023 | VESSEL ARRIVED AND CURRENTLY WORKING | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, DISPATCHING DURBAN TODAY | JHB ENROUTE BEIT BRIDGE | MWENEZI ENROUTE CHIRUNDU | HARARE ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | VEHICLE IN LUSAKA ENROUTE TO NDOLA | VEHICLE IN NDOLA ENROUTE TO KASUMBULESA | MOKAMBO BORDER CLEARING | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA BORDER CLEARING | WHISKEY AWAITING RELEASE | KANYAKA PARKING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO COMPLETE THE OFFLOADING | ON SITE WAITING TO COMPLETE THE OFFLOADING - PLEASE ASSIST | OFFLOADED 13-12-2023 | OFFLOADED 13-12-2023
BA2526 | CAT D9 TRACK TYPE TRACTOR - MAIN UNIT | BARTRAC EQUIPMENT / MUTANDA MINING SARP | 7500042924 | AK400898 | CAT000D9CAK400898 | TNR00763 | 2311DSI2280 | COD 2023 341720 | BCE5482ZM | ADF711ZM / BCE8760ZM | ND61161 | VESSEL: GENUINE ACE V. 0087A - ETA 22-11-2023 | OFFLOADED 27-12-2023 | 20-11-2023 | 24-11-2023 |  |  | BV NUMBER RECEIVED | 20-11-2023 | 27-11-2023 | 28-11-2023 | 29-11-2023 | 29-11-2023 | 30-11-2023 | 02-12-2023 | 03-12-2023 | 03-12-2023 | 11-12-2023 | 11-12-2023 | 12-12-2023 | 14-12-2023 | 14-12-2023 | 15-12-2023 | 22-12-2023 | 23-12-2023 | 26-12-2023 | 27-12-2023 | 27-12-2023 | AWAITING VESSEL ARRIVAL ON THE 22-11-2023 | AWAITING VESSEL ARRIVAL ON THE 22-11-2023 | AWAITING VESSEL ARRIVAL ON THE 22-11-2023 | AWAITING VESSEL ARRIVAL ON THE 20-11-2023 | AWAITING VESSEL ARRIVAL ON THE 20-11-2023 | VESSEL ARRIVED AND CURRENTLY WORKING | COLLECTING UNIT FROM PORT TOMORROW - BV INSPECTION BOOKED FOR FRIDAY 24-11-2023 | COLLECTING UNIT FROM PORT TODAY - BV INSPECTION BOOKED FOR FRIDAY 24-11-2023 | BV INSPECTION TO BE DONE TODAY | CAMPERDOWN ENROUTE JOHANNESBURG | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE BEIT BRIDGE | POLOKWANE ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE WAITING RELEASE & PERMIT | DISPATCHED CHIRUNDU ENROUTE KASUMBALESA | LUSAKA ENROUTE KASUMBALESA | KITWE ENROUTE KASUMBALESA | DISPATCHING KITWE FOR KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE - ELECTION DAY | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-12-2023 | OFFLOADED 27-12-2023 | OFFLOADED 27-12-2023
BA2532 | CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / MUTANDA MINING SARP | 7500042927 PT02 | 3F606124 | CAT00745K3F3F606124 | TXW07677 | 2310DSI2267 | COD 2023 343178 | ND919945 | ND133379 | 2310DSI2267 | VESSEL: GOLDEN KAROO 231220-ETA 18-12-2023 | OFFLOADED | 20-11-2023 | 08-01-2024 |  |  | BV COMPLETED | 18-12-2023 | 08-01-2024 | MIDDELBURG 09-01-2023 | MIDDELBURG 09-01-2023 | 10-01-2023 | 10-01-2024 | 11-01-2024 | 12-01-2024 | 14-01-2024 | 16-01-2024 | 17-01-2024 | 18-01-2024 | 18-01-2024 | 18-01-2024 | 19-01-2024 | 20-01-2024 | 21-01-2024 | 21-01-2024 | 21-01-2024 | 23-01-2024 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | VESSEL ARRIVE - CURRENLTY DISCHARGING | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR FRIDAY 22-12-2023 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR FRIDAY 22-12-2023 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR FRIDAY 22-12-2023 - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | DISPATCHING FROM DURBAN TODAY | GREYTOWN ENROUTE MUSINA | MARBLE HALL ENROUTE MUSINA | BEIT BRIDGE ZIM SIDE | MASVINGO ENROUTE HARARE | CHIRUNDU ZAM SIDE CLEARING | LUSAKA ENROUTE MOKAMBO BORDER | VEHICLE CURRENTLY AT MASAITI ENROUTE KITWE | VEHICLE CURRENTLY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | TRUCK IS ON SITE AWAITING TO OFFLOAD | TRUCK IS ON SITE AWAITING TO OFFLOAD DAY 2 | OFFLOADED
BA2534 | CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / MUTANDA MINING SARP | 7500042927 PT01 | 3F606126 | CAT00745C3F606126 | TXW07618 | 2310DSI2268 | COD 2023 343189 | ND919947 | ND923085 | 2310DSI2268 | VESSEL: GOLDEN KAROO 231220-ETA 18-12-2023 | OFFLOADED | 20-11-2023 | 08-01-2024 |  |  | BV COMPLETED | 18-12-2023 | 08-01-2024 | MIDDELBURG 09-01-2023 | MIDDELBURG 09-01-2023 | 10-01-2023 | 10-01-2024 | 11-01-2024 | 12-01-2024 | 14-01-2024 | 16-01-2024 | 17-01-2024 | 18-01-2024 | 18-01-2024 | 18-01-2024 | 19-01-2024 | 20-01-2024 | 21-01-2024 | 21-01-2024 | 21-01-2024 | 23-01-2024 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | VESSEL ARRIVE - CURRENLTY DISCHARGING | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR FRIDAY 22-12-2023 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR FRIDAY 22-12-2023 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR FRIDAY 22-12-2023 - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - DUE TO FULL ROAD EMBARO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | DISPATCHING FROM DURBAN TODAY | LADYSMITH ENROUTE MUSINA | MARBLE HALL ENROUTE MUSINA | BEIT BRIDGE ZIM SIDE | MASVINGO ENROUTE HARARE | CHIRUNDU ZAM SIDE CLEARING | LUSAKA ENROUTE MOKAMBO BORDER | VEHICLE CURRENTLY AT MASAITI ENROUTE KITWE | VEHICLE CURRENTLY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | TRUCK IS ON SITE AWAITING TO OFFLOAD | TRUCK IS ON SITE AWAITING TO OFFLOAD DAY 2 | OFFLOADED
BA2661 | COBRA LUBE SERVICE UNIT | BARTRAC EQUIPMENT / MUTANDA MINING SARP | 7500042972 | N/A | N/A | N/A | 2402DRE2398 | COD 2024 131525 | ND919945 | ND133379 | 2402DRE2398 | ON ROAD | OFFLOADED 11-03-2024 | 20-02-2024 | 22-02-2024 |  |  | BV COMPLETED | N/A | N/A | N/A | 26-02-2024 | 27-02-2024 | 29-02-2024 | 01-03-2024 | 02-03-2024 | 03-03-2024 | 03-03-2024 | 04-03-2024 | 05-03-2024 | 05-03-2024(MOKAMBO) | 08-03-2024 | 08-03-2024 | 08-03-2024 | 08-03-2024 | 08-03-2024 | 08-03-2024 | 11-06-2024 | [29 empty] | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING DOCS AND BV INSPECTION | AWAITING AMENDED BV LICENCE WITH CORRECT HS CODE | AWAITING AMENDED BV LICENCE WITH CORRECT HS CODE | AWAITING AMENDED BV LICENCE WITH CORRECT HS CODE | NEW BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THURSDAY | BV INSPECTION TO BE BOOKED FOR TOMORROW 22-02-2024 - LOADING PLANNED FOR FRIDAY | BV INSPECTION TO BE BOOKED FOR TODAY 22-02-2024 - LOADING PLANNED FOR MONDAY | BV INSPECTION DONE - LOADING TODAY | DISPATCHED JOHANNESBURG ENROUTE MUSINA | POLOKWANE ENROUTE MUSINA | VEHCILE CURRENTLY AT LOUIS TRICHARDT ENROUTE MUSINA | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHILCE CURRENTLY AT MASVINGO ENROUTE HARARE | VEHILCE CURRENTLY AT KAPIRI MPHOSHI ENROUTE MOKAMBO BORDER | VEHILCE CURRENTLY AT MOKAMBO BORDER AWAITING CLEARANCE | VEHILCE CURRENTLY AT MOKAMBO BORDER AWAITING CLEARANCE | VEHILCE CURRENTLY AT MOKAMBO BORDER AWAITING CLEARANCE DAY 3 | VEHILCE CURRENTLY AT KASUMBALESA AWAITING RELEASE TO PROCEED TO WHISKEY | ON SITE WAITING TO OFFLOAD | OFFLOADED 11-03-2024 | OFFLOADED 11-03-2024
BA2533 | CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / MUTANDA MINING SARP | TBC | 3F606125 | CAT00745J606125 | TBC | 2312DSI2351 | COD 2024 103793 | ND706468 | ND476150 | ND64637 | VESSEL: BLUE MASTER II Voy. 241203 - ETA DURBAN 16-02-2024 | OFFLOADED 14-03-2024 | 12-01-2024 | 21-02-2024 |  |  | BV COMPLETED | 16-02-2024 | 26-02-2024 | 26-02-2024 | 28-02-2024 | 28-02-2024 | 29-02-2024 | 01-03-2024 | 02-03-2024 | 05-03-2024 | 06-03-2024 | 07-03-2024 | 07-03-2024 | 07-03-2024 | 09-03-2024 | 09-03-2024 | 12-03-2024 | 12-03-2023 | 13-03-2024 | 13-03-2024 | 14-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-02-2025 | BV INSPECTION BOOKED FOR TOMORROW 21-02-2024 | BV INSPECTION BOOKED FOR TODAY 21-02-2024 | BV INSPECTION COMPLETED - AWAITING PERMIT BEFORE DISPATCHING | BV INSPECTION COMPLETED - AWAITING PERMIT BEFORE DISPATCHING | MOOI REVIER ENROUTE JOHANNESBURG | JOHANNESBURG AWAITING LIMPOPO PERMIT | VEHICLE CURRENLTY AT MOKOPANE ENROUTE BEITBRIDGE BORDER | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | VEHILCE CURRENTLY AT CHIBI ENROUTE HARARE | VEHILCE CURRENTLY AT MAKUTI ENROUTE CHIRUNDU | VEHILCE CURRENTLY AT CHIRUNDU | VEHILCE CURRENTLY AT CHISAMBA EN-ROUTE TO BEITBRIDGE BORDER | VEHILCE CURRENTLY AT CHINGOLA EN-ROUTE TO BEITBRIDGE BORDER | VEHILCE CURRENTLY AT KASUMBALESA BORDER ZAM SIDE | VEHILCE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHILCE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHILCE CURRENTLY AT LIKASI ENROUTE SITE | VEHILCE ON SITE WAITING TO OFFLOAD | OFFLOADED 14-03-2024 | OFFLOADED 14-03-2024
BA2642 | COBRA 35,000LTS WATER TANK FOR CAT745 | BARTRAC EQUIPMENT / MUTANDA MINING SARP | 7500042969 | N/A | N/A | N/A | 2402DRE2435 | COD 2024 152892 | CAD 5991 ZM | HN 85 RX GP | ND64698 | EX RSA | OFFLOADED | 20-03-2024 | 25-03-2024 |  |  | BV NUMVER RECEIVED | N/A | N/A | N/A | 26-03-2024 | 27-06-2024 | 27-03-2024 | 29-03-2024 | 29-03-2024 | 30-03-2024 | 01-03-2024 | 02-04-2024 | 02-04-2024 | 03-04-2024 | 05-04-2024 | 08-04-2024 | 08-04-2024 | 09-04-2024 | 09-04-2024 | 09-04-2024 | 10-04-2024 | [29 empty] | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING DOCS AND BV INSPECTION | AWAITING AMENDED BV LICENCE WITH CORRECT HS CODE | AWAITING AMENDED BV LICENCE WITH CORRECT HS CODE | AWAITING AMENDED BV LICENCE WITH CORRECT HS CODE | NEW BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THURSDAY | BV INSPECTION TO BE BOOKED FOR TOMORROW 22-02-2024 - LOADING PLANNED FOR FRIDAY | BV INSPECTION TO BE BOOKED FOR TODAY 22-02-2024 - LOADING PLANNED FOR MONDAY | BV INSPECTION DONE - LOADING TODAY | DISPATCHED JOHANNESBURG ENROUTE MUSINA | POLOKWANE ENROUTE MUSINA | VEHCILE CURRENTLY AT LOUIS TRICHARDT ENROUTE MUSINA | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHILCE CURRENTLY AT MASVINGO ENROUTE HARARE | VEHILCE CURRENTLY AT KAPIRI MPHOSHI ENROUTE MOKAMBO BORDER | VEHILCE CURRENTLY AT MOKAMBO BORDER AWAITING CLEARANCE | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV BOOKD FOR MONDAY THE 25/03/2024, PLANNING TO LOAD ON THE 26/03/2024 | BV BOOKD FOR MONDAY THE 25/03/2024, PLANNING TO LOAD ON THE 26/03/2024 | BV BOOKD FOR TODAY THE 25/03/2024, PLANNING TO LOAD ON THE 26/03/2024 | BV INSPECTION COMPLETED - LOADING TODAY | POLOKWANE ENOUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | DISPATCHED FROM LUSAKA ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAMBIAN SIDE | KASUMBALESA DRC SIDE | TRUCK IS AT WHISKEY AWAITING RELEASE | TRUCK IS ON SITE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2643 | COBRA 36,000LTS DIESEL BOWSER FOR CAT745 | BARTRAC EQUIPMENT / MUTANDA MINING SARP | 7500042973 | N/A | N/A | N/A | 2402DRE2436 | COD 2024 152888 | ND730794 | ND443606 | ND64714 | EX RSA | OFFLOADED 28-04-2024 | 20-03-2024 | 28-03-2024 |  |  | BV COMPLETED | N/A | N/A | N/A | 05-04-2024 | 06-04-2024 | 08-04-2024 | 08-04-2024 | 09-04-2024 | 12-04-2024 | 13-04-2024 | 14-04-2024 | 15-04-2024 | 15-04-2024 | 18-04-2024 | 18-04-2024 | 20-04-2024 | 20-04-2024 | 21-04-2024 | 21-04-2024 | 28-04-2024 | [29 empty] | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING DOCS AND BV INSPECTION | AWAITING AMENDED BV LICENCE WITH CORRECT HS CODE | AWAITING AMENDED BV LICENCE WITH CORRECT HS CODE | AWAITING AMENDED BV LICENCE WITH CORRECT HS CODE | NEW BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THURSDAY | BV INSPECTION TO BE BOOKED FOR TOMORROW 22-02-2024 - LOADING PLANNED FOR FRIDAY | BV INSPECTION TO BE BOOKED FOR TODAY 22-02-2024 - LOADING PLANNED FOR MONDAY | BV INSPECTION DONE - LOADING TODAY | DISPATCHED JOHANNESBURG ENROUTE MUSINA | POLOKWANE ENROUTE MUSINA | VEHCILE CURRENTLY AT LOUIS TRICHARDT ENROUTE MUSINA | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHILCE CURRENTLY AT MASVINGO ENROUTE HARARE | VEHILCE CURRENTLY AT KAPIRI MPHOSHI ENROUTE MOKAMBO BORDER | VEHILCE CURRENTLY AT MOKAMBO BORDER AWAITING CLEARANCE | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | AWAITING READINESS FROM SUPPLIER | BV INSPECTION BOOKED FOR TOMORROW 28-03-2024 - LOADING DATE TO BE ADVISED | BV INSPECTION BOOKED FOR TODAY 28-03-2024 - LOADING WEDNESDAY 03-04-2024 | BV INSPECTION COMPLETED - LOADING WEDNESDAY 03-04-2024 | LOADING TODAY | LOADED - AWAITING PERMIT | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE | TRUCK IS AT BEITBRIDGE ZIM SIDE | TRUCK IS AT HARARE EN-ROUTE TO CHIRUNDU | TRUCK IS AT HARARE TO DISPATCH TODAY EN-ROUTE TO CHIRUNDU | TRUCK IS AT MAPINGA TO DISPATCH TODAY EN-ROUTE TO CHIRUNDU | TRUCK IS AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | TRUCK IS AT CHISAMBA ENROUTE KASUMBALESA | TRUCK IS AT KASUMBALESA ZAM SIDE | TRUCK IS AT KASUMBALESA ZAM SIDE | TRUCK IS AT KASUMBALESA DRC SIDE | TRUCK IS AT WHISKEY | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD DAY 2 | ON SITE WAITING TO OFFLOAD DAY 3 | ON SITE WAITING TO OFFLOAD DAY 4 | ON SITE WAITING TO OFFLOAD DAY 5 | OFFLOADED 28-04-2024
BA2860 | CAT226B3 SKID STEER LOADER | MUTANDA MINING SARL | C003025466 | DXZ04166 | CAT0226BKDXZ04166 | CZ213500 | 2502DSI2674A | COD 2025 166156 | LG87RCGP | WJD486GP / WJD488GP | 2502DSI2674A | VESSEL MSC PRELUDE Voy. XA506A - TRANSHIPMENT VESSEL: MSC LUCY Voy. ZF507A - ETA DURBAN 31-03-2025 | OFFLOADED 25-06-2025 | 24-04-2025 | 02-06-2025 |  |  | BV COMPLETED - CRF ISSUED 25-06-2025 | 31-03-2025 | 03-06-2025 | 05-06-2025 | 06-06-2025 | ZEERUST 06-06-2025 | KOPFONTEIN BORDER 07-06-2025 | KOPFONTEIN BORDER 09-06-2025 | FRANCISTOWN 10-06-2025 | KAZUNGULA 10-06-2025 | 13-06-2025 | 13-06-2025 | 13-06-2025 | 13-06-2025 | 15-06-2025 | 15-06-2025 | 20-06-2025 | 20-06-2025 | 20-06-2025 | 20-06-2025 | 25-06-2025 | BV INSPECTION BOOKED FOR NEXT WEEK. AWAITING FOR BV RSA TO CONFIRM THE INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY 02-06-2025 - LOADING PLANNED FOR TOMORROW | BV INSPECTION DONE - LOADING PLANNED FOR TODAY | LOADED 03-06-2025 - RICHARDS BAY ENROUTE BORDER | ENROUTE KOPFONTEIN BORDER | ZEERUST ENROUTE KOPFONTEIN BORDER | KOPFONTEIN BORDER CLEARING | PALAPYE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | CHOMA ENROUTE NDOLA | KAPIRI ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY IN THE QUEUE TO EXIT | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 25-06-2025
BA2793 | CAT980 WHEEL LOADER | MUTANDA MINING SARL | C003172763 | MK910133 | CAT00980CMK910133 | P4E06368 | 2408DSI2567 | COD 2025 201059 | CJ98MWZN | BV08NFZN | MFSTD006889 | VESSEL SERENITY HIGHWAY Voy. 6 - ETA DURBAN 06-09-2024 | OFFLOADED 11-07-2025 | 06-06-2025 | 23-06-2025 |  | 26-06-2025 | CRF ISSUED 26-06-2025 | 06-09-2024 | 25-06-2025 | PRETORIA 26-06-2025 | PRETORIA 27-06-2025 | 28-06-2025 | 30-06-2025 | 01-07-2025 | 02-07-2025 | 05-07-2025 | 05-07-2025 | 06-06-2025 | 07-07-2025 | MOKAMBO 07-07-2025 | MOKAMBO 09-07-2025 | 09-07-2025 | 10-07-2025 | 10-07-2025 | 10-07-2025 | 10-07-2025 | 11-07-2025 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED | BV NUMBER RECEIVED - INSPECTION AND LOADING PLANNED FOR NEXT WEEK | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR MONDAY 23-06-2025 - LOADING PLANNED FOR TUESDAY 24-06-2025 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR MONDAY 23-06-2025 - LOADING PLANNED FOR TUESDAY 24-06-2025 | BV INSPECTION BOOKED FOR TODAY 23-06-2025 - LOADING PLANNED FOR TOMORROW 24-06-2025 | LOADING TODAY | HOWICK ENROUTE JOHANNESBURG | VAN REENEN ENROUTE JOHANNESBURG | PRETORIA ENROUTE BEIT BRIDGE BORDER - ROAD EMBARGO STARTS 12PM TODAY | POLOKWANE ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | MASVINGO ENROUTE HARARE | HURUNGWE ENROUTE CHIRUNDU | DISPATCHING HURUNGWE TODAY FOR CHIRUNDU BORDER | KAPIRI MPOSHI ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING | MOKAMBO BORDER ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | ON SITE WAITNIG TO OFFLOAD | OFFLOADED 11-07-2025
BA2924 | CATERPILLAR DISEL GENERATOR SET IN CONTAINER # XHCU508310/6 | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003027034 | LY300431 | CAT3516BPLY300431 |  | FML2507DSI2702 | COD 2025 260290 | BCC9364ZM | BCH2094ZM | 2507DSI2702A | VESSEL: JOLLY ARGENTO Voy. 25225 - ETA DURBAN: 25-08-2025 | OFFLOADED 28-09-2025 | 20-08-2025 | 29-08-2025 | 30-09-2025 | 06-09-2025 | CRF ISSUED 06-09-2025 | 25-08-2025 | 01-09-2025 | 01-09-2025 | 02-09-2025 | 02-09-2025 | GRB ARR 03-09-2025 | GRB DSP 04-09-2025 | FRANCISTOWN 04-08-2025 | KAZUNGULA 05-09-2025 | 10-09-2025 | 11-09-2025 | 11-09-2025 | 16-09-2025 | 18-09-2025 | 18-09-2025 | 23-09-2025 | 23-09-2025 | 24-09-2025 | 24-09-2025 | 28-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 20-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | VESSEL ARRIVED AM TODAY 25-08-2025 - AWAITING COMPLETION OF DISCHARGE | VESSEL STILL DISCHARGING CARGO | COLLECTING THE CONTAINER FROM PORT TODAY | COLLECTED FROM PORT - AWAITING BV INSPECTION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | PN RECEIVE TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | MARTINS DRIFT BW - AWAITING RELEASE | NATA ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KALOMO ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | LUSAKA TO DISPATCH FOR NDOLA | NDOLA DOING MANTANANCE CHECK ON VEHICLE | CHILILABOMBWE | CHILILABOMBWE - AWAITING CLEARANCE TO PROCEED TO KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE - CLEARING | KASUMBALESA BORDER ZAMBIAN SIDE - CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 28-09-2025
BA2925 | CATERPILLAR DISEL GENERATOR SET IN CONTAINER # XHCU527909/0 | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003027034 | LY300433 | CAT3516BJLY300433 |  | FML2507DSI2702 | COD 2025 260375 | BCE9005ZM | BCH2068ZM | 2507DSI2702B | VESSEL: JOLLY ARGENTO Voy. 25225 - ETA DURBAN: 25-08-2025 | OFFLOADED 29-09-2025 | 20-08-2025 | 29-08-2025 | 30-09-2025 | 03-09-2025 | CRF ISSUED 03-09-2025 | 25-08-2025 | 01-09-2025 | 01-09-2025 | 02-09-2025 | 02-09-2025 | GRB ARR 03-09-2025 | GRB DSP 04-09-2025 | FRANCISTOWN 04-08-2025 | KAZUNGULA 05-09-2025 | 10-09-2025 | 10-09-2025 | 10-09-2025 | 16-09-2025 | 18-09-2025 | 18-09-2025 | 23-09-2025 | 23-09-2025 | 24-09-2025 | 24-09-2025 | 29-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 20-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | VESSEL ARRIVED AM TODAY 25-08-2025 - AWAITING COMPLETION OF DISCHARGE | VESSEL STILL DISCHARGING CARGO | COLLECTING THE CONTAINER FROM PORT TODAY | COLLECTED FROM PORT - AWAITING BV INSPECTION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | PN RECEIVE TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | MARTINS DRIFT BW - AWAITING RELEASE | SEBUTU ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KALOMO ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | NDOLA DOING MANTANANCE CHECK ON VEHICLE | NDOLA DOING MANTANANCE CHECK ON VEHICLE | CHILILABOMBWE | CHILILABOMBWE - AWAITING CLEARANCE TO PROCEED TO KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE - CLEARING | KASUMBALESA BORDER DRC SIDE - AWAITING RELEASE TO PROCEED TO WHISKEY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 29-09-2025
BA2926 | CATERPILLAR DISEL GENERATOR SET IN CONTAINER # KSBU008233/3 | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003027034 | LY300434 | CAT3516BCLY300434 |  | FML2507DSI2702 | COD 2025 260367 | BCD3140ZM | BCH2089ZM | 2507DSI2702C | VESSEL: JOLLY ARGENTO Voy. 25225 - ETA DURBAN: 25-08-2025 | OFFLOADED 26-09-2025 | 20-08-2025 | 29-08-2025 | 02-09-2025 | 02-09-2025 | CRF ISSUED 02-09-2025 | 25-08-2025 | 02-09-2025 | 02-09-2025 | 03-09-2025 | 02-09-2025 | GRB ARR 03-09-2025 | GRB DSP 06-09-2025 | FRANCISTOWN 06-08-2025 | KAZUNGULA 07-09-2025 | 10-09-2025 | 11-09-2025 | 11-09-2025 | 16-09-2025 | 18-09-2025 | 18-09-2025 | 23-09-2025 | 23-09-2025 | 24-09-2025 | 24-09-2025 | 26-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 20-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | VESSEL ARRIVED AM TODAY 25-08-2025 - AWAITING COMPLETION OF DISCHARGE | VESSEL STILL DISCHARGING CARGO | COLLECTING THE CONTAINER FROM PORT TODAY | COLLECTED FROM PORT - AWAITING BV INSPECTION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING BV RELEASE | AWAITING PN / BV RELEASE | BELA BELA ENROUTE GROBLERS BIRDGE BORDER | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | PEMBA ENROUTE LUSAKA | KAFUE ENROUTE NDOLA | KABWE ENROUTE NDOLA | NDOLA DOING MANTANANCE CHECK ON VEHICLE | CHILILABOMBWE | CHILILABOMBWE - AWAITING CLEARANCE TO PROCEED TO KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE - CLEARING | KASUMBALESA BORDER DRC SIDE - AWAITING RELEASE TO PROCEED TO WHISKEY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 26-09-2025
BA2927 | CATERPILLAR DISEL GENERATOR SET IN CONTAINER # LYGU102218/3 | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003027034 | LY300439 | CAT3516BELY300439 |  | FML2507DSI2702 | COD 2025 260320 | BCG6130ZM | BCE92ZM | 2507DSI2702D | VESSEL: JOLLY ARGENTO Voy. 25225 - ETA DURBAN: 25-08-2025 | OFFLOADED 26-09-2025 | 20-08-2025 | 29-08-2025 | 02-09-2025 | 02-09-2025 | CRF ISSUED 02-09-2025 | 25-08-2025 | 02-09-2025 | 02-09-2025 | 03-09-2025 | 02-09-2025 | GRB ARR 03-09-2025 | GRB DSP 06-09-2025 | FRANCISTOWN 06-08-2025 | KAZUNGULA 07-09-2025 | 10-09-2025 | 10-09-2025 | 10-09-2025 | 16-09-2025 | 18-09-2025 | 18-09-2025 | 23-09-2025 | 23-09-2025 | 24-09-2025 | 24-09-2025 | 26-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 20-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | VESSEL ARRIVED AM TODAY 25-08-2025 - AWAITING COMPLETION OF DISCHARGE | VESSEL STILL DISCHARGING CARGO | COLLECTING THE CONTAINER FROM PORT TODAY | COLLECTED FROM PORT - AWAITING BV INSPECTION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING BV RELEASE | AWAITING PN / BV RELEASE | BELA BELA ENROUTE GROBLERS BIRDGE BORDER | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | MONZE ENROUTE LUSAKA | KAPIRI ENROUTE NDOLA | NDOLA DOING MANTANANCE CHECK ON VEHICLE | NDOLA DOING MANTANANCE CHECK ON VEHICLE | CHILILABOMBWE | CHILILABOMBWE - AWAITING CLEARANCE TO PROCEED TO KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE - CLEARING | KASUMBALESA BORDER DRC SIDE - AWAITING RELEASE TO PROCEED TO WHISKEY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 26-09-2025
BA2928 | CATERPILLAR DISEL GENERATOR SET IN CONTAINER # KSBU006939/4 | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003027034 | LY300440 | CAT3516BPLY300440 |  | FML2507DSI2702 | COD 2025 261925 | BCE9065ZM | BCH2073ZM | 2507DSI2702E | VESSEL: JOLLY ARGENTO Voy. 25225 - ETA DURBAN: 25-08-2025 | OFFLOADED 29-09-2025 | 25-08-2025 | 29-08-2025 | 30-09-2025 | 03-09-2025 | CRF ISSUED 03-09-2025 | 25-08-2025 | 01-09-2025 | 01-09-2025 | 02-09-2025 | 02-09-2025 | GRB ARR 03-09-2025 | GRB DSP 03-09-2025 | FRANCISTOWN 04-08-2025 | KAZUNGULA 04-09-2025 | 10-09-2025 | 10-09-2025 | 10-09-2025 | 16-09-2025 | 17-09-2025 | 17-09-2025 | 23-09-2025 | 23-09-2025 | 24-09-2025 | 24-09-2025 | 29-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 20-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | VESSEL ARRIVED AM TODAY 25-08-2025 - AWAITING COMPLETION OF DISCHARGE | VESSEL STILL DISCHARGING CARGO | COLLECTING THE CONTAINER FROM PORT TODAY | COLLECTED FROM PORT - AWAITING BV INSPECTION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | PN RECEIVE TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KALOMO ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | NDOLA DOING MANTANANCE CHECK ON VEHICLE | NDOLA DOING MANTANANCE CHECK ON VEHICLE | BALUBA ENROUTE CHILILABOMBWE | CHILILABOMBWE - AWAITING CLEARANCE TO PROCEED TO KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE - CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 5 | WHISKEY AWAITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 29-09-2025
BA2929 | CATERPILLAR DISEL GENERATOR SET IN CONTAINER # XHCU523931/2 | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003027034 | LY300442 | CAT3516BELY300442 |  | FML2507DSI2702 | COD 2025 260311 | BCF1094ZM | BCF6246ZM | 2507DSI2702F | VESSEL: JOLLY ARGENTO Voy. 25225 - ETA DURBAN: 25-08-2025 | OFFLOADED 26-09-2025 | 20-08-2025 | 29-08-2025 | 02-09-2025 | 05-09-2025 | CRF ISSUED 05-09-2025 | 25-08-2025 | 02-09-2025 | 02-09-2025 | 03-09-2025 | 02-09-2025 | GRB ARR 03-09-2025 | GRB DSP 06-09-2025 | FRANCISTOWN 06-08-2025 | KAZUNGULA 07-09-2025 | 10-09-2025 | 11-09-2025 | 11-09-2025 | 16-09-2025 | 18-09-2025 | 18-09-2025 | 23-09-2025 | 23-09-2025 | 24-09-2025 | 24-09-2025 | 26-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 20-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | VESSEL ARRIVED AM TODAY 25-08-2025 - AWAITING COMPLETION OF DISCHARGE | VESSEL STILL DISCHARGING CARGO | COLLECTING THE CONTAINER FROM PORT TODAY | COLLECTED FROM PORT - AWAITING BV INSPECTION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING BV RELEASE | AWAITING PN / BV RELEASE | BELA BELA ENROUTE GROBLERS BIRDGE BORDER | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | MAZABUKA ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | LUSAKA TO DISPATCH FOR NDOLA | NDOLA DOING MANTANANCE CHECK ON VEHICLE | NDOLA DOING MANTANANCE CHECK ON VEHICLE | CHILILABOMBWE - AWAITING CLEARANCE TO PROCEED TO KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE - CLEARING | KASUMBALESA BORDER ZAMBIAN SIDE - CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 26-09-2025
BA2930 | CATERPILLAR DISEL GENERATOR SET IN CONTANER # MCCU301114/9 | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003027034 | LY300441 | CAT3516BHLY300441 |  | FML2507DSI2702 | COD 2025 260310 | BCD3412ZM | BCH2064ZM | 2507DSI2702G | VESSEL: JOLLY ARGENTO Voy. 25225 - ETA DURBAN: 25-08-2025 | OFFLOADED 27-09-2025 | 20-08-2025 | 29-08-2025 | 03-09-2025 | 02-09-2025 | CRF ISSUED 02-09-2025 | 25-08-2025 | 02-09-2025 | 02-09-2025 | 03-09-2025 | 02-09-2025 | GRB ARR 03-09-2025 | GRB DSP 06-09-2025 | FRANCISTOWN 06-08-2025 | KAZUNGULA 07-09-2025 | 09-09-2025 | 11-09-2025 | 11-09-2025 | 16-09-2025 | 18-09-2025 | 18-09-2025 | 23-09-2025 | 23-09-2025 | 24-09-2025 | 24-09-2025 | 27-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 20-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 21-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 24-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 25-08-2025 | VESSEL ARRIVED AM TODAY 25-08-2025 - AWAITING COMPLETION OF DISCHARGE | VESSEL STILL DISCHARGING CARGO | COLLECTING THE CONTAINER FROM PORT TODAY | COLLECTED FROM PORT - AWAITING BV INSPECTION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING BV RELEASE | AWAITING PN / BV RELEASE | BELA BELA ENROUTE GROBLERS BIRDGE BORDER | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | GROBLERS BRIDGE BORDER RSA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | LIVINGSTON ENROUTE LUSAKA | CHIBOMBO ENROUTE NDOLA | NDOLA DOING MANTANANCE CHECK ON VEHICLE | NDOLA DOING MANTANANCE CHECK ON VEHICLE | CHAMBISHI ENROUTE CHILILABOMBWE | CHILILABOMBWE - AWAITING CLEARANCE TO PROCEED TO KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE - CLEARING | KASUMBALESA BORDER DRC SIDE - AWAITING RELEASE TO PROCEED TO WHISKEY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 27-09-2025
BA2942 | CAT777 OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003078782 | 7W805361 | CAT00777A7W805361 | ZRK02225 | FML2507DSI2705 | COD 2025 255911 | CM09LLZN | CN32HBZN / CM09LKZN | ND60663 | VESSEL: GLOVIS SAFETY Voy.54A - TRANSHIPMENT VESSEL: GLOVIS SUNRISE Voy. 073 - ETA DURBAN: 18-08-2025 | OFFLOADED 11-10-2025 | 18-08-2025 | 27-08-2025 | 29-08-2025 | 02-09-2025 | CRF ISSUED 02-09-2025 | 18-08-2025 | 02-09-2025 | 10-09-2025 | 11-09-2025 | 16-09-2025 | 18-09-2025 | 21-09-2025 | 22-09-2025 | 26-09-2025 | 29-09-2025 | 29-09-2025 | 29-09-2025 | 30-09-2025 | 01-10-2025 | 02-10-2025 | 08-10-2025 | 08-10-2025 | 09-10-2025 | 09-10-2025 | 11-10-2025 |  |  | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - UNIT DISCHARGED FROM VESSEL, AWAITING BOOKING CONFIRMATION TO COLLECT THE UNIT FROM PORT | LOADING FROM PORT TODAY | LOADING FROM PORT TODAY | AWAITING CONFIRMATION ON BV INSPECTION DATE | BV INSPECTION BOOKED FOR THURSDAY - AWAITING CONFIMRATION FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING BV RELEASE | BV INSPECTION COMPLETED - AWAITING BV RELEASE | DURBAN - STILL WAITING FOR BV RELEASE | DISPATCHING DURBAN TODAY - POLICE ECORT TO ASSIST AM TODAY | PIETERMARITZBURG - AWAITING POLICE ESCORT | WEENEN ENROUTE BEIT BRIDGE BORDER | VAN REENEN ENROUTE BEIT BRIDGE BORDER | VAN REENEN AWAITING POLICE ESCORTS | VAN REENEN AWAITING PERMITS AND PORICE EXCORTS | HARRISMITH AWAITING POLICE ESCORTS | HEIDELBERG ENROUTE BEIT BRIDGE BORDER | ROETAN ENROUTE BEIT BRIDGE BORDER | ROETAN AWAITING POLICE ESCORT TO PROCEED TO BEIT BRIDGE BORDER | POLOKWANE AWAITING POLICE ESCORT TO PROCEED TO BEIT BRIDGE BORDER | DISPATCHING DENDRON PROCEED TO BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE AWAITING RELEASE TO CROSS TO ZIM SIDE | MASVINGO ENROUTE HARARE | HARARE ENROUTE CHIRUNDU BORDER | MAKUTI ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE CLEARING | LUSAKA ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 5 | WHISKEY AWAITING RELEASE - DAY 6 PLEASE ASSIST WITH RELEASE | KANYAKA ENROUTE KOLWEZI | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 11-10-2025
BA2943 | CAT777 OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003078782 | 7W805362 | CAT00777L7W805362 | ZRK02227 | FML2507DSI2706 | COD 2025 255904 | CD46KBZN | CT37XGZN | ND60664 | VESSEL: GLOVIS SAFETY Voy.54A - TRANSHIPMENT VESSEL: GLOVIS SUNRISE Voy. 073 - ETA DURBAN: 18-08-2025 | OFFLOADED 11-10-2025 | 18-08-2025 | 27-08-2025 | 27-08-2025 | 11-09-2025 | CRF ISSUED 11-09-2025 | 18-08-2025 | 02-09-2025 | 10-09-2025 | 11-09-2025 | 16-09-2025 | 18-09-2025 | 21-09-2025 | 22-09-2025 | 26-09-2025 | 30-09-2025 | 30-09-2025 | 01-10-2025 | 01-10-2025 | 05-10-2025 | 06-10-2025 | 08-10-2025 | 08-10-2025 | 09-10-2025 | 09-10-2025 | 11-10-2025 |  |  | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - UNIT DISCHARGED FROM VESSEL, AWAITING BOOKING CONFIRMATION TO COLLECT THE UNIT FROM PORT | LOADED YESTERDAY - AWAITING PERMIT AND POLISE ESCORTS | AWAITING POLISE ESCORTS | LOADED AWAITING POLISE ESCORTS | LOADED - POLISE ESCORTS TO ASSIST THIS MORNING - BV INSPECTION BOOKED FOR THURSDAY - AWAITING CONFIRMATION FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING BV RELEASE | BV INSPECTION COMPLETED - AWAITING BV RELEASE | DURBAN - STILL WAITING FOR BV RELEASE | DISPATCHING DURBAN TODAY - POLICE ECORT TO ASSIST AM TODAY | PIETERMARITZBURG - AWAITING POLICE ESCORT | WEENEN ENROUTE BEIT BRIDGE BORDER | VAN REENEN ENROUTE BEIT BRIDGE BORDER | VAN REENEN AWAITING POLICE ESCORTS | VAN REENEN AWAITING PERMITS AND PORICE EXCORTS | HARRISMITH AWAITING POLICE ESCORTS | HEIDELBERG ENROUTE BEIT BRIDGE BORDER | ROETAN ENROUTE BEIT BRIDGE BORDER | ROETAN AWAITING POLICE ESCORT TO PROCEED TO BEIT BRIDGE BORDER | POLOKWANE AWAITING POLICE ESCORT TO PROCEED TO BEIT BRIDGE BORDER | DISPATCHING DENDRON PROCEED TO BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE AWAITING RELEASE TO CROSS TO ZIM SIDE | MASVINGO ENROUTE HARARE | HARARE ENROUTE CHIRUNDU BORDER | MAKUTI ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE CLEARING | SIYAVONGA ENROUTE KASUMBALESA BORDER | LUSAKA ENROUTE KASUMBALESA BORDER | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER DRC SIDE CLEARING | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 PLEASE ASSIST WITH RELEASE | KANYAKA ENROUTE KOLWEZI | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 11-10-2025
BA2944 | CAT777 OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003078782 | 7W805363 | CAT00777H7W805363 | ZRK02226 | FML2507DSI2707 | COD 2025 255895 | CT37XKZN | ND654346 / ND526680 | ND60665 | VESSEL: GLOVIS SAFETY Voy.54A - TRANSHIPMENT VESSEL: GLOVIS SUNRISE Voy. 073 - ETA DURBAN: 18-08-2025 | OFFLOADED 11-10-2025 | 18-08-2025 | 27-08-2025 | 29-09-2025 | 04-09-2025 | CRF ISSUED 04-09-2025 | 18-08-2025 | 02-09-2025 | 10-09-2025 | 11-09-2025 | 16-09-2025 | 18-09-2025 | 22-09-2025 | 22-09-2025 | 26-09-2025 | 30-09-2025 | 30-09-2025 | 01-10-2025 | 01-10-2025 | 05-10-2025 | 06-10-2025 | 08-10-2025 | 08-10-2025 | 09-10-2025 | 09-10-2025 | 11-10-2025 |  |  | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-08-2025 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - UNIT DISCHARGED FROM VESSEL, AWAITING BOOKING CONFIRMATION TO COLLECT THE UNIT FROM PORT | IN PORT LOADING TOMORROW | LOADING FROM PORT TODAY | LOADED AWAITING POLISE ESCORTS | LOADED - POLISE ESCORTS TO ASSIST THIS MORNING - BV INSPECTION BOOKED FOR THURSDAY - AWAITING CONFIRMATION FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING BV RELEASE | BV INSPECTION COMPLETED - AWAITING BV RELEASE | DURBAN - BV RELEASE RECEIVED - AWAITING POLICE ESCORT | DISPATCHING DURBAN TODAY - POLICE ECORT TO ASSIST AM TODAY | PIETERMARITZBURG - AWAITING POLICE ESCORT | WEENEN ENROUTE BEIT BRIDGE BORDER | VAN REENEN ENROUTE BEIT BRIDGE BORDER | VAN REENEN AWAITING POLICE ESCORTS | VAN REENEN AWAITING PERMITS AND PORICE EXCORTS | HARRISMITH AWAITING POLICE ESCORTS | HEIDELBERG ENROUTE BEIT BRIDGE BORDER | ROETAN ENROUTE BEIT BRIDGE BORDER | ROETAN AWAITING POLICE ESCORT TO PROCEED TO BEIT BRIDGE BORDER | POLOKWANE AWAITING POLICE ESCORT TO PROCEED TO BEIT BRIDGE BORDER | DISPATCHING DENDRON PROCEED TO BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE AWAITING RELEASE TO CROSS TO ZIM SIDE | BEIT BRIDGE BORDER ZIM SIDE | HARARE ENROUTE CHIRUNDU BORDER | MAKUTI ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE CLEARING | SIYAVONGA ENROUTE KASUMBALESA BORDER | LUSAKA ENROUTE KASUMBALESA BORDER | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER DRC SIDE CLEARING | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 PLEASE ASSIST WITH RELEASE | KANYAKA ENROUTE KOLWEZI | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 11-10-2025
BA2946 | CAT16 MOTOR GRADER | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003084295-2 | EB900261 | CAT00016EEB900261 | P4E06805 | FML2509DSI2718 | COD 2025 301724 | ND760431 | CT37XGZN | ND60793 | VESSEL: GUI JIANG KOU Voy. 004 - ETA DURBAN: 10-10-2025 | OFFLOADED 14-11-2025 | 15-10-2025 | 27-10-2025 | 28-11-2025 | 04-11-2025 | CRF ISSUE 04-11-2025 | 10-10-2025 | 28-10-2025 | MIDDELBURG 30-10-2025 | MIDDELBURG 30-10-2025 | 31-10-2025 | 31-10-2025 | 02-11-2025 | 03-11-2025 | 04-11-2025 | 08-11-2025 | 08-11-2025 | 09-11-2025 | 09-11-2025 | 10-11-2025 | 11-11-2025 | 13-11-2025 | 13-11-2025 | 13-11-2025 | 13-11-2025 | 14-11-2025 | [53 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 10-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 10-10-2025 | VESSEL ARRIVED 10-10-2025 - COLLECTING UNIT FROM PORT TODAY | UNIT COLLECTED FROM PORT - AWAITING BV NUMBER | UNIT COLLECTED FROM PORT - AWAITING BV NUMBER | BV NUMBER RECEIVED - BOOKING INSPECTION - TO CONFIRM INSPECTION DATE ONCE BV RSA CONFIRMS | AWAITING CONFIRMATION ON BV INSPECTION DATE | AWAITING CONFIRMATION ON BV INSPECTION DATE FROM BV RSA | AWAITING CONFIRMATION ON BV INSPECTION DATE FROM BV RSA - INSPECTION PLANNED FOR THUSDAY | BV INSPECTION BOOKED FOR TOMORROW 22-10-2025 | BV INSPECTION MOVED TO FRIDAY | AWAITING BV INSPECTION | AWAITING BV RELEASE - TO DISPATCH ONCE BV RELEASE RECEIVED | AWAITING PERMIT AND BV RELEASE | AMERSFOORT ENROUTE BEIT BRIDGE BORDER | MIDDELBURG ENROUTE BEIT BRIDGE BORDER | POLOKWANE ENROUTE BEIT BRIDGE BORDER | HARARE ENROUTE CHIRUNDU | CHINOYI ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE | CHIRUNDU ZAMBIAN SIDE - AWAITING RELEASE AND PERMIT | CHIRUNDU ZAMBIAN SIDE - AWAITING RELEASE | KASUMBALESA BORDER ZAMBIAN SIDE | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | KANYAKA ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 14-11-2025
BA2958 | CAT D9GC-03B TRACTOR - MAIN UNIT | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003189922 | AK401084 | CAT000D9LAK401084 | TNR00981 | FML2510DSI2725 | COD 2025 329441 | BT33NKZN | KW72PLGP | 2510DSI2725A | VESSEL: GRAND CHAMPION Voy. 0011A - ETA DURBAN PORT: 24-11-2025 | OFFLOADED 19-12-2025 | 26-11-2025 | 01-12-2025 | 01-12-2025 | 03-12-2025 | CRF ISSUE DATE 03-1-2025 | 24-11-2025 | 27-11-2025 | PRETORIA 28-11-2025 | PRETORIA 02-12-2025 | 02-12-2025 | 02-12-2025 | 04-12-2025 | 05-12-2025 | 05-12-2025 | 08-12-2025 | 08-12-2025 | 08-12-2025 | 09-12-2025 | 10-12-2025 | 11-12-2025 | 17-11-2025 | 18-12-2025 | 18-12-2025 | 18-12-2025 | 19-12-2025 | [80 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA DURBAN PORT: 25-11-2025 | VESSEL IN AND WORKING - PLEASE FORWARD THE BV & FIX NUMBERS | LOADING FROM PORT TODAY | LOADED FROM PORT - BV INSPECTION PLANNED FOR MONDAY 01-12-2025 | BETHAL ENROUTE PRETORIA - BV INSPECTION PLANNED FOR MONDAY 01-12-2025 | PRETORIA - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - DISPATCHING PRETORIA TODAY TO PROCEED TO BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER ZIM SIDE WAITING RELEASE | CHEGUTU ENROUTE CHIRUNDU | LUSAKA ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 5 | WHISKEY AWAITING RELEASE - DAY 7 | KANYAKA ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-12-2025
BA2958 | CAT D9GC-03B TRACTOR - PARTS/ACCESSORIES | BARTRAC EQUIPMENT / MUTANDA MINING SALR | C003189922 | AK401084 | CAT000D9LAK401084 | TNR00981 | FML2510DSI2725 | COD 2025 329441 | KL63XPGP | KG93XNGP | 2510DSI2725B | VESSEL: GRAND CHAMPION Voy. 0011A - ETA DURBAN PORT: 24-11-2025 | OFFLOADED 05-01-2026 | 26-11-2025 | 01-12-2025 | 01-12-2025 | 03-12-2025 | CRF ISSUE DATE 03-1-2025 | 24-11-2025 | 28-11-2025 | PRETORIA 29-11-2025 | PRETORIA 04-12-2025 | 04-12-2025 | 04-12-2025 | 07-12-2025 | 08-12-2025 | 10-12-2025 | 15-12-2025 | 16-12-2025 | 17-12-2025 | 19-12-2025 | 23-12-2025 | 23-12-2025 | 29-12-2025 | 31-12-2025 | 31-12-2025 | 01-01-2026 | 05-01-2026 | [80 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA DURBAN PORT: 25-11-2025 | VESSEL IN AND WORKING - PLEASE FORWARD THE BV & FIX NUMBERS | LOADING FROM PORT TODAY | LOADING TODAY FROM PORT - BV INSPECTION PLANNED FOR MONDAY 01-12-2025 | ESCOURT ENROUTE PRETORIA - BV INSPECTION PLANNED FOR MONDAY 01-12-2025 | PRETORIA - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - DISPATCHING PRETORIA TOMORROW | DISPATCHING PRETORIA TODAY | ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | MASVINGO ENROUTE HARARE | HARARE ENROUTE CHIRUNDU BORDER | KAROI ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE CLEARING - AWAYTING RELEASE | KITWE ENROUTE KASUMBALESA | CHILIBOMBWE IN THE QUE TO KASUMBALESA | KASUMBALESA IN THE QUE TO CROSS TO DRC SIDE | KASUMBALESA STILL IN THE QUE TO CROSS TO DRC SIDE | KASUMBALESA STILL IN THE QUE TO CROSS TO DRC SIDE - BORDER CONGESTED | WHISKEY AWAITING FINAL RELEASE - DAY 1 | WHISKEY AWAITING FINAL RELEASE - DAY 6 - PLEASE ASSIST WITH RELEASE | KANYAKA ENROUTE KOLWEZI | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 - PLEASE ASSIST | OFFLOADED 05-01-2026