## CURRENT SHIPMENTS
CLIENT INVOICE NR | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | DBN ARR | DBN DISP | CAPE TOWN ARR | ON SITE ARRIVE | OFFLOADED | COMMENTS 13-01-2026 | COMMENTS 15-01-2026 | COMMENTS 16-01-2026 | COMMENTS 19-01-2026 | COMMENTS 20-01-2026 | COMMENTS 21-01-2026 | COMMENTS 22-01-2026 | COMMENTS 14-01-2026 | DATE RECEIVED INTO BONDED FACILITY | REMOVAL FROM BOND REQUIRED DATE ON OR BEFORE | BOND EXPIRY DATE | HANDLING IN | HANDLING OUT | JANUARY 2026 - STORAGE PER MONTH @ R250 PER DAY PER UNIT (7 DAYS FREE STORAGE ) | FEBRUARY 2026 - STORAGE PER MONTH @ R250 PER DAY PER UNIT (7 DAYS FREE STORAGE ) | MARCH 2026 - STORAGE PER MONTH @ R250 PER DAY PER UNIT (7 DAYS FREE STORAGE ) | NUMBER OF DAYS STORED UNTIL END OF FEBRUARY 2026 | TOTAL COST PER UNIT
INV,2551059288 | CASE885 GRADER | CASE CONTRUCTIONS / KANU EQUIPMENT | NSAF10899 | HBZN885CHASF10899 | 6330873 | 2512DSI2750 |  |  |  | VESSEL: NEPTUNE ACE Voy. 0119A - ETA DURBAN: 10-01-2026 | AT BONDED FACILITY 13-01-2026 | 10-01-2026 |  |  |  |  | DELIVERING TO PORT TODAY | AT BONDED FACILITY 13-01-2026 | AT BONDED FACILITY 13-01-2026 | AT BONDED FACILITY 13-01-2026 | AT BONDED FACILITY 13-01-2026 | AT BONDED FACILITY 13-01-2026 | AT BONDED FACILITY 13-01-2026 | AT BONDED FACILITY 13-01-2026 | 13-01-2026 | 07-06-2026 | 07-07-2026 | 5100 | 5100 | 3000 | 7000 | 500 | 2 | 20700 | 2
INV,2551059294 | CASE885 GRADER | CASE CONTRUCTIONS / KANU EQUIPMENT | NSAF10925 | HBZN885CPSAF10925 | 6331830 | 2512DSI2750 |  |  |  | VESSEL: NEPTUNE ACE Voy. 0119A - ETA DURBAN: 10-01-2026 | AT BONDED FACILITY 12-01-2026 | 10-01-2025 |  |  |  |  | AT BONDED FACILITY 12-01-2026 | AT BONDED FACILITY 12-01-2026 | AT BONDED FACILITY 12-01-2026 | AT BONDED FACILITY 12-01-2026 | AT BONDED FACILITY 12-01-2026 | AT BONDED FACILITY 12-01-2026 | AT BONDED FACILITY 12-01-2026 | AT BONDED FACILITY 12-01-2026 | 12-01-2026 | 07-06-2026 | 07-07-2026 | 5100 | 5100 | 3250 | 7000 | 500 | 2 | 20950 | 2

## OFFLOADED 2025
CLIENT INVOICE NR | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | DBN ARR | DBN DISP | CAPE TOWN ARR | ON SITE ARRIVE | OFFLOADED | COMMENTS -11-02-2025 | COMMENTS 12-02-2025 | COMMENTS 13-02-2025 | COMMENTS 14-02-2025 | DATE RECEIVED INTO BONDED FACILITY | REMOVAL FROM BOND REQUIRED DATE ON OR BEFORE | BOND EXPIRY DATE | HANDLING | JANUARY 2025 - STORAGE PER MONTH @ R200 PER DAY PER UNIT (10 DAYS FREE STORAGE ) | JANUARY 2025 - STORAGE PER MONTH @ R200 PER DAY PER UNIT (10 DAYS FREE STORAGE ) | NUMBER OF DAYS STORED UNTIL END OF JANUARY 2025 | TOTAL COST PER UNIT
| CASE CX220 CRAWLER EXCAVATOR | KANU EQUIPMENT | VRKA01287 | NKJ22CLMVRKA01287 | 6247864 | 2501DSI2654 | KIYARA - ZN | BB35DY-ZN |  | VESSEL: CATTLEYA ACE Voy. 0099A - ETA DURBAN: 18-01-2025 | OFFLOADED 13-02-2025 | 18-01-2025 | 11-02-2025 | 13-02-2025 | 13-02-2025 | 13-02-2025 | DISPATCHING DURBAN | HANOVER ENROUTE CAPE TOWN | VEHICLE TO ARRIVE ON SITE TODAY FOR OFFLOADING | OFFLOADED 13-02-2025 | 21-01-2025 | 15-06-2025 | 15-07-2025 | 5100 | 200 | 2000 | 21 | 7300 | 10
| CASE CX220 CRAWLER EXCAVATOR | KANU EQUIPMENT | ARKA01288 | NKJ22CLMARKA01288 | 6252977 | 2501DSI2654 | BS53XH-AN | NUR 60835 |  | VESSEL: CATTLEYA ACE Voy. 0099A - ETA DURBAN: 18-01-2025 | OFFLOADED 14-02-2025 | 18-01-2025 | 12-02-2025 | 14-02-2025 | 14-02-2025 | 14-02-2025 | DISPATCHING DURBAN | AWAITING PERMIT BEFORE DISPATCHING | BLOEMFONTEIN ENROUTE CAPE TOWN | BEAUFORT WEST ENROUTE CAPE TOWN | OFFLOADED 14-02-2025 | 21-01-2025 | 15-06-2025 | 15-07-2025 | 5100 | 200 | 0 | 11 | 5300
| CASE 821F WHEEL LOADER | KANU EQUIPMENT | NZHE16994 | FNH821F1NZHE16994 | TBA | 2502DSI2673 | BJ68NDZN | ND320772 |  | VESSEL: HOEGH TRIGGER Voy. 54 - ETA DURBAN: 23-02-2025 | OFFLOADED 20-06-2025 | 23-02-2025 |  |  |  |  | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2025 | VESSEL ARRIVED YESTERDAY - UNIT TO BE COLLECTED FROM PORT TODAY | VESSEL ARRIVED YESTERDAY - UNIT TO BE COLLECTED FROM PORT TODAY | UNIT AT BONDED FACILITY | 24-02-2025 | 18-07-2025 | 18-08-2025 | 5100 | 5 FREE DAYS | 6750 | 7500 | 7750 | 0 | 98 | 27100
| CASE 821F WHEEL LOADER | KANU EQUIPMENT | NZHE16995 | FNH821F1NZHE16995 | TBA | 2502DSI2673 | BF77JSZN | CS10MSZN |  | VESSEL: HOEGH TRIGGER Voy. 54 - ETA DURBAN: 23-02-2025 | OFFLOADED 20-06-2025 | 23-02-2025 |  |  |  |  | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2025 | VESSEL ARRIVED YESTERDAY - UNIT TO BE COLLECTED FROM PORT TODAY | VESSEL ARRIVED YESTERDAY - UNIT TO BE COLLECTED FROM PORT TODAY | UNIT AT BONDED FACILITY | 25-02-2025 | 18-07-2025 | 18-08-2025 | 5100 | 4 FREE DAYS | 6500 | 7500 | 7750 | 0 | 97 | 26850
SIN2509S3302757 | CASE885B MOTOR GRADER | CNHI INTERNATIONAL / EQUIPMENT SALES (KANU EQUIPMENT) | NSAF10830 | HBZN885CPSAF10830 | 6327918 | 2509DSI2719 |  |  |  | VESSEL: PARADISE ACE Voy. 0161A - ETA DURBAN: 05-10-2025 | UNIT COLLECTED FROM PORT - TO BE DELIVERED TODAY | 08-10-2025 |  |  |  |  | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 075-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-10-2025 | VESSEL DUE TO BIRTH TODAY | VESSEL IN AND WORKING | UNIT COLLECTED FROM PORT - TO BE DELIVERED TODAY | DELIVERED 10-10-2025
TBA | CASE885B MOTOR GRADER | CNHI INTERNATIONAL / EQUIPMENT SALES (KANU EQUIPMENT) | KSAF10893 | HBZN885CKSAF10893 | 6330549 | 2510DSI2722 |  |  |  | VESSEL: ELEGANT ACE Voy. 0094A - ETA DURBAN: 29-10-2025 | COLLECTED FROM PORT 30-10-2025 - ARRIVED ON STIE 31-10-2025 - OFFLOADED 31-10-2025 | 29-10-2025 | 30-10-2025 |  | 31-10-2025 | 31-10-2025 | [7 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-10-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-10-2025 | VESSEL DUE TO ARRIVE TODAY | TO COLLECT THE UNIT FROM PORT | COLLECTED FROM PORT 30-10-2025 - ARRIVED ON STIE 31-10-2025 - OFFLOADED 31-10-2025

## REMOVED FROM WHSE
CLIENT INVOICE NR | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | DBN ARR | DBN DISP | HARRISMIRTH | JHB ARR | JHB DISP | RUSTENBURG | ZEERUST | KOPFONTEIN RSA SIDE | KOPFONTEIN BOTS SIDE | TLOKWENG | ON SITE OFFLOADED | COMMENTS 10-07-2024 | COMMENTS 11-07-2024 | COMMENTS 12-07-2024 | COMMENTS 15-07-2024 | COMMENTS 16-07-2024 | COMMENTS 17-07-2024 | COMMENTS 18-07-2024 | COMMENTS 19-07-2024 | COMMENTS 22-07-2024 | COMMENTS 23-07-2024 | COMMENTS 24-07-2024 | COMMENTS 25-07-2024 | COMMENTS 26-07-2024 | COMMENTS 29-07-2024 | COMMENTS 30-07-2024 | COMMENTS 31-07-2024 | COMMENTS 01-08-2024 | COMMENTS 02-08-2024 | COMMENTS 05-08-2024 | COMMENTS 06-08-2024 | COMMENTS 07-08-2024 | COMMENTS 08-08-2024 | COMMENTS 09-08-2024 | COMMENTS 12-08-2024 | COMMENTS 13-08-2024 | COMMENTS 14-08-2024 | COMMENTS 15-08-2024 | COMMENTS 16-08-2024 | COMMENTS 19-08-2024 | COMMENTS 20-08-2024 | COMMENTS 21-08-2024 | COMMENTS 22-08-2024 | COMMENTS 23-08-2024 | COMMENTS 26-08-2024 | COMMENTS 27-08-2024 | COMMENTS 28-08-2024 | COMMENTS 29-08-2024 | COMMENTS 30-08-2024 | COMMENTS 02-09-2024 | COMMENTS 03-09-2024 | COMMENTS 04-09-2024 | COMMENTS 05-09-2024 | COMMENTS 20-09-2024 | DATE RECEIVED INTO BONDED FACILITY | REMOVAL FROM BOND REQUIRED DATE ON OR BEFORE | BOND EXPIRY DATE | HANDLING | SEPTEMBER 2024 - STORAGE PER MONTH @ R200 PER DAY PER UNIT (10 DAYS FREE STORAGE ) | NUMBER OF DAYS STORED UNTIL END OF SEPTEMBER 2024
2451042619 | CASE 570V SS 4WD | CNHI INTERNATIONAL / KANU EQUIPMENT | HPKH36646 | NKJ0570VHPKH36646 | 45-418963 | FML2407DSI2557 |  |  |  | VESSEL: AS CHRISTIANA Voy. 428S - ETA DURBAN: 31-08-2024 | LOADED FROM WAREHOUSE 20-09-2024 | 31-08-2024 | [10 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 29-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | CONTAINER TO BE COLLECTED FROM PORT | UNIT AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | LOADED FROM WAREHOUSE 20-09-2024 | 03-09-2024 | 08-01-2025 | 08-02-2025 | 5100 | 1600 | 18 | 18
2451042592 | CASE 570V SS 4WD | CNHI INTERNATIONAL / KANU EQUIPMENT | VPKH36626 | NKJ0570VVPKH36626 | 45-419416 | FML2407DSI2557 |  |  |  | VESSEL: AS CHRISTIANA Voy. 428S - ETA DURBAN: 31-08-2024 | DELIVERED 10-10-2024 | 31-08-2024 | [10 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 29-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | CONTAINER TO BE COLLECTED FROM PORT | UNIT AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | 03-09-2024 | 08-01-2025 | 08-02-2025 | 5100 | 3600 | 0 | 28
2451042708 | CASE 570V SS 4WD | CNHI INTERNATIONAL / KANU EQUIPMENT | APKH36627 | NKJ0570VAPKH36627 | 45-419413 | FML2407DSI2557 |  |  |  | VESSEL: AS CHRISTIANA Voy. 428S - ETA DURBAN: 31-08-2024 | DELIVERED 15-10-2024 | 31-08-2024 | [10 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 29-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | CONTAINER TO BE COLLECTED FROM PORT | UNIT AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | 03-09-2024 | 08-01-2025 | 08-02-2025 | 5100 | 3600 | 0 | 28
2451042709 | CASE 570V SS 4WD | CNHI INTERNATIONAL / KANU EQUIPMENT | CPKH36634 | NKJ0570VCPKH36634 | 45-418266 | FML2407DSI2557 |  |  |  | VESSEL: AS CHRISTIANA Voy. 428S - ETA DURBAN: 31-08-2024 | DELIVERING TODAY 16-10-2024 | 31-08-2024 | [10 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 29-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | CONTAINER TO BE COLLECTED FROM PORT | UNIT AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | 03-09-2024 | 08-01-2025 | 08-02-2025 | 5100 | 3600 | 0 | 28

## OFFLOADED
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | DBN ARR | DBN DISP | HARRISMIRTH | JHB ARR | JHB DISP | RUSTENBURG | ZEERUST | KOPFONTEIN RSA SIDE | KOPFONTEIN BOTS SIDE | TLOKWENG | ON SITE OFFLOADED | COMMENTS 09-02-2024 | COMMENTS 12-02-2024 | COMMENTS 13-02-2024 | COMMENTS 14-02-2024 | COMMENTS 15-02-2024 | COMMENTS 16-02-2024 | COMMENTS 19-02-2024 | COMMENTS 20-02-2024 | COMMENTS 21-02-2024 | COMMENTS 22-02-2024 | COMMENTS 22-02-2024 | COMMENTS 23-02-2024 | COMMENTS 26-02-2024
| LIEBHERR CRAWLER EXCAVATOR | KANU EQUIPMENT | 58003 | WLHZ1786AZC58003 | 2023140192 | 2401DSI2355 | ND760431 | ND760424 / ND760428 | ND64648 | VESSEL: THALATTA Voy. EE324 - ETA 31-01-2024 | OFFLOADED 24-02-2024 | 31-01-2024 | 15-02-2024 | 21-02-2024 | 22-02-2024 | 23-02-2024 | 23-02-2024 | 23-02-2024 | 23-02-2024 | 24-02-2024 | 24-02-2024 | 24-02-2024 | DURBAN TO DISPATCH MODNAY | UNIT TO DISPATCH TODAY EN-ROUTE TO JHB | TRUCK IS AT OUR FACILITY IN DURBAN ONDERGOING TRIP CHECK BEFORE DISPATCH | TRUCK DISPATCHING DURBAN TODAY EN-ROUTE TO KOPFONTEIN | TRUCK AT MARIANHILL PLAZA EN-ROUTE TO JHB | TRUCK AT CATORIDGE-AWAITING POLICE ESCORTS IN ORDER TO MOVE TO JHB | TRUCK AT PIETERMARITZBURG ENROUTE KOPFONTEIN | PIETERMARITZBURG AWAITNIG PERMITS | VOLKSRUST ENROUTE KOPFONTEIN | ERMELO ENROUTE KOPFONTEIN | ERMELO ENROUTE KOPFONTEIN | PRETORIA | OFFLOADED 24-02-2024
| LIEBHERR CRAWLER EXCAVATOR | KANU EQUIPMENT | 58003 | WLHZ1786AZC58003 | 2023140192 | 2401DSI2355 | JF92ZTGP | BX45RWGP | ND64648-1 | VESSEL: THALATTA Voy. EE324 - ETA 31-01-2024 | OFFLOADED 24-02-2024 | 31-01-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 22-02-2024 | 22-02-2024 | 22-02-2024 | 23-02-2024 | 24-02-2024 | 24-02-2024 | 24-02-2024 | JOHANNESBURG | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | KOPFONTEIN AWAITING MAIN UNIT | OFFLOADED 24-02-2024
| LIEBHERR CRAWLER EXCAVATOR | KANU EQUIPMENT | 58003 | WLHZ1786AZC58003 | 2023140192 | 2401DSI2355 | JL87VXGP | MJW681GP | NA64648-2 | VESSEL: THALATTA Voy. EE324 - ETA 31-01-2024 | OFFLOADED 24-02-2024 | 31-01-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 22-02-2024 | 22-02-2024 | 22-02-2024 | 23-02-2024 | 24-02-2024 | 24-02-2024 | 24-02-2024 | JOHANNESBURG | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | KOPFONTEIN AWAITING MAIN UNIT | OFFLOADED 24-02-2024
| LIEBHERR CRAWLER EXCAVATOR | KANU EQUIPMENT | 57814 | WLHZ1786TZC57814 | 2023140165 | 2401DSI2356 | ND568309 | ND566910 / ND564162 | ND64647 | VESSEL: THALATTA Voy. EE324 - ETA 31-01-2024 | OFFLOADED 22-02-2024 | 31-01-2024 | 15-02-2024 | 20-02-2024 | 20-02-2024 | 21-02-2024 | 21-02-2024 | 22-02-2024 | 22-02-2024 | 22-02-2024 | 22-02-2024 | 22-02-2024 | DURBAN TO DISPATCH MODNAY | UNIT IN PORT LOADING TODAY | TRUCK IS AT OUR FACILITY IN DURBAN ONDERGOING TRIP CHECK BEFORE DISPATCH | TRUCK DISPATCHING DURBAN TODAY EN-ROUTE TO KOPFONTEIN | TRUCK AT MARIANHILL PLAZA EN-ROUTE TO JHB | TRUCK AT CATORIDGE-AWAITING POLICE ESCORTS IN ORDER TO MOVE TO JHB | TRUCK AT CATORIDGE-DISPATCHING TODAY | VOLKSRUST AWAITING PERMITS | RUSTENBURG ENROUTE KOPFONTEIN | KOPFONTEIN | KOPFONTEIN | OFFLOADED 22-02-2024 | OFFLOADED 22-02-2024
| LIEBHERR CRAWLER EXCAVATOR | KANU EQUIPMENT | 57814 | WLHZ1786TZC57814 | 2023140165 | 2401DSI2356 | KG17GNGP | HK48JKGP | ND64647-1 | VESSEL: THALATTA Voy. EE324 - ETA 31-01-2024 | OFFLOADED 24-02-2024 | 31-01-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 21-02-2024 | 21-02-2024 | 22-02-2024 | 22-02-2024 | 23-02-2024 | 24-02-2024 | 24-02-2024 | JOHANNESBURG | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | DISPATCHING JOHANNESBURG TODAY | KOPFONTEIN | KOPFONTEIN | KOPFONTEIN AWAITING CUSTOMS RELEASE | OFFLOADED 24-02-2024
| LIEBHERR CRAWLER EXCAVATOR | KANU EQUIPMENT | 57814 | WLHZ1786TZC57814 | 2023140165 | 2401DSI2356 | CW07CFGP | HTT398GP | ND64647-2 | VESSEL: THALATTA Voy. EE324 - ETA 31-01-2024 | OFFLOADED 24-02-2024 | 31-01-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 21-02-2024 | 21-02-2024 | 22-02-2024 | 22-02-2024 | 23-02-2024 | 24-02-2024 | 24-02-2024 | JOHANNESBURG | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | JOHANNESBURG AWAITING MAIN UNIT | DISPATCHING JOHANNESBURG TODAY | KOPFONTEIN | KOPFONTEIN | KOPFONTEIN AWAITING CUSTOMS RELEASE | OFFLOADED 24-02-2024
| 2451042820 | CASE 570V SS 4WD | CNHI INTERNATIONAL / KANU EQUIPMENT | CPKH36625 | NKJ0570VCPKH36625 | 45-419419 | FML2407DSI2557 | BN39KGZN | BK82PRZN |  | VESSEL: AS CHRISTIANA Voy. 428S - ETA DURBAN: 31-08-2024 | OFFLOADED 04-11-2024 | 31-08-2024 | 31-10-2024 | 01-11-2024 | [6 empty] | 02-11-2024 | 04-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 29-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER COLLECTED FROM PORT TO BE UNPACKED TODAY AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | 04-09-2024 | 08-01-2025 | 08-02-2025 | 5100 | 3400 | 6000 | 0 | 56
| 2451042828 | CASE 570V SS 4WD | CNHI INTERNATIONAL / KANU EQUIPMENT | LPKH36628 | NKJ0570VLPKH36628 | 45-419411 | FML2407DSI2557 | BN39KGZN | BK82PRZN |  | VESSEL: AS CHRISTIANA Voy. 428S - ETA DURBAN: 31-08-2024 | OFFLOADED 04-11-2024 | 31-08-2024 | 31-10-2024 | 01-11-2024 | [6 empty] | 02-11-2024 | 04-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 29-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-08-2024 | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER COLLECTED FROM PORT TO BE UNPACKED TODAY AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | UNIT AT FML BONDED FACILITY | 04-09-2024 | 08-01-2025 | 08-02-2025 | 5100 | 3400 | 6000 | 0 | 56
| DAR 15025558 | LIEBHERR L566 WHEEL LOADER - 1 UNIT & 1 PKGS | LIEBHERR MACHINERY / KANU EQUIPMENT | 74599 | VATZ1797CZD074599 | RG6090G040181 | FML2408DSI2566 |  |  |  | VESSEL: UNDINE Voy. 032 - ETA DURBAN: 04-09-2024 | OFFLOADED 25-12-2024 | 04-09-2024 | 12-12-2024 | 17-12-2024 | 17-12-2024 | 23-12-2024 | 23-12-2024 | 23-12-2024 | 23-12-2024 | 24-12-2024 |  | 25-12-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | VESSEL IN AND WORKING | UNIT RECIVED INTO BOND 05-09-2024 - LOADED OUT OF BOND 11-12-2024 | LOADED YESTERDAY - CURRENTLY ENROUTE KOPFONTEIN BORDER | GREYTOWN - ROAD CLOSED DUE TO A ACCIDENT | GREYTOWN - DISPATCHING FOR THE BORDER | JOHANNESBURG AWAITING PERMIT TO PROCEED TO KOPFONTEIN | JOHANNESBURG AWAITING CROSS BORDER PERMIT TO PROCEED TO KOPFONTEIN | JOHANNESBURG AWAITING CROSS BORDER PERMIT TO PROCEED TO KOPFONTEIN | JOHANNESBURG AWAITING CROSS BORDER PERMIT TO PROCEED TO KOPFONTEIN | KOPFONTEIN BORDER CLEARING | OFFLOADED 25-12-2024
| DAR 15025557 | LIEBHERR L566 WHEEL LOADER - 1 UNIT & 1 PKGS | LIEBHERR MACHINERY / KANU EQUIPMENT | 74600 | VATZ1797AZD074600 | RG6090G040185 | FML2408DSI2565 |  |  |  | VESSEL: UNDINE Voy. 032 - ETA DURBAN: 04-09-2024 | OFFLOADED 25-12-2024 | 04-09-2024 | 12-12-2024 | 17-12-2024 | 17-12-2024 | 23-12-2024 | 23-12-2024 | 23-12-2024 | 23-12-2024 | 24-12-2024 |  | 25-12-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-09-2024 | VESSEL IN AND WORKING | UNIT RECIVED INTO BOND 05-09-2024 - LOADED OUT OF BOND 11-12-2024 | LOADED YESTERDAY - CURRENTLY ENROUTE KOPFONTEIN BORDER | GREYTOWN - ROAD CLOSED DUE TO A ACCIDENT | GREYTOWN - DISPATCHING FOR THE BORDER | JOHANNESBURG AWAITING PERMIT TO PROCEED TO KOPFONTEIN | JOHANNESBURG AWAITING CROSS BORDER PERMIT TO PROCEED TO KOPFONTEIN | JOHANNESBURG AWAITING CROSS BORDER PERMIT TO PROCEED TO KOPFONTEIN | JOHANNESBURG AWAITING CROSS BORDER PERMIT TO PROCEED TO KOPFONTEIN | KOPFONTEIN BORDER CLEARING | OFFLOADED 25-12-2024
| TBA | CASE 885B MOTOR GRADER | KANU EQUIPMENT | HBZN0885VPAF10196 | HBZN0885VPAF10196 | 6293053 | 2412DSI2649 |  |  |  | VESSEL: LEO SPIRIT Voy. 0073A - ETA DURBAN: 09-01-2025 | DELIVERED 10-01-2025 | 09-01-2025 | 10-01-2025 | [8 empty] | 10-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2025 | VESSEL DUE TO ARRIVE TODAY | COLLECTED FROM PORT YESTERDAY - UNIT TO BE DELIVERED AM TODAY | DELIVERED 10-01-2025 | DELIVERED 10-01-2025
| S332501PRF0004 | CASE CX220 CRAWLER EXCAVATOR | KANU EQUIPMENT | JRKA01450 | NKJ22CLMJRKA01450 | 2199010 | 2501DSI2653 | BL64MKZN | ND702944 |  | VESSEL: ALLIANCE NORFOLK Voy. 140 - ETA DURBAN: 10-01-2025 | OFFLOADED 14-01-2025 | 10-01-2025 | 14-01-2025 | [8 empty] | 14-01-2025 |  |  |  | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-01-2025 | VESSEL DUE TO ARRIVE TODAY | COLLECTED FORM PORT 12-01-2025 | VAN REENEN ENROUTE JOHANNESBURG | OFFLOADED 14-01-2025 | OFFLOADED 14-01-2025
| S332501PRF0003 | CASE CX220 CRAWLER EXCAVATOR | KANU EQUIPMENT | CRKA01451 | NKJ22CLMCRKA01451 | 2195265 | 2501DSI2653 | BP43GGZN | BJ85MZZN |  | VESSEL: ALLIANCE NORFOLK Voy. 140 - ETA DURBAN: 10-01-2025 | OFFLOADED 16-01-2025 | 10-01-2025 | 14-01-2025 | [8 empty] | 16-01-2025 |  |  |  | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-01-2025 | VESSEL DUE TO ARRIVE TODAY | COLLECTED FORM PORT 12-01-2025 | VAN REENEN ENROUTE BRACKENFELL | COLESBERG ENROUTE BRACKENFELL | ENROUTE BRACKENFELL - TO ARRIVE BEFORE 12H00 TODAY | OFFLOADED 16-01-2025
| S332501PRF0005 | CASE CX220 CRAWLER EXCAVATOR | KANU EQUIPMENT | VRKA01452 | NKJ22CLMVRKA01452 | 2199017 | 2501DSI2653 | ND142761 | ND542263 |  | VESSEL: ALLIANCE NORFOLK Voy. 140 - ETA DURBAN: 10-01-2025 | OFFLOADED 16-01-2025 | 10-01-2025 | 14-01-2025 | [8 empty] | 16-01-2025 |  |  |  | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-01-2025 | VESSEL DUE TO ARRIVE TODAY | COLLECTED FORM PORT 12-01-2025 | VAN REENEN ENROUTE BRACKENFELL | COLESBERG ENROUTE BRACKENFELL | ENROUTE BRACKENFELL - TO ARRIVE BEFORE 12H00 TODAY | OFFLOADED 16-01-2025