## CONGO EQUIPMENT TFM SPARES
BARTRAC INVOICE NUMBERS | CARGO DETAILS | CLIENT | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | VESSEL DETAILS | ACTUAL STATUS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | GROBLERSBRIDGE ARR | GROBLERSBRIDGE DISPATCH | PANDAMATENGA | KAZUNGULA | LIVINGSTONE | KALOMO | MAZABUKA | LUSAKA | KABWE | KITWE | KASUMBALESA ARRIVAL | KASUMBALESA DISPATCH | WHISKY | LUBUMBASHI | LIKASI | TENKE | OFFLOADED | COMMENTS 31-01-2025 | COMMENTS 03-02-2025 | COMMENTS 04-02-2025 | COMMENTS 05-02-2025 | COMMENTS 06-02-2025 | COMMENTS 07-02-2025 | COMMENTS 10-02-2025 | COMMENTS 11-02-2025 | COMMENTS 12-02-2025 | COMMENTS 13-02-2025 | COMMENTS 14-02-2025 | COMMENTS 17-02-2025 | COMMENTS 18-02-2025 | COMMENTS 19-02-2025 | COMMENTS 20-02-2025 | COMMENTS 21-02-2025 | COMMENTS 24-02-2025 | COMMENTS 25-02-2025 | COMMENTS 26-02-2025 | COMMENTS 27-02-2025 | COMMENTS 28-02-2025 | COMMENTS 03-03-2025 | COMMENTS 04-03-2025 | COMMENTS 05-03-2025 | COMMENTS 06-03-2025 | COMMENTS 07-03-2025 | COMMENTS 10-03-2025 | COMMENTS 11-03-2025 | COMMENTS 12-03-2025 | COMMENTS 13-03-2025 | COMMENTS 14-03-2025 | COMMENTS 17-03-2025 | COMMENTS 18-03-2025 | COMMENTS 19-03-2025 | COMMENTS 20-03-2025 | COMMENTS 24-03-2025 | COMMENTS 25-03-2025 | COMMENTS 26-03-2025 | COMMENTS 27-03-2025 | COMMENTS 28-03-2025 | COMMENTS 31-03-2025 | COMMENTS 01-04-2025 | COMMENTS 02-04-2025 | COMMENTS 03-04-2025 | COMMENTS 04-04-2025 | COMMENTS 07-04-2025 | COMMENTS 08-04-2025 | COMMENTS 09-04-2025 | COMMENTS 10-04-2025 | COMMENTS 11-04-2025 | COMMENTS 14-04-2025 | COMMENTS 15-04-2025 | COMMENTS 16-04-2025 | COMMENTS 17-04-2025 | COMMENTS 22-04-2025 | COMMENTS 23-04-2025 | COMMENTS 24-04-2025 | COMMENTS 25-04-2025 | COMMENTS 29-04-2025 | COMMENTS 30-04-2025 | COMMENTS 02-05-2025 | COMMENTS 05-05-2025 | COMMENTS 06-05-2025 | COMMENTS 07-05-2025 | COMMENTS 08-05-2025 | COMMENTS 09-05-2025 | COMMENTS 12-05-2025 | COMMENTS 13-05-2025 | COMMENTS 14-05-2025 | COMMENTS 15-05-2025 | COMMENTS 16-05-2025 | COMMENTS 19-05-2025 | COMMENTS 20-05-2025 | COMMENTS 21-05-2025 | COMMENTS 22-05-2025 | COMMENTS 23-05-2025 | COMMENTS 26-05-2025 | COMMENTS 27-05-2025 | COMMENTS 28-05-2025 | COMMENTS 29-05-2025 | COMMENTS 30-05-2025 | COMMENTS 02-06-2025
FC42058597, FC42058598, FC42058763, FC42058829, | 6 PKGS OF MACHINERY SPARE PARTS | TENKE FUNGURUME MINING | 2501DSI2667 | COD 2024 257081 PT07 | CM16FLGP | DH97VNGP / DH97VPGP | POR5827 |  | VESSEL: APL VANCOUVER Voy. MA503R - TRANSHIPMENT VESSEL: MSC ELAINE Voy. ZF512A ETA DURBAN - 05-04-2025 | OFFLOADED 01-06-2025 | 05-04-2025 | 13-04-2025 | 14-04-2025 | 16-04-2025 | 17-04-2025 | 21-04-2025 | 23-04-2025 | 23-04-2025 | 07-05-2025 | 08-05-2025 | 08-05-2025 | 09-05-2025 | 10-05-2025 | 10-05-2025 | 11-05-2025 | 13-05-2025 | 14-05-2025 | 22-05-2025 | 29-05-2025 | 29-05-2025 | 01-06-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 18-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 27-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 27-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 27-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 27-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 27-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 28-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 28-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 28-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 31-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 31-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 31-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 31-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 02-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 02-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 02-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 02-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 02-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 03-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 04-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 04-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 05-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 05-04-2025 | VESSEL ARRIVED 05-04-2025 - CURRENTLY DISCHARDING CONTAINERS | VESSEL ARRIVED 05-04-2025 - CURRENTLY DISCHARDING CONTAINERS | VESSEL STILL DISCHARGING CONTAINERS - AWAITING CONTAINER TO ARRIVE AT UNPACK DEPOT | CONTAINER UNPACED - COLLECTING CARGO FROM UNPACK DEPOT | CARGO TO BE DELIVERED TO CONSOLIDATION WAREHOUSE ON MONDAY | CARGO TO BE DELIVERED TO CONSOLIDATION WAREHOUSE TODAY | CARGO AT CONSOLIDATION WAREHOUSE - LOADING DATE TO BE ADVISED | CARGO AT CONSOLIDATION WAREHOUSE - LOADING DATE & VEHICLE DETAILS TO BE ADVISED | CARGO LOADED - VEHICLE TO DISPATCH FOR GRB BORDER TODAY | PALAPYE ENROUTE KAZUNGULA BORDER | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | KAZUNGULA ZAMBIAN SIDE CLEARING | KAZUNGULA ZAMBIAN SIDE CLEARING - AWAITING PHYSICAL INSPECTION | KAZUNGULA ZAMBIAN SIDE CLEARING - AWAITING CUSTOMS PHYSICAL INSPECTION | KAZUNGULA ZAMBIAN SIDE CLEARING - AWAITING CUSTOMS RELEASE | KAZUNGULA ZAMBIAN SIDE CLEARING - AWAITING CUSTOMS RELEASE ON DOCUMENTS AND VEHICLE | KAZUNGULA ZAMBIAN SIDE CLEARING - AWAITING CUSTOMS RELEASE ON DOCUMENTS AND VEHICLE | KAZUNGULA ZAMBIAN SIDE VEHICLE TO DISPATCH BY MIDDAY TODAY | KAFUE ENROUTE KASUMBALESA BORDER | LUSAKA ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER IN THE QUEUE TO CROSS TO DRC SIDE | GOMES CHECK PIONT TO PROCEED TO WHISKEY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE & EXIT FORMALITIES - DAY 7 | WHISKEY AWAITING RELEASE & EXIT FORMALITIES - DAY 8 | VEHICLE CURRENTLY AT OFFLOADING POINT 1 IN LUBUMBAHSI | VEHICLE CURRENTLY AT OFFLOADING POINT 2 IN LUBUMBAHSI | VEHICLE STILL AT OFFLOADING POINT 2 IN LUBUMBAHSI | VEHICLE STILL AT OFFLOADING POINT 2 IN LUBUMBAHSI - AWAITING OFFLOADING AND CUSTOMS RELEASE TO PROCEED TO 3RD OFFLOADING POINT | AT AGL WAREHOUSE IN LUBUMBASHI WAITING TO OFFLOAD | DISPATCHING LUBUMBASHI FOR TENKE | TENKE WAITING TO ENTER INTO TFM | OFFLOADED 01-06-2025
FC42059356 | 1 PKGS OF MACHINERY SPARE PARTS | TENKE FUNGURUME MINING | 2501DSI2668 | COD 2023 146317 PT81 | CM16FLGP | DH97VNGP / DH97VPGP | POR5827 |  | VESSEL: APL VANCOUVER Voy. MA503R - TRANSHIPMENT VESSEL: MSC ELAINE Voy. ZF512A ETA DURBAN - 05-04-2025 | OFFLOADED 01-06-2025 | 05-04-2025 | 13-04-2025 | 14-04-2025 | 16-04-2025 | 17-04-2025 | 21-04-2025 | 23-04-2025 | 23-04-2025 | 07-05-2025 | 08-05-2025 | 08-05-2025 | 09-05-2025 | 10-05-2025 | 10-05-2025 | 11-05-2025 | 13-05-2025 | 14-05-2025 | 22-05-2025 | 29-05-2025 | 29-05-2025 | 01-06-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 18-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - ETAL DURBAN 15-02-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 15-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 27-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 27-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 27-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 27-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 27-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 28-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 28-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 28-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 31-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 31-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 31-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 31-03-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 02-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 02-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 02-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 02-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 02-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 03-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 04-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 04-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 05-04-2025 | AWAITING VESSEL ARRIVAL - TRANSHIPMENT VESSEL DETAILS RECEIVED - NEW ETA DURBAN 05-04-2025 | VESSEL ARRIVED 05-04-2025 - CURRENTLY DISCHARDING CONTAINERS | VESSEL ARRIVED 05-04-2025 - CURRENTLY DISCHARDING CONTAINERS | VESSEL STILL DISCHARGING CONTAINERS - AWAITING CONTAINER TO ARRIVE AT UNPACK DEPOT | CONTAINER UNPACED - COLLECTING CARGO FROM UNPACK DEPOT | CARGO TO BE DELIVERED TO CONSOLIDATION WAREHOUSE ON MONDAY | CARGO TO BE DELIVERED TO CONSOLIDATION WAREHOUSE TODAY | CARGO AT CONSOLIDATION WAREHOUSE - LOADING DATE TO BE ADVISED | CARGO AT CONSOLIDATION WAREHOUSE - LOADING DATE & VEHICLE DETAILS TO BE ADVISED | CARGO LOADED - VEHICLE TO DISPATCH FOR GRB BORDER TODAY | PALAPYE ENROUTE KAZUNGULA BORDER | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | KAZUNGULA ZAMBIAN SIDE CLEARING | KAZUNGULA ZAMBIAN SIDE CLEARING - AWAITING PHYSICAL INSPECTION | KAZUNGULA ZAMBIAN SIDE CLEARING - AWAITING CUSTOMS PHYSICAL INSPECTION | KAZUNGULA ZAMBIAN SIDE CLEARING - AWAITING CUSTOMS RELEASE | KAZUNGULA ZAMBIAN SIDE CLEARING - AWAITING CUSTOMS RELEASE ON DOCUMENTS AND VEHICLE | KAZUNGULA ZAMBIAN SIDE CLEARING - AWAITING CUSTOMS RELEASE ON DOCUMENTS AND VEHICLE | KAZUNGULA ZAMBIAN SIDE VEHICLE TO DISPATCH BY MIDDAY TODAY | KAFUE ENROUTE KASUMBALESA BORDER | LUSAKA ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER IN THE QUEUE TO CROSS TO DRC SIDE | GOMES CHECK PIONT TO PROCEED TO WHISKEY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE & EXIT FORMALITIES - DAY 7 | WHISKEY AWAITING RELEASE & EXIT FORMALITIES - DAY 8 | VEHICLE CURRENTLY AT OFFLOADING POINT 1 IN LUBUMBAHSI | VEHICLE CURRENTLY AT OFFLOADING POINT 2 IN LUBUMBAHSI | VEHICLE STILL AT OFFLOADING POINT 2 IN LUBUMBAHSI | VEHICLE STILL AT OFFLOADING POINT 2 IN LUBUMBAHSI - AWAITING OFFLOADING AND CUSTOMS RELEASE TO PROCEED TO 3RD OFFLOADING POINT | AT AGL WAREHOUSE IN LUBUMBASHI WAITING TO OFFLOAD | DISPATCHING LUBUMBASHI FOR TENKE | TENKE WAITING TO ENTER INTO TFM | OFFLOADED 01-06-2025

## OFFLOADED - 2024
CLIENT PO | CARGO DETAILS | CLIENT | PARTS | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | GROBLERSBRIDGE ARR | GROBLERSBRIDGE DISPATCH | PANDAMATENGA | KAZUNGULA | LIVINGSTONE | KALOMO | MAZABUKA | LUSAKA | KABWE | KITWE | KASUMBALESA ARRIVAL | KASUMBALESA DISPATCH | WHISKY | LUBUMBASHI | LIKASI | TENKE | OFFLOADED | COMMENTS 20-09-2023 | COMMENTS 21-09-2023 | COMMENTS 22-09-2023 | COMMENTS 26-09-2023 | COMMENTS 27-09-2023 | COMMENTS 28-09-2023 | COMMENTS 29-09-2023 | COMMENTS 03-10-2023 | COMMENTS 04-10-2023 | COMMENTS 05-10-2023 | COMMENTS 06-10-2023 | COMMENTS 09-10-2023 | COMMENTS 10-10-2023 | COMMENTS 11-10-2023 | COMMENTS 12-10-2023 | COMMENTS 13-10-2023 | COMMENTS 16-10-2023 | COMMENTS 17-10-2023 | COMMENTS 18-10-2023 | COMMENTS 19-10-2023 | COMMENTS 20-10-2023 | COMMENTS 24-10-2023 | COMMENTS 26-10-2023 | COMMENTS 27-10-2023 | COMMENTS 30-10-2023 | COMMENTS 31-10-2023 | COMMENTS 01-11-2023 | COMMENTS 02-11-2023 | COMMENTS 03-11-2023 | COMMENTS 06-11-2023 | COMMENTS 07-11-2023 | COMMENTS 08-11-2023 | COMMENTS 09-11-2023 | COMMENTS 10-11-2023 | COMMENTS 14-11-2023 | COMMENTS 15-11-2023 | COMMENTS 16-11-2023 | COMMENTS 17-11-2023 | COMMENTS 20-11-2023 | COMMENTS 21-11-2023 | COMMENTS 22-11-2023 | COMMENTS 23-11-2023 | COMMENTS 24-11-2023 | COMMENTS 27-11-2023 | COMMENTS 28-11-2023 | COMMENTS 29-11-2023 | COMMENTS 30-11-2023 | COMMENTS 01-12-2023 | COMMENTS 04-12-2023 | COMMENTS 05-12-2023 | COMMENTS 06-12-2023 | COMMENTS 07-12-2023 | COMMENTS 08-12-2023 | COMMENTS 11-12-2023 | COMMENTS 12-12-2023 | COMMENTS 13-12-2023 | COMMENTS 14-12-2023 | COMMENTS 18-12-2023 | COMMENTS 19-12-2023 | COMMENTS 20-12-2023 | COMMENTS 21-12-2023 | COMMENTS 22-12-2023 | COMMENTS 27-12-2023 | COMMENTS 28-12-2023 | COMMENTS 29-12-2023 | COMMENTS 02-01-2024 | COMMENTS 03-01-2024 | COMMENTS 05-01-2024 | COMMENTS 08-01-2024 | COMMENTS 09-01-2024 | COMMENTS 10-01-2024 | COMMENTS 11-01-2024 | COMMENTS 12-01-2024 | COMMENTS 15-01-2024 | COMMENTS 16-01-2024 | COMMENTS 17-01-2024
FC42055702 | 3 X PKGS STC SPARE PARTS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | SLAC MACHINERY PARTS | 2308DSI2192 | COD 2023 256133 PT03 | KX29RRGP | KW99WXGP / KW99XKGP | POR5694 | N/A | OFFLOADED 13-12-2023 | 13-10-2023 | 13-11-2023 | 13-11-2023 | 23-11-2023 | 23-11-2023 | 25-11-2023 | 26-11-2023 | 26-11-2023 | 28-11-2023 | 30-11-2023 | 30-11-202 | 01-12-2023 | 01-12-2023 | 02-12-2023 | 03-12-2023 | 04-12-2023 | 04-12-2023 | 09-12-2023 | N/A | N/A | 13-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 04-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 04-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 04-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 11-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 11-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 11-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 11-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 11-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 11-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 11-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 13-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 15-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 15-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 13-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN:- 13-10-2023 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CONTAINERS | CONTAINER CURRENLTY UNDER UNPACK | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADEDING TRUCK DETAILS AND LOADING DATE | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADEDING TRUCK DETAILS AND LOADING DATE | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADEDING TRUCK DETAILS AND LOADING DATE, TRUCK TO BE BACK FROM DRC NEXT WEEK TO LOAD | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADEDING TRUCK DETAILS AND LOADING DATE, TRUCK TO BE BACK FROM DRC NEXT WEEK TO LOAD | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADING TRUCK DETAILS AND LOADING DATE, TRUCK TO BE BACK FROM DRC THIS WEEK TO LOAD | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADING TRUCK DETAILS AND LOADING DATE, TRUCK TO BE BACK FROM DRC THIS WEEK TO LOAD | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADING TRUCK DETAILS AND LOADING DATE, TRUCK TO BE BACK FROM DRC THIS/NEXT WEEK TO LOAD | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADING TRUCK DETAILS AND LOADING DATE, TRUCK TO BE BACK FROM DRC NEXT WEEK TO LOAD | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADING TRUCK DETAILS AND LOADING DATE, TRUCK TO BE BACK FROM DRC THIS WEEK TO LOAD | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADING TRUCK DETAILS AND LOADING DATE, TRUCK TO BE BACK FROM DRC THIS WEEK TO LOAD | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADING TRUCK DETAILS AND LOADING DATE, TRUCK TO BE BACK FROM DRC THIS WEEK TO LOAD | THE 3 X PIECES ARE AT OUR TRANSPORTERS FACILITY AWAITING CO-LOADING TRUCK DETAILS AND LOADING DATE, TRUCK TO BE BACK FROM DRC THIS WEEK TO LOAD | VEHICLE AT WAREHOUSE UNDERGOING FINAL TRIP CHECK - TO LOAD MONDAY 13-11-2023 | TRUCK LOADED, UNDERGOING FINAL TRIP CHECK BEFORE DISPATCHING | TRUCK LOADED, UNDERGOING FINAL TRIP CHECK BEFORE DISPATCHING ON MONDAY THE 20/11/2023 | TRUCK LOADED, UNDERGOING FINAL TRIP CHECK BEFORE DISPATCHING ON MONDAY THE 20/11/2023 | TRUCK LOADED, UNDERGOING FINAL TRIP CHECK BEFORE DISPATCHING ON MONDAY THE 20/11/2024 | TRUCK LOADED, UNDERGOING FINAL TRIP CHECK BEFORE DISPATCHING TOMORROW 21/11/2024 | VEHICLE TO DISPATCH TODAY | VEHICLE WAS DELAYED YESTERDAY TO DISPATCH TODAY | THE DRIVER IS SICK AND NEED TO CHANGE VEHICLES - NEW DETAILS TO FOLLOW | VEHICLE CURRENTLY AT GRB BORDER CLEARING | VEHICLE AT KAZUNGULA ZAM SIDE CLEARING | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MONZE ENROUTE KASUMBALESA | VEHICLE AT MONZE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC | KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI WAITING TO OFFLOAD | VEHICLE AT LUBUMBASHI WAITING TO OFFLOAD - PLEASE ASSIST | VEHICLE IN LUBUMBASHI AT OFFLOADING POINT 1 - AWAITING RELEASE BEFORE PROCEEDING TO CONGO EQUIPMENT FOR OFFLOADING | OFFLOADED 13-12-2023 | OFFLOADED 13-12-2023 | OFFLOADED 13-12-2023 | OFFLOADED 13-12-2023 | OFFLOADED 13-12-2023 | OFFLOADED 13-12-2023 | OFFLOADED 13-12-2023 | OFFLOADED 13-12-2023 | OFFLOADED 13-12-2024 | OFFLOADED 13-12-2024 | OFFLOADED 13-12-2025 | OFFLOADED 13-12-2026 | OFFLOADED 13-12-2026 | OFFLOADED 13-12-2026 | OFFLOADED 13-12-2026 | OFFLOADED 13-12-2026 | OFFLOADED 13-12-2026 | OFFLOADED 13-12-2026 | OFFLOADED 13-12-2026 | OFFLOADED 13-12-2026
4501707063 | 3 X PKGS STC SPARE PARTS | BARTRAC EQUIPMENT / TENKE FUNGURUME MINING | MACHINERY SPARE PARTS | 2311DAI2289 | COD 2023 264885 | YSD665GP | JDR120MP / JDR117MP | POR5718 |  | OFFLOADED 16-01-2024 | N/A | N/A | 14-12-2023 | 22-12-2023 | 22-12-2023 | 23-12-2023 | 27-12-2023 | 27-12-2023 | 03-01-2024 | 04-01-2024 | 04-01-2024 | 05-01-2024 | 07-01-2024 | 10-01-2024 | 10-01-2024 | 11-01-2024 | 11-01-2024 | 15-01-2024 | 16-01-2024 | 16-01-2024 | 16-01-2024 | [46 empty] | AWAITING FLIGHT ARRIVAL - ETA JHB 03-12-2023 | AWAITING FLIGHT ARRIVAL - ETA JHB 03-12-2023 | AIR FREIGHT ARRIVED, UNDER CUSTOMS CLEARANCE | AWAITING RELEASE FROM AIRLINE | AWAITING RELEASE FROM AIRLINE | CARGO IS DUE TO ARRIVE AT JOHANNESBURG AIR PORT TOMORROW 08-12-2023 | AWAITING CARGO TO ARRIVE IN JHB | AWAITING CARGO TO ARRIVE IN JHB - AWAITING NEW ETA | AWAITING CARGO TO ARRIVE IN JHB - AWAITING NEW ETA | CARGO IS BOOKED TO ARRIVE IN JHB 14-12-2023 | CARGO IS BOOKED TO ARRIVE IN JHB 14-12-2023 | CARGO ARRIVED - WAITING RELEASE FROM AIRLINE | COLLECTING CARGO FROM AIRLINE TODAY - AWAITING CONSOLIDATION VEHICLE TO ARRIVE IN JHB IN ORDER TO LOAD | COLLECTING CARGO FROM AIRLINE TODAY - AWAITING CONSOLIDATION VEHICLE TO ARRIVE IN JHB IN ORDER TO LOAD | CARGO AT OUR FACILITY - AWAITING CONSOLIDATION VEHICLE TO ARRIVE IN JHB IN ORDER TO LOAD | CARGO LOADED - DISPATCHING TODAY | PANDAMATENGA ENROUTE KAZUNGULA | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER AWAIITNG FINAL RELEASE | KAZUNGULA BORDER AWAIITNG FINAL RELEASE | TRUCK IS AT SENKOBO EN-ROUTE TO KASUMBALESA BORDER | TRUCK IS AT LUSAKA EN-ROUTE TO KASUMBALESA BORDER | TRUCK IS AT NDOLA EN-ROUTE TO KASUMBALESA BORDER | TRUCK IS AT NDOLA DEPOT, BUSY WITH TRIP CHECK BEFORE VEHICLE DISPATCH FOR KASUMBALESA | TRUCK IS AT CHINGOLA ENROUTE KASUMBALESA | TRUCK IS AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | TRUCK IS AT WHISKEY AWAITING RELEASE | TRUCK IS AT WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI | OFFLOADED 16-01-2024
INV2024000004 | 8 X PKGS STC SPARE PARTS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | 2405DSI2549 | COD 2024 121814 | BCE 5028ZM | ATB2573T | 2405DSI2549 | 08-08-2024 | VESSEL: EVER UNITED Voy 199W - ETA DURBAN: 30-07-2024 | OFFLOADED06-09-2024 | 30-07-2024 | 09-08-2024 | 10-08-2024 | 11-08-2024 | 11-08-2024 | 12-08-2024 | 13-08-2024 | 13-08-2024 | 18-08-2024 | 19-08-2024 | 19-08-2024 | 19-08-2024 | 19-08-2024 | 24-08-2024 | 25-08-2024 | 28-08-2024 | 28-08-2024 | 31-08-2024 | N/A | N/A | 06-09-2024 | [41 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-07-2024 | AWAITING VESSEL ARRIVAL - VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING. | CONTAINER TO BE COLLECTED FROM PORT | AWAITING IN-TRANSIT INSPECTION APPROVAL FROM BV DRC TO DO THE BV INSEPCTION IN RSA | AWAITING IN-TRANSIT INSPECTION APPROVAL FROM BV DRC TO DO THE BV INSEPCTION IN RSA - PLEASE ASSIST - VEHICLE ON STANDBY TO LOAD | AWAITING IN-TRANSIT INSPECTION APPROVAL FROM BV DRC TO DO THE BV INSEPCTION IN RSA - PLEASE ASSIST - VEHICLE ON STANDBY TO LOAD | AWAITING IN-TRANSIT INSPECTION APPROVAL FROM BV DRC TO DO THE BV INSEPCTION IN RSA - PLEASE ASSIST - VEHICLE ON STANDBY TO LOAD | BV INSPECTION BOOKED FOR TODAY - LOADING MONDAY | LOADED YESTERDAY - TO DISPATCH FOR THE BORDER | CURRENTLY AT GROBERSBRIDGE BORDER CLEARING | SERULE BW ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER FINALIZING CLEARING | KAPIRI ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE CHECK | NDOLA UNDER ROUTINE MAINTENANCE CHECK | NDOLA FINALIZING MAINTENANCE CHECK | DISPATCHING NDOLA FOR KASUMBALESA BORDER | KASUMBALESA BORDER CLEARING | KASUMBALESA BORDER - DRC SIDE CLEARING | KASUMBALESA BORDER - DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | VEHICLE AT CONNEX LUBUMBASHI, AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED06-09-2024 | OFFLOADED06-09-2024
FC42057952, FC42057953, FC42058053 | 3 X PKGS STC SPARE PARTS | BARTRAC EQUIPMENT / CMOC (TENKE) | 2406DSI2554 | COD 2023 264885 PT89 | XML368GP | N/A | 2407DSI2560 | TBA | VESSEL: CONTI CORTESIA Voy MA422R Transshipment Vessel: NYK FUJI Voy, 126W - ETA DURBAN: 11-08-2024 | OFFLOADED 06-10-2024 | 11-08-2024 | 13-09-2024 | 14-09-2024 | 16-09-2024 | 16-09-2024 | 19-09-2024 | 20-09-2024 | 21-09-2024 | 22-09-2024 | 22-09-2024 | 22-09-2024 | 22-09-2024 | 22-09-2024 | 23-09-2024 | 23-09-2024 | 30-09-2024 | 30-09-2024 | 04-10-2024 | 04-10-2024 | 04-10-2024 | 04-10-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-08-2024 | CARGO TO BE COLLECTED TODAY AT UNPACK DEPOT | TO BE DELIVERED TO FML BOND STORE TODAY | TO BE DELIVERED TO FML BOND STORE TODAY | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD - LOADING PLANNED FOR THIS WEEK | LOADING TOMORROW 12-09-2024 | LOADING TODAY | LOADED - ENROUTE GROBLERS BRIDGE BORDER | DISPATCHING JOHANNESBURG FOR GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER TO CROSS TO BOTSWANA SIDE | MARTINS DRIFT BORDER AWAITING RELEASE | SHERWOOD ENROUTE KAZUNGULA BORDER | PALAPYE ENROUTE KAZUNGULA BORDER | KITWE ENORUTE KASUMBALESA BORDER | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED - CUSTOMS SYSTEM DOWN | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED - CUSTOMS SYSTEM DOWN | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 3 PLEASE ASSIST | WHISKEY AWAITING RELEASE - DAY 4 PLEASE ASSIST | KANYAKA AWAITING RELEASE - DAY 4 PLEASE ASSIST | OFFLOADED 06-10-2024
FC42057956 | 1 X PKGS STC SPARE PARTS | BARTRAC EQUIPMENT / CMOC (TENKE) | 2406DSI2554 | COD 2023 146317 PT66 | XML368GP | N/A | 2407DSI2560 | TBA | VESSEL: CONTI CORTESIA Voy MA422R Transshipment Vessel: NYK FUJI Voy, 126W - ETA DURBAN: 11-08-2024 | OFFLOADED 06-10-2024 | 11-08-2024 | 13-09-2024 | 14-09-2024 | 16-09-2024 | 16-09-2024 | 19-09-2024 | 20-09-2024 | 21-09-2024 | 22-09-2024 | 22-09-2024 | 22-09-2024 | 22-09-2024 | 22-09-2024 | 23-09-2024 | 23-09-2024 | 30-09-2024 | 30-09-2024 | 04-10-2024 | 04-10-2024 | 04-10-2024 | 04-10-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL DETAILS AND PRE-ALERT - SAILING FROM MELBOURNE 11-06-2024 - ETA DURBAN PORT 10-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-08-2024 | CARGO TO BE COLLECTED TODAY AT UNPACK DEPOT | TO BE DELIVERED TO FML BOND STORE TODAY | TO BE DELIVERED TO FML BOND STORE TODAY | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | DELIVERED TO FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD - LOADING PLANNED FOR THIS WEEK | LOADING TOMORROW 12-09-2024 | LOADING TODAY | LOADED - ENROUTE GROBLERS BRIDGE BORDER | DISPATCHING JOHANNESBURG FOR GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER TO CROSS TO BOTSWANA SIDE | MARTINS DRIFT BORDER AWAITING RELEASE | SHERWOOD ENROUTE KAZUNGULA BORDER | PALAPYE ENROUTE KAZUNGULA BORDER | KITWE ENORUTE KASUMBALESA BORDER | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED - CUSTOMS SYSTEM DOWN | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED - CUSTOMS SYSTEM DOWN | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 3 PLEASE ASSIST | WHISKEY AWAITING RELEASE - DAY 4 PLEASE ASSIST | KANYAKA AWAITING RELEASE - DAY 4 PLEASE ASSIST | OFFLOADED 06-10-2024