## ENROUTE SITE
CLIENT PO | CARGO DETAILS | PACKING LIST DIMENSIONS & WEIGHT (LxWxH-W) | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | VESSEL DETAILS | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | ACTUAL STATUS | ANTICIPATED ETA AT KCC SITE | ESTIMATED DRC BORDER crossing date | BV RECEIVED | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE ARR | HARARE DSP | CHIRUNDU ARR | CHIRUNDU DSP | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY ARR | WHISKY DISPATCH | LUBUMBASHI ARR | LUBUMBASHI DSP | KOLWEZI ARR | OFFLOADED | COMMENTS 20-12-2024 | COMMENTS 23-12-2024 | COMMENTS 24-12-2024 | COMMENTS 27-12-2024 | COMMENTS 30-12-2024 | COMMENTS 02-01-2025 | COMMENTS 03-01-2025 | COMMENTS 06-01-2025 | COMMENTS 07-01-2025 | COMMENTS 08-01-2025 | COMMENTS 09-01-2025 | COMMENTS 10-01-2025 | COMMENTS 13-01-2025 | COMMENTS 14-01-2025 | COMMENTS 15-01-2025 | COMMENTS 16-01-2025 | COMMENTS 17-01-2025 | COMMENTS 20-01-2025 | COMMENTS 21-01-2025 | COMMENTS 22-01-2025 | COMMENTS 23-01-2025 | COMMENTS 24-01-2025 | COMMENTS 27-01-2025 | COMMENTS 28-01-2025 | COMMENTS 29-01-2025 | COMMENTS 30-01-2025 | COMMENTS 31-01-2025 | COMMENTS 03-02-2025 | COMMENTS 04-02-2025 | COMMENTS 05-02-2025 | COMMENTS 06-02-2025 | COMMENTS 07-02-2025 | COMMENTS 10-02-2025 | COMMENTS 11-02-2025 | COMMENTS 12-02-2025 | COMMENTS 13-02-2025 | COMMENTS 14-02-2025 | COMMENTS 17-02-2025 | COMMENTS 18-02-2025 | COMMENTS 19-02-2025 | COMMENTS 20-02-2025 | COMMENTS 21-02-2025 | COMMENTS 24-02-2025 | COMMENTS 25-02-2025 | COMMENTS 26-02-2025 | COMMENTS 27-02-2025 | COMMENTS 28-02-2025 | COMMENTS 03-03-2025 | COMMENTS 04-03-2025 | COMMENTS 05-03-2025 | COMMENTS 06-03-2025 | COMMENTS 07-03-2025 | COMMENTS 10-03-2025 | COMMENTS 11-03-2025 | COMMENTS 12-03-2025 | COMMENTS 13-03-2025 | COMMENTS 14-03-2025 | COMMENTS 17-03-2025 | COMMENTS 18-03-2025 | COMMENTS 19-03-2025 | COMMENTS 20-03-2025 | COMMENTS 24-03-2025 | COMMENTS 25-03-2025 | COMMENTS 26-03-2025 | COMMENTS 27-03-2025 | COMMENTS 28-03-2025 | COMMENTS 31-03-2025 | COMMENTS 01-04-2025 | COMMENTS 02-04-2025
BA2757A | TYRE HANDLER FOR CAT988K | 4,88 x 2,28 x 1,90 - 9884KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | TH25K164241001 |  |  | FML2502DSI2669 | VESSEL: MAERSK VALLVIK Voy. 505S - ETA DURBAN: 04-03-2025 | COD 2025 129381 PT02 | BCE4032ZM | BCE5095ZM | 2502DSI2669 | OFFLOADED 01-04-2025 |  |  | 28-02-2025 | BV NUMBER RECEIVED | 04-03-2025 | 16-03-2025 | 16-03-2025 | 17-03-2025 | RUSTENBURG 17-03-2025 | KOPFONTEIN BORDER 17-03-2025 | KOPFONTEIN BORDER 19-03-2025 | FRANCISTOWN 20-03-2025 |  | KAZUNGULA BORDER 20-03-2025 | KAZUNGULA BORDER 23-03-2025 | 25-03-2025 | 25-03-2025 | 26-03-2025 | SAKANIA 26-03-2025 | SAKANIA 29-03-2025 | 29-03-2025 | 29-03-2025 | 29-03-2025 | 29-03-2025 | 30-03-2025 | 01-04-2025 | [33 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKIN G | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT - TO BE DELIVERED TO BONDED FACILITY FOR UNPACK | UNIT RECEIVED IN TO BOND - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLAN TO BE CONFIRMED | UNIT RECEIVED IN TO BOND - BV INSPECTION BOOKED FOR TODAY - LOADING PLAN TO BE CONFIRMED | UNIT RECEIVED IN TO BOND - BV INSPECTION COMPLETED - LOADING PLAN TO BE CONFIRMED | UNIT RECEIVED IN TO BOND - BV INSPECTION COMPLETED - LOADING PLAN FOR NEXT MID WEEK | UNIT RECEIVED IN TO BOND - BV INSPECTION COMPLETED - LOADING PLAN FOR NEXT MID WEEK | LOADED, CURRENTLY IN JOHANNESBURG TO DISPATCH FOR THE BORDER | KOPFONTEIN BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | KOPFONTEIN BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KALOMO ENROUTE NDOLA | KAPIRI ENROUTE NDOLA | NDOLA TO PROCEED TO SAKANIA BORDER | SAKANIA BORDER ZAMBIAN SIDE IN THE QUEUE TO CROSS TO DRC SIDE | SAKANIA BORDER ZAMBIAN SIDE IN THE QUEUE TO CROSS TO DRC SIDE | ON SITE WAITING TO OFFLOAD | VEHICLE SENT FOR OFFLOADING | OFFLOADED 01-04-2025

## OFFLOADED - 2025
CLIENT PO | CARGO DETAILS | PACKING LIST DIMENSIONS & WEIGHT (LxWxH-W) | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | VESSEL DETAILS | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | ACTUAL STATUS | ANTICIPATED ETA AT KCC SITE | ESTIMATED DRC BORDER crossing date | BV RECEIVED | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE ARR | HARARE DSP | CHIRUNDU ARR | CHIRUNDU DSP | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY ARR | WHISKY DISPATCH | LUBUMBASHI ARR | LUBUMBASHI DSP | KOLWEZI ARR | OFFLOADED | COMMENTS 04-11-2024 | COMMENTS 05-11-2024 | COMMENTS 06-11-2024 | COMMENTS 07-11-2024 | COMMENTS 08-11-2024 | COMMENTS 11-11-2024 | COMMENTS 12-11-2024 | COMMENTS 12-11-2024 - PM UPDATE | COMMENTS 13-11-2024 | COMMENTS 14-11-2024 | COMMENTS 15-11-2024 | COMMENTS 18-11-2024 | COMMENTS 19-11-2024 | COMMENTS 20-11-2024 | COMMENTS 21-11-2024 | COMMENTS 22-11-2024 | COMMENTS 25-11-2024 | COMMENTS 26-11-2024 | COMMENTS 27-11-2024 | COMMENTS 28-11-2024 | COMMENTS 29-11-2024 | COMMENTS 02-12-2024 | COMMENTS 03-12-2024 | COMMENTS 04-12-2024 | COMMENTS 05-12-2024 | COMMENTS 06-12-2024 | COMMENTS 09-12-2024 | COMMENTS 10-12-2024 | COMMENTS 11-12-2024 | COMMENTS 12-12-2024 | COMMENTS 13-12-2024 | COMMENTS 16-12-2024 | COMMENTS 17-12-2024 | COMMENTS 18-12-2024 | COMMENTS 19-12-2024 | COMMENTS 19-12-2024 - PM UPDATE | COMMENTS 20-12-2024 | COMMENTS 23-12-2024 | COMMENTS 24-12-2024 | COMMENTS 27-12-2024 | COMMENTS 30-12-2024 | COMMENTS 02-01-2025 | COMMENTS 03-01-2025 | COMMENTS 06-01-2025 | COMMENTS 07-01-2025 | COMMENTS 08-01-2025 | COMMENTS 09-01-2025 | COMMENTS 10-01-2025 | COMMENTS 13-01-2025 | COMMENTS 14-01-2025 | COMMENTS 15-01-2025 | COMMENTS 16-01-2025 | COMMENTS 17-01-2025 | COMMENTS 20-01-2025 | COMMENTS 21-01-2025 | COMMENTS 22-01-2025 | COMMENTS 23-01-2025 | COMMENTS 24-01-2025 | COMMENTS 27-01-2025 | COMMENTS 28-01-2025 | COMMENTS 29-01-2025 | COMMENTS 30-01-2025 | COMMENTS 31-01-2025 | COMMENTS 03-02-2025 | COMMENTS 04-02-2025 | COMMENTS 05-02-2025 | COMMENTS 06-02-2025
BA2767 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02234 - LINK LOAD SKID CAB SKID BODY SKID RIM TROPHY SKID OUTRIGGERS SKID HANDRAILS SKID FSTRUT | LINK LOAD 3,250 x 2,260 x 1,930 - 2514KGS 2,130 x 0,760 x 1,290 - 1125KGS 1,820 x 1,820 x 0,910 - 1950KGS 2,460 x 2,230 x 0,760 - 1288KGS 3,960 x 2,260 x 1,880 - 1515KGS 3,300 x 1,520 x 1,520 - 6505KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02234 | CAT0793DEFDB02234 | EXM00354 | FML2411DSI2621 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | AJF3857ZM | PXJ049GP / PXJ052GP | 2411DSI2621-4 | OFFLOADED 05-02-2025 | 30-01-2025 | 15-01-2025 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 20-12-2024 | 21-12-2024 | 23-12-2024 | 26-12-2024 | 26-12-2024 | 03-01-2025 | 04-01-2025 | 06-01-2025 | 06-01-2025 | 11-01-2025 | 13-01-2025 | 13-01-2025 | 13-01-2025 | 15-01-2025 | 21-01-2025 | 21-01-2025 | 29-01-2025 | 30-01-2025 | 30-01-2025 | 02-02-2025 | 06-02-2025 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADING TODAY FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 26-11-2024 - AWAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE THURSDAY 28-11-2024 | LOADED - AWAITING BV INSPECTION. BV TO BE DONE THURSDAY 28-11-2024 | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY 28-11-2024 | TO DISPATCH DURBAN FOR BEIT BRIDGE BORDER | ENROUTE JOHANNESBURG | HOUWICK ENROUTE JOHANNESBURG | HOUWICK TO DISPATCH FOR JOHANNESBURG TODAY | HOUWICK - VEHICLE ON BREAKDOWN - ATTENDING TO THE PROBLEM | HOUWICK - VEHICLE ON BREAKDOWN - ATTENDING TO THE PROBLEM | HOUWICK - VEHICLE TO DISPATCH TODAY | MOOIREVER ENROUTE BEIT BRIDGE BORDER - ESTIMATED ETA ON SITE 20-12-2024 | VEHICLE ON BREAKDOWN - AWAITING REPLACEMENT HORSE | VEHICLE ON BREAKDOWN - AWAITING REPLACEMENT HORSE | VEHICLE ON BREAKDOWN - AWAITING REPLACEMENT HORSE | VEHICLE ON BREAKDOWN - AWAITING REPLACEMENT HORSE - NEW HORSE ENROUTE TO COLLECT TRAILERS | VEHICLE ON BREAKDOWN -REPLACEMENT HORSE ENROUTE DURBAN TO COLLECT TRAILERS | VEHICLE ON BREAKDOWN -REPLACEMENT VEHICLE ENROUTE DURBAN TO COLLECT TRAILERS | VEHICLE ON BREAKDOWN -REPLACEMENT VEHICLE ENROUTE DURBAN TO COLLECT TRAILERS THIS AFTERNOON | VEHICLE ON BREAKDOWN -REPLACEMENT VEHICLE ENROUTE DURBAN TO COLLECT TRAILERS THIS AFTERNOON | VEHICLE TO DISPATCH DURBAN TODAY | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | ENROUTE BEIT BRIDGE BORDER | DISPATCHED PRETORIA - ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER IN THE QUEUE TO CROSS TO ZIM SIDE | BEIT BRIDGE BORDER - AWAITING RELEASE | BEIT BRIDGE BORDER - AWAITING RELEASE | HARARE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER ZIM SIDE - AWAITING FOR DOCUMENTS TO CROSS TO ZAMBIAN SIDE | CHIRUNDU BORDER ZIM SIDE - IN QUEUE TO CROSS TO ZAMBIA SIDE | CHIRUNDU BORDER ZAM SIDE WAITING RELEASE | KAFUE ENROUTE NDOLA | NDOLA ENROUTE KASUMBALESA BORDER | NDOLA UNDER ROUTINE MAINTENANCE | KASUMBALESA BORDER CLEARING | KASUMBALESA BORDER CLEARING | KASUMBALESA BORDER CLEARING | KASUMBALESA BORDER CLEARING - DAY 6 | WHISKEY - AWAITING RELEASE | WHISKEY - AWAITING RELEASE - DAY 3 PLEASE ASSIST | WHISKEY - AWAITING RELEASE - DAY 4 PLEASE ASSIST | WHISKEY - AWAITING RELEASE - DAY 7 PLEASE ASSIST - DELAY WITH DOCUMENTS AS THE AMENDED MANIFEST WAS NOT SENT TO CONNEX AFRICA BY CAPLAINE | WHISKEY - AMENDED DOCUMENTS RECEIVED 27-01-2025 - AWAITING RELEASE FROM CUSTOMS/DGDA - DAY 8 | WHISKEY - AMENDED DOCUMENTS RECEIVED 27-01-2025 - AWAITING CUSTOMS INSPECTION AND RELEASE - DAY 9 | LUBUMBASHI ENROUTE KOLWEZI | ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 05-02-2025
BA2825 | CAT CP13GC VIBRATORY COMPACTOR | 5,630 x 2,310 x 3,090 - 12520KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 54700103 | CAT0CP13H54700103 | MFX14978 | FML2412DSI2637 | VESSEL: TOREADOR Voy. 034 - ETA DURBAN 14-01-2025 | COD 2025 100421 | BL47WKZN | BL64PBZN | ND59407 | OFFLOADED 11-02-2025 |  |  | 10-01-2025 | BV NUMBER RECEIVED | 14-01-2025 | 20-01-2025 | 21-01-2025 | 22-01-2025 | 22-01-2025 | 23-01-2025 | 25-01-2025 | 26-01-2025 | 27-01-2025 | 28-01-2025 | 30-01-2025 | 30-01-2025 | 31-01-2025 | 31-01-2025 | 31-01-2025 | 04-02-2025 | 04-02-2025 | 06-02-2025 | 07-10-2025 | 08-10-2025 | 08-10-2025 | 11-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | VESSEL IN AND WORKING | COLLECTING UNIT FROM PORT TODAY | UNIT COLLECTED FROM PORT - BV INSPECTION TO BE DONE THIS AFTERNOON | BV INSPECTION COMPLETED - DISPATCHING DURBAN TODAY | VAN REENEN ENROUTE JOHANNESBURG | BELA BELA ENROUTE BEIT BRIDGE BORDER | MUSINA ENROUTE BEIT BRIDGE FOR CLEARANCE | BEIT BRIDGE RSA BORDER CLEARING | HARARE ENROUTE CHIRUNDU | CHINOYI ENROUTE CHRIRUNDU BORDER | CHIRUNDU BORDER ZIM SIDE CLEARING | CHIRUNDU BORDER ZAM SIDE CLEARING | KABWE ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE WAING TRUCKER SEAL | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | KANYAKA AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 11-02-2025
BA2823 | CAT CP13GC VIBRATORY COMPACTOR | 5,630 x 2,310 x 3,090 - 12520KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 54700101 | CAT0CP13A54700101 | MFX14948 | FML2412DSI2637 | VESSEL: TOREADOR Voy. 034 - ETA DURBAN 14-01-2025 | COD 2025 100421 | ND834401 | ND854241 | ND59404 | OFFLOADED 18-02-2025 |  |  | 10-01-2025 | BV NUMBER RECEIVED | 14-01-2025 | 23-01-2025 | 24-01-2025 | 24-01-2025 | 25-01-2025 | 25-01-2025 | 28-01-2025 | 01-02-2025 | 02-02-2025 | 02-02-2025 | 04-02-2025 | 05-02-2025 | 05-02-2025 | 06-02-2025 | 06-02-2025 | 10-02-2025 | 10-02-2025 | 12-02-2025 | 13-02-2025 | 13-02-2025 | 14-02-2025 | 18-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | VESSEL IN AND WORKING | COLLECTING UNIT FROM PORT TODAY | UNIT COLLECTED FROM PORT - BV INSPECTION TO BE DONE THIS AFTERNOON | BV INSPECTION COMPLETED - DISPATCHING DURBAN TODAY | VEHICLE TO DISPATCH TOMORROW FOR THE BORDER | VEHICLE TO DISPATCH TODAY ONCE HEAVY RAINS CLEAR UP | DISPATCHED ENROUTE JOHANNESBURG | PIETERMARITSBURG ENROUTE JOHANNESBURG | BEIT BRIDGE RSA BORDER CLEARING | BEIT BRIDGE RSA BORDER CLEARING | CHIVHU ENROUTE HARARE | GWERU ENROUTE HARARE | KWEKWE ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE WAITING RELEASE | LUSAKA ENROUTE KASUMBALESA BORDER | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER, ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER, DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | DISPATCHING WHISKEY | KIMBEMBE ENROUTE KOLWEZI | LIKASHI - VEHICLE STOPPED BY ANTI FRAUD - AWAITING CONNEX TO PROVIDE DOCUMENTS | ON SITE, WAITING TO OFFLOAD | ON SITE, WAITING TO OFFLOAD - DAY 4 PLEASE ASSIST | OFFLOADED 18-02-2025 | OFFLOADED 18-02-2025
BA2824 | CAT CP13GC VIBRATORY COMPACTOR | 5,630 x 2,310 x 3,090 - 12520KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 54700102 | CAT0CP13L54700102 | MFX14975 | FML2412DSI2637 | VESSEL: TOREADOR Voy. 034 - ETA DURBAN 14-01-2025 | COD 2025 100421 | ND834401 | ND854241 | ND59404 | OFFLOADED 18-02-2025 |  |  | 10-01-2025 | BV NUMBER RECEIVED | 14-01-2025 | 23-01-2025 | 24-01-2025 | 24-01-2025 | 25-01-2025 | 25-01-2025 | 28-01-2025 | 01-02-2025 | 02-02-2025 | 02-02-2025 | 04-02-2025 | 05-02-2025 | 05-02-2025 | 06-02-2025 | 06-02-2025 | 10-02-2025 | 10-02-2025 | 12-02-2025 | 13-02-2025 | 13-02-2025 | 14-02-2025 | 18-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-01-2024 | VESSEL IN AND WORKING | COLLECTING UNIT FROM PORT TODAY | UNIT COLLECTED FROM PORT - BV INSPECTION TO BE DONE THIS AFTERNOON | BV INSPECTION COMPLETED - DISPATCHING DURBAN TODAY | VEHICLE TO DISPATCH TOMORROW FOR THE BORDER | VEHICLE TO DISPATCH TODAY ONCE HEAVY RAINS CLEAR UP | DISPATCHED ENROUTE JOHANNESBURG | PIETERMARITSBURG ENROUTE JOHANNESBURG | BEIT BRIDGE RSA BORDER CLEARING | BEIT BRIDGE RSA BORDER CLEARING | CHIVHU ENROUTE HARARE | GWERU ENROUTE HARARE | KWEKWE ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE WAITING RELEASE | LUSAKA ENROUTE KASUMBALESA BORDER | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER, ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER, DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | DISPATCHING WHISKEY | KIMBEMBE ENROUTE KOLWEZI | LIKASHI - VEHICLE STOPPED BY ANTI FRAUD - AWAITING CONNEX TO PROVIDE DOCUMENTS | ON SITE, WAITING TO OFFLOAD | ON SITE, WAITING TO OFFLOAD - DAY 4 PLEASE ASSIST | OFFLOADED 18-02-2025 | OFFLOADED 18-02-2025
BA2757 | CAT988K WHEEL LOADER | 10,36 x 3,56 x 4,27 - 46266KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | S3E00236 | CAT00988TS3E00236 | H4E01662 | FML2502DSI2671 | VESSEL: CRYSTAL ACE Voy. 0107A - ETA DURBAN: 27-02-2025 | COD 2025 129381 PT01 | BJ60GTZN | BN39DMZN / BN54MHZN | MFST002992 | OFFLOADED 25-03-2025 |  |  | 28-02-2025 | BV COMPLETED | 27-02-2025 | 05-03-2025 | MIDDELBURG 07-03-2025 | MIDDELBURG 07-03-2025 | 10-03-2025 | 10-03-2025 | 11-03-2025 | 12-03-2025 | 13-03-2025 | 13-03-2025 | 16-03-2025 | 16-03-2025 | 17-03-2025 | 18-03-2025 | MOKAMBO 18-03-2025 | MOKAMBO 20-03-2025 | 20-03-2025 | 21-03-2025 | 21-03-2025 | 22-03-2025 | 22-03-2025 | 25-03-2025 | [33 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-02-2025 | VESSEL DUE TO ARRIVE PM TODAY | VESSEL IN AND WORKING - PLEASE ASSIST WITH THE BV NUMBER | LOADING FROM PORT TODAY - BV INSPECTION BOOKED FOR TOMORROW 04-03-2025 | BV INSPECTION BOOKED FOR TODAY 04-03-2025 | BV INSPECTION COMPLETED - CURRENTLY IN PETERMARITZBURG AWAITING POLICE ESCORTS | UMVOTI ENROUTE BEIT BRIDGE BORDER | STANDERTON ENROUTE BEIT BRIDGE BORDER | POLOKWANE ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ZIM ENROUTE HARARE | CHIKOMBA ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHISAMBA ENROUTE MOKAMBO BORDER | APPROCHING KITWE | MOKAMBO BORDER ZAMBIAN SIDE AWAITING CLEARANCE | MOKAMBO BORDER ZAMBIAN SIDE AWAITING CLEARANCE | ON SITE - WAITING FINAL CLEARANCE AND OFFLOADING | ON SITE - WAITING TO OFFLOADING | OFFLOADED 25-03-2025

## OFFLOADED - 2024
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | BV RECEIVED | BV COMPLETE | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY ARR | WHISKY DISPATCH | LUBUMBASHI ARR | LUBUMBASHI DSP | KOLWEZI ARR | OFFLOADED | COMMENTS 30-08-2022
BA2054 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | DXZ03312 | CAT0226BJDXZ03312 | CZ208651 | FML2206DSI1629 | COD 2022 256498 | AJB9958 | N/A | FML2206DSI1629 | VESSEL: BUXCOAST Voy. 0206W ETA: 01-07-2022 | OFFLOADED 28-08-2022 | 02-08-2022 | 05.08.2022 | BV NUMBER RECEIVED AND BV INSPECTION BOOKED FOR 05-08-2022 | 03.07.2022 | 05.08.2022 | 06.08.2022 | 06.08.2022 | 07.08.2022 | 07.08.2022 | 07.08.2022 | 08.08.2022 | 09.08.2022 | 10.08.2022 | 11.08.2022 | 11.08.2022 | 11.08.2022 | 18.08.2022 | 18.08.2022 | 24-08-2022 | 24-08-2022 | 24-08-2022 | 24-08-2022 | 28-08-2022 | OFFLOADED 28-08-2022
BA2055 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | DXZ03313 | CAT0226BCDXZ03313 | CZ208655 | FML2206DSI1628 | COD 2022 256440 | AJB9958 | N/A | FML2206DSI1628 | VESSEL: BUXCOAST Voy. 0206W ETA: 01-07-2022 | OFFLOADED 28-08-2022 | 02-08-2022 | 05.08.2022 | BV NUMBER RECEIVED AND BV INSPECTION BOOKED FOR 05-08-2022 | 03.07.2022 | 05.08.2022 | 06.08.2022 | 06.08.2022 | 07.08.2022 | 07.08.2022 | 07.08.2022 | 08.08.2022 | 09.08.2022 | 10.08.2022 | 11.08.2022 | 11.08.2022 | 11.08.2022 | 18.08.2022 | 18.08.2022 | 24-028-2022 | 24-08-2022 | 24-08-2022 | 24-08-2022 | 28-08-2022 | OFFLOADED 28-08-2022
BA2056 | 1 X CAT 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | DXZ03333 | CAT0226BLDXZ03333 | CZ208683 | FML2207DSI1661 | COD 2022 256499 | AEZ8923 | AEU6975 | FML2207DSI1661 | VESSEL: NYK PAULA Voy. 2227W ETA 29-07-2022 | * OFFLOADED 07.09.2022 | 02-08-2022 | 05.08.2022 | BV NUMBER RECEIVED AND BV INSPECTION BOOKED FOR 05-08-2022 | 29-07-2022 | 05.08.2022 | 08.08.2022 | 09.08.2022 | 10.08.2022 | 12.08.2022 | 14.08.2022 | 14.08.2022 | 15.08.2022 | 18.08.2022 | 18.08.2022 | 19.08.2022 | 21-08-2022 | 27-08-2022 | 27-08-2022 | 31-08-2022 | 01-09-2022 | 01-09-2022 | 02.09.2022 | 07.09.20222 | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | TRUCK IN JOHANNESBURG UNDER GOING TRIP CHECK | TRUCK IS IN POLOKWANE, THE DRIVER IS ILL AND IS SEEING A DOCTOR BEFORE DISPATCH TO BEITBRIDGE BORDER | TRUCK AND MUSINA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE UNDER CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM AWAITING RELEASE | * VEHICLE CURRENTLY AT KITWE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE IN DIE QUEUE TO CROSS TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE WAITING RELEASE IN ORDER TO PROCEED TO WHISKEY | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | LIKSASI EN-ROUTE TO SITE | ON SITE AWAITING TO OFFLOAD | VEHICLE ARRIVED ON SITE 02.09.2022 - WAITING TO OFFLOAD | VEHICLE ARRIVED ON SITE 02.09.2022 - WAITING TO OFFLOAD - DAY 5 | * OFFLOADED 07.09.2022
BA2057 | 1 X CAT 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | DXZ03334 | CAT0226BHDXZ03334 | CZ208675 | FML2207DSI1661 | COD 2022 256438 | AEZ8923 | AEU6975 | FML2207DSI1661 | VESSEL: NYK PAULA Voy. 2227W ETA 29-07-2022 | * OFFLOADED 07.09.2022 | 02-08-2022 | 05.08.2022 | BV NUMBER RECEIVED AND BV INSPECTION BOOKED FOR 05-08-2022 | 29-07-2022 | 05.08.2022 | 08.08.2022 | 09.08.2022 | 10.08.2022 | 12.08.2022 | 14.08.2022 | 14.08.2022 | 15.08.2022 | 18.08.2022 | 18.08.2022 | 19.08.2022 | 21-08-2022 | 27-08-2022 | 27-08-2022 | 31-08-2022 | 01-09-2022 | 01-09-2022 | 02.09.2022 | 07.09.20222 | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | TRUCK IN JOHANNESBURG UNDER GOING TRIP CHECK | TRUCK IS IN POLOKWANE, THE DRIVER IS ILL AND IS SEEING A DOCTOR BEFORE DISPATCH TO BEITBRIDGE BORDER | TRUCK AND MUSINA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE UNDER CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM AWAITING RELEASE | * VEHICLE CURRENTLY AT KITWE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE IN DIE QUEUE TO CROSS TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE WAITING RELEASE IN ORDER TO PROCEED TO WHISKEY | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | LIKSASI EN-ROUTE TO SITE | ON SITE AWAITING TO OFFLOAD | VEHICLE ARRIVED ON SITE 02.09.2022 - WAITING TO OFFLOAD | VEHICLE ARRIVED ON SITE 02.09.2022 - WAITING TO OFFLOAD - DAY 5 | * OFFLOADED 07.09.2022
BA2117 | 1 X CAT 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | DXZ03335 | CAT0226BEDXZ03335 | CZ208647 | FML2207DSI1661 | COD 2022 256444 | AEZ8923 | AEU6975 | FML2207DSI1661 | VESSEL: NYK PAULA Voy. 2227W ETA 29-07-2022 | * OFFLOADED 07.09.2022 | 02-08-2022 | 05.08.2022 | BV NUMBER RECEIVED AND BV INSPECTION BOOKED FOR 05-08-2022 | 29-07-2022 | 05.08.2022 | 08.08.2022 | 09.08.2022 | 10.08.2022 | 12.08.2022 | 14.08.2022 | 14.08.2022 | 15.08.2022 | 18.08.2022 | 18.08.2022 | 19.08.2022 | 21-08-2022 | 27-08-2022 | 27-08-2022 | 31-08-2022 | 01-09-2022 | 01-09-2022 | 02.09.2022 | 07.09.20222 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 29.07.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 29.07.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 29.07.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 29.07.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 29.07.2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | TRUCK IN JOHANNESBURG UNDER GOING TRIP CHECK | TRUCK IS IN POLOKWANE, THE DRIVER IS ILL AND IS SEEING A DOCTOR BEFORE DISPATCH TO BEITBRIDGE BORDER | TRUCK AND MUSINA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE UNDER CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM AWAITING RELEASE | * VEHICLE CURRENTLY AT KITWE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE IN DIE QUEUE TO CROSS TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE WAITING RELEASE IN ORDER TO PROCEED TO WHISKEY | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | LIKSASI EN-ROUTE TO SITE | ON SITE AWAITING TO OFFLOAD | VEHICLE ARRIVED ON SITE 02.09.2022 - WAITING TO OFFLOAD | VEHICLE ARRIVED ON SITE 02.09.2022 - WAITING TO OFFLOAD - DAY 5 | * OFFLOADED 07.09.2022
BA2118 | 1 X CAT 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | DXZ03336 | CAT0226BCDXZ03336 | CZ208642 | FML2207DSI1661 | COD 2022 256441 | AEZ8923 | AEU6975 | FML2207DSI1661 | VESSEL: NYK PAULA Voy. 2227W ETA 29-07-2022 | * OFFLOADED 07.09.2022 | 02-08-2022 | 05.08.2022 | BV NUMBER RECEIVED AND BV INSPECTION BOOKED FOR 05-08-2022 | 29-07-2022 | 05.08.2022 | 08.08.2022 | 09.08.2022 | 10.08.2022 | 12.08.2022 | 14.08.2022 | 14.08.2022 | 15.08.2022 | 18.08.2022 | 18.08.2022 | 19.08.2022 | 21-08-2022 | 27-08-2022 | 27-08-2022 | 31-08-2022 | 01-09-2022 | 01-09-2022 | 02.09.2022 | 07.09.20222 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 29.07.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 29.07.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 29.07.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 29.07.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 29.07.2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 | TRUCK IN JOHANNESBURG UNDER GOING TRIP CHECK | TRUCK IS IN POLOKWANE, THE DRIVER IS ILL AND IS SEEING A DOCTOR BEFORE DISPATCH TO BEITBRIDGE BORDER | TRUCK AND MUSINA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE UNDER CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM AWAITING RELEASE | * VEHICLE CURRENTLY AT KITWE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE IN DIE QUEUE TO CROSS TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE WAITING RELEASE IN ORDER TO PROCEED TO WHISKEY | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | LIKSASI EN-ROUTE TO SITE | ON SITE AWAITING TO OFFLOAD | VEHICLE ARRIVED ON SITE 02.09.2022 - WAITING TO OFFLOAD | VEHICLE ARRIVED ON SITE 02.09.2022 - WAITING TO OFFLOAD - DAY 5 | * OFFLOADED 07.09.2022
BA2191 | 1 X CAT426F2 BACKHOE LOADER (8 PIECES) | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | EJ405363 | CAT0426FEEJ405363 | CC205552 | FML2206DSI1629 | COD 2022 256494 | NU112272 | ND629383 | ND60549 | VESSEL: BUXCOAST Voy. 0206W ETA: 01-07-2022 | OFFLOADED 14-09-2022 | 02-08-2022 | 05.08.2022 | BV NUMBER RECEIVED AND BV INSPECTION BOOKED FOR 05-08-2022 | 03.07.2022 | 24-08-2022 | MIDDELBURG 25-08-2022 | MIDDELBURG 26-08-2022 | 26-08-2022 | 26-08-2022 | 29-08-2022 | 31.08.2022 | 02.09.2022 | 03.09.2022 | 04.09.2022 | 05.09.2022 | 06.09.2022 | 07.09.2022 | 08.09.2022 | 10-09-2022 | 10-09-2022 | 12-09-2022 | 12-09-2022 | 14-09-2022 | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION - LOADING PLANNED FOR 11-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 - LOADING PLANNED FOR 11-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 - LOADING PLANNED FOR 11-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 - LOADING PLANNED FOR 11-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 - LOADING PLANNED FOR 11-08-2022 | BV NUMBER RECEIVED 02-08-2022 - BV INSPECTION TO BE BOOKED FOR 05-08-2022 - LOADING PLANNED FOR 11-08-2022 | BV COMPLETE AND TRUCK TO LOAD AND DISPATCH ON THE 17/08/2022 ONCE RETURN FROM DRC | BV COMPLETE AND TRUCK TO LOAD AND DISPATCH ON THE 17/08/2022 ONCE RETURN FROM DRC | BV COMPLETE AND TRUCK TO LOAD AND DISPATCH ON THE 17/08/2022 ONCE RETURN FROM DRC | BV COMPLETE AND TRUCK TO LOAD AND DISPATCH ON THE 19/08/2022 ONCE RETURN FROM DRC | BV COMPLETE AND TRUCK TO LOAD AND DISPATCH ON THE 19/08/2022 ONCE RETURN FROM DRC | BV COMPLETE AND TRUCK TO LOAD AND DISPATCH ON THE 19/08/2022 ONCE RETURN FROM DRC | BV COMPLETE AND TRUCK TO LOAD AND DISPATCH ON THE 23/08/2022 ONCE RETURN FROM DRC | LOADING TODAY | DISPATCHING DURBAN TODAY | CAMPERDOWN ENROUTE JOHANNESBURG | HOWICK ENROUTE JOHANNESBURG | MIDDELBURG ENROUTE MUSINA | BEIT BRIDGE RSA SIDE | MASVINGO ENROUTE HARARE | HARARE EN-ROUTE TO CHIRUNDU | CHINOYI EN-ROUTE TO CHIRUNDU | CHIRUNDU AWAITING CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | LUBUMBASHI | ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 14-09-2022
BA2133 | 1 X NEW CAT D8GC TRACTOR | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | KGX00358 | CAT000D8LKGX00358 | TXJ02313 | FML2208DSI1688 | COD 2022 261563 | ND834401 | ND654346 / ND526680 | ND60576 | VESSEL: PAGNA ETA: 01-09-2022 | OFFLOADED 10-11-2022 | 05-08-2022 | 09-09-2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED AS SOON AS THE UNIT WAS AVAILABLE | 02-09-2022 | 05.10.2022 | 07.10.2022 | 08.10.2022 | 10.10.2022 | 11.10.2022 | 12.10.2022 | 13-10-2022 | 13-10-2022 | 15-10-2022 | 17-10-2022 | 17-10-2022 | 17-10-2022 | 19-10-2022 | 24.10.2022 | 25.10.2022 | 26.10.2022 | 28.10.2022 | 31.10.2022 | 31.10.2022 | 01.11.2022 | 10-11-2022 | [11 empty] | AWAITING VESSEL ARRIVAL ON THE 01/09/2022 | AWAITING VESSEL ARRIVAL ON THE 01/09/2022 | AWAITING VESSEL ARRIVAL ON THE 01/09/2022 | AWAITING VESSEL ARRIVAL ON THE 01/09/2022 | AWAITING VESSEL ARRIVAL ON THE 01/09/2022 | AWAITING VESSEL ARRIVAL ON THE 01/09/2022 | AWAITING VESSEL ARRIVAL ON THE 01/09/2022 | AWAITING VESSEL ARRIVAL ON THE 30/08/2022 | AWAITING VESSEL ARRIVAL ON THE 30/08/2022 | AWAITING VESSEL ARRIVAL ON THE 30/08/2022 | AWAITING VESSEL ARRIVAL ON THE 30/08/2022 | AWAITING VESSEL ARRIVAL ON THE 30/08/2022 | AWAITING VESSEL ARRIVAL ON THE 01/09/2022 | AWAITING VESSEL ARRIVAL ON THE 01/09/2022 | AWAITING VESSEL ARRIVAL ON THE 01/09/2022 | THE VESSEL IS IN AND WORKING | THE VESSEL IS CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNIT ONCE AVAILABLE | * UNIT IS AT OUR FACILITY - BV INSPECTION TO BE BOOKED FOR FRIDAY 09.09.2022 | * UNIT IS AT OUR FACILITY - BV INSPECTION TO BE BOOKED FOR FRIDAY 09.09.2022 | * UNIT IS AT OUR FACILITY - BV INSPECTION TO BE BOOKED FOR FRIDAY 09.09.2022 - LOADING PLANNED for 19-09-2022 | * UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED for 19-09-2022 | * UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED for 19-09-2022 | * UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED for 19-09-2022 | * UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED for 22-09-2022 | * UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED for 23-09-2022 | * UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED for 23-09-2022 | * UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED for 23-09-2023 | * UNIT IS PLANNED TO LOAD ON MONDAY AND DISPATCH THE 29/09/2022 AS WE ARE AWAITING OUR TRUCK TO RETURN FROM DRC | * UNIT IS PLANNED TO LOAD ON WEDNESDAY AND DISPATCH THE 29/09/2022 AS WE ARE AWAITING OUR TRUCK TO RETURN FROM DRC | * UNIT IS PLANNED TO LOAD ON WEDNESDAY AND DISPATCH THE 29/09/2022 AS WE ARE AWAITING OUR TRUCK TO RETURN FROM DRC | VEHICLE ARRIVED AND IS CURRENTLY IN THE WORKSHOP UNDER GOING MAINTENANCE - LOADING FRIDAY 30-09 AND DISPATCHING MONDAY 03-10 | VEHICLE ARRIVED AND IS CURRENTLY IN THE WORKSHOP UNDER GOING MAINTENANCE - LOADING FRIDAY 30-09 AND DISPATCHING MONDAY 03-10 | VEHICLE ARRIVED AND IS CURRENTLY IN THE WORKSHOP UNDER GOING MAINTENANCE - PLANNING TO DISPATCH ON MONDAY 03-10-2022 | VEHICLE ARRIVED AND IS CURRENTLY IN THE WORKSHOP UNDER GOING MAINTENANCE - PLANNING TO DISPATCH ON MONDAY 05-10-2022 | VEHICLE ARRIVED AND IS CURRENTLY IN THE WORKSHOP UNDER GOING MAINTENANCE - PLANNING TO DISPATCH ON MONDAY 05-10-2022 | DISPATCHING DURBAN ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT ESTCOURT ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT VOLKSRUST ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT MUSINA EN-ROUTE TO BEITBRDIGE BORDER | VEHICLE CURRENTLY AT BEITBRDIGE BORDER | VEHICLE CURRENTLY AT MASVINGO EN-ROUTE TO CHIRUNDU | VEHICLE CURRENTLY AT MVUMA EN-ROUTE TO CHIRUNDU | VEHICLE CURRENTLY AT KAROI EN-ROUTE TO CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU | VEHICLE CURRENTLY KABWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY NDOLA ON BREAKSOEN, WAITING FOR NEW HORSE TO COLLECT VEHICLE | VEHICLE CURRENTLY AT KITWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHILLIBOMWE IN THE QUE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA DRC AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT LUBUMBASHI | * VEHICLE CURRENTLY AT KOLWEZI EN-ROUTE TO SITE | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE AWAITING FINAL CLEARANCE AND OFFLOADING | * VEHICLE CURRENTLY ON SITE AWAITING FINAL CLEARANCE AND OFFLOADING | * VEHICLE CURRENTLY ON SITE AWAITING FINAL CLEARANCE AND OFFLOADING | * VEHICLE CURRENTLY ON SITE AWAITING FINAL CLEARANCE AND OFFLOADING | STILL ON SITE WAITING TO OFFLOAD - PLEASE ASSIST | OFFLOADED 10-11-2022 | OFFLOADED 10-11-2022
BA2287 | 1 X CAT 980-14A WHEEL LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | MK900546 | CAT00980JMK900546 | P4E05317 | FML2209DSI1744 | COD 2022 291355 | ND491242 | ND256330 | ND63616 | VESSEL: TARIFA ETA: 27-09-2022 | OFFLOADED | 16.09.2022 | 03.10.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 27-09-2022 | 12.10.2022 | 15-10-2022 | 03-11-2022 | 08-11-2022 | 08-11-2022 | 10-11-2022 | 12.11.2022 | 13.11.2022 | 14.11.2022 | 14.11.2022 | 14.11.2022 | 14.11.2022 | 15.11.2022 | 17.11.2022 | 19-11-2022 | 19-11-2022 | 21-11-2022 | 22-11-2022 | 24-11-2022 | 24-11-2022 | 01-12-2022 | [29 empty] | * WAITING VESSEL ARRIVAL - CURRENT ETA 05.10.2022 | * WAITING VESSEL ARRIVAL - CURRENT ETA 05.10.2022 | * WAITING VESSEL ARRIVAL - CURRENT ETA 05.10.2022 | * WAITING VESSEL ARRIVAL - CURRENT ETA 05.10.2022 | * WAITING VESSEL ARRIVAL - CURRENT ETA 05.10.2022 | * WAITING VESSEL ARRIVAL - CURRENT ETA 05.10.2022 | * WAITING VESSEL ARRIVAL - CURRENT ETA 05.10.2022 | * WAITING VESSEL ARRIVAL - CURRENT ETA 05.10.2022 | * WAITING VESSEL ARRIVAL - CURRENT ETA 05.10.2023 | * WAITING VESSEL ARRIVAL - CURRENT ETA 05.10.2022 | * WAITING VESSEL ARRIVAL - CURRENT ETA 27-09-2022 | * WAITING VESSEL ARRIVAL - CURRENT ETA 27-09-2022 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | COLLECTING FORM PORT TODAY - BV INSPECTION TO BE BOOKED FOR MONDAY | * BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO DISPATCH 05.10.2022 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH 08.10.2022 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH 08.10.2022 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH 08.10.2022 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH 12.10.2022 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH 12.10.2022 | TRUCK AT PIETERMARITZBURG EN-ROUTE TO JNB | TRUCK AT HARRISMITH EN-ROUTE TO JOHANNESBURG | TRUCK AT VILLIERS EN-ROUTE TO JOHANNESBURG | JOHANNESBURG | JOHANNESBURG UNDERGOING MAINTENANCE | JOHANNESBURG UNDERGOING MAINTENANCE | JOHANNESBURG WAITING LIMPOPO PERMITS | JOHANNESBURG WAITING LIMPOPO PERMITS | JOHANNESBURG WAITING LIMPOPO PERMITS | JOHANNESBURG WAITING LIMPOPO PERMITS | JOHANNESBURG WAITING LIMPOPO PERMITS | JOHANNESBURG WAITING LIMPOPO PERMITS | JOHANNESBURG WAITING LIMPOPO PERMITS | JOHANNESBURG WAITING LIMPOPO PERMITS - SHOULD RECEIVE PERMIT BY TOMORROW | JOHANNESBURG WAITING LIMPOPO PERMITS - SHOULD RECEIVE PERMIT BY TOMORROW | JOHANNESBURG WAITING LIMPOPO PERMITS - SHOULD RECEIVE PERMIT BY TOMORROW | TRUCK TO DISPATCH JOHANNESBURG EN-ROUTE TO BEITBRIDGE BORDER | BELA BELA ENROUTE BEIT BRIDGE | MOKOPANE ENROUTE MUSINA | POLOKWANE ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE WAITING ESCORT | MASVINGO ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KITWE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT CHILILABOMWE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY | * VEHICLE CURRENTLY AT KANYAKA | * VEHICLE CURRENTLY AT LUBUMBASHI ON BREAKDOWN | * VEHICLE CURRENTLY AT LUBUMBASHI WAITING ESCORT TO PROCEED TO SITE | * VEHICLE CURRENTLY AT KOLWEZI PARKING | * VEHICLE CURRENTLY AT KOLWEZI PARKING | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD DAY 11 IN DRC, STANDING TIME APPLIES | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2119 | 1 X NEW CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | DXZ03449 | CAT0226BTDXZ03449 | CZ209305 | FML2210DSI1787 | COD 2022 315476 | HL40KXGP | N/A | S2210DSI1787 | VESSEL: BUXCOAST Voy 0208W - Transhipment Vessel: SEASPAN LAHORE ETA 11-11-2022 | OFFLOADED 16-12-2022 | 19-08-2022 | 18-11-2022 | BV NUMBER RECEIVED. BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 12.11.2022 | 23-11-2022 | 24-11-2022 | 25-11-2022 | 26-11-2022 | 27-11-2022 | 02-12-2022(GRB) | 02-12-2022(FRANCIST TOWN) | 02.12.2022 | 02.12.2022 | 03.12.2022 | 03.12.2022 | 03.12.2022 | 04.12.2022 | 04.12.2022 | 06.12.2022 | 07.12.2022 | 10-12-2022 | 10-12-2022 | 10-12-2022 | 10-12-2022 | 16-12-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 22-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 22-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 08-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 08-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 08-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 10-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 11-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 11-11-2022 | * BV INSPECTION TO BE BOOKED FOR THURSDAY 17 NOV 2022 | * BV INSPECTION TO BE BOOKED FOR THURSDAY 17 NOV 2022 | * BV INSPECTION TO BE BOOKED FOR THURSDAY 17 NOV 2022 | * BV INSPECTION TO BE BOOKED FOR FRIDAY 18 NOV 2022 | BV TO BE DONE TODAY, PLANNING TO LOAD AND DISPATCH ON THE 24/11/2022 | BV INSPECTION COMPLETED, PLANNING TO LOAD AND DISPATCH ON THE 24/11/2022 | BV INSPECTION COMPLETED, PLANNING TO LOAD TODAY | LOADED - DISPATCHING DURBAN TODAY | ENROUTE JOHANNESBURG | JOHANNESBURG | GROBBLERS BRIDGE CROSSING TO BOTSWANA SIDE | GROBBLERS BRIDGE BOTSWANA SIDE AWAITING RELEASE | GROBBLERS BRIDGE BOTSWANA SIDE AWAITING RELEASE | GROBBLERS BRIDGE BOTSWANA SIDE AWAITING RELEASE, UNDERGOING CUSTOMS INSPECTION | * VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CORSS TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CORSS TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CORSS TO DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 3 | * VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD - DAY 3 PLEASE ASSIST | * VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD - DAY 4 PLEASE ASSIST | * VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD - DAY 5 PLEASE ASSIST | OFFLOADED 16-12-2022
BA2120 | 1 X NEW CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | DXZ03450 | CAT0226BEDXZ03450 | CZ209326 | FML2210DSI1787 | COD 2022 315458 | HL40KXGP | N/A | S2210DSI1787 | VESSEL: BUXCOAST Voy 0208W - Transhipment Vessel: SEASPAN LAHORE ETA 11-11-2022 | OFFLOADED 16-12-2022 | 19-08-2022 | 18-11-2022 | BV NUMBER RECEIVED. BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 12.11.2022 | 23-11-2022 | 24-11-2022 | 25-11-2022 | 26-11-2022 | 27-11-2022 | 02-12-2022(GRB) | 02-12-2022(FRANCIST TOWN) | 02.12.2022 | 02.12.2022 | 03.12.2022 | 03.12.2022 | 03.12.2022 | 04.12.2022 | 04.12.2022 | 06.12.2022 | 07.12.2022 | 10-12-2022 | 10-12-2022 | 10-12-2022 | 10-12-2022 | 16-12-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 22-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 22-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 04-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 08-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 08-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 08-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 10-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 11-11-2022 | WAITING VESSEL ARRIVAL:- ETA DURBAN PORT 11-11-2022 | * BV INSPECTION TO BE BOOKED FOR THURSDAY 17 NOV 2022 | * BV INSPECTION TO BE BOOKED FOR THURSDAY 17 NOV 2022 | * BV INSPECTION TO BE BOOKED FOR THURSDAY 17 NOV 2022 | * BV INSPECTION TO BE BOOKED FOR FRIDAY 18 NOV 2022 | BV TO BE DONE TODAY, PLANNING TO LOAD AND DISPATCH ON THE 24/11/2022 | BV INSPECTION COMPLETED, PLANNING TO LOAD AND DISPATCH ON THE 24/11/2022 | BV INSPECTION COMPLETED, PLANNING TO LOAD TODAY | LOADED - DISPATCHING DURBAN TODAY | ENROUTE JOHANNESBURG | JOHANNESBURG | GROBBLERS BRIDGE CROSSING TO BOTSWANA SIDE | GROBBLERS BRIDGE BOTSWANA SIDE AWAITING RELEASE | GROBBLERS BRIDGE BOTSWANA SIDE AWAITING RELEASE | GROBBLERS BRIDGE BOTSWANA SIDE AWAITING RELEASE, UNDERGOING CUSTOMS INSPECTION | * VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CORSS TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CORSS TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CORSS TO DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 3 | * VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD - DAY 3 PLEASE ASSIST | * VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD - DAY 4 PLEASE ASSIST | * VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD - DAY 5 PLEASE ASSIST | OFFLOADED 16-12-2022
BA2251 | 1 X NEW CAT834K WHEEL LOADER - MAIN UNIT | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | L4Y00272 | CAT0834KVL4Y00272 | TXW07021 | FML2211DSI1807 | COD 2022 339759 | CR84FXGP | WGR358GP / WGR365GP | ND63691-1 | VESSEL: VALIANT ACE ETA: 22-11-2022 | OFFLOADED 19-12-2022 | 18-11-2022 | 30.11.2022 | BV NUMBER RECEIVED. BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 22-11-2022 | 30-11-2022 | 01-12-2022 | 01-12-2022 | 02-12-2022 | 02-12-2022 | 03.12.2022 | 04.12.2022 | 04.12.2022 | 05.12.2022 | 06.12.2022 | 07.12.2022 | 07-12-2022 | 08-12-2022 | 08-12-2022 | 12-12-2022 | 12-12-2022 | 14-12-2022 | 14-12-2022 | [16 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | VESSEL IN AND WORKING - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | VESSEL IN AND WORKING - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | VESSEL IN AND WORKING - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | TRUCK IS AT VAN REENEN EN-ROUTE TO JOHANNESBURG | TRUCK IS AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLY AT LUSAKA ENROUTE KASUMBALESA | * VEHICLE CURRENLY AT KAPIRI ENROUTE KASUMBALESA | * VEHICLE CURRENLY AT KASUMBALESA ZAMBIAN SIDE | * VEHICLE CURRENLY AT KASUMBALESA DRC SUCTOMS IN QUEUE TO MOVE TO WHISKEY | * VEHICLE CURRENLY AT WHISKEY | * VEHICLE CURRENLY DISPATCHING WHISKEY | * VEHICLE CURRENLY KANYAKA WAITING RELEASE | OFFLOADED 19-12-2022
BA2251 | 1 X NEW CAT834K WHEEL LOADER - PARTS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | L4Y00272 | CAT0834KVL4Y00272 | TXW07021 | FML2211DSI1807 | COD 2022 339759 | TBA | TBA | ND63691-2 | VESSEL: VALIANT ACE ETA: 22-11-2022 | OFFLOADED 05-01-2023 | 18-11-2022 | 30.11.2022 | BV NUMBER RECEIVED. BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 22-11-2022 | 30-11-2022 | 01-12-2022 | 01-12-2022 | 02-12-2022 | 02-12-2022 | 03.12.2022 | 04.12.2022 | 04.12.2022 | 05.12.2022 | 08-12-2022 | 08-12-2022 | 09-12-2022 | 10-12-2022 | 16-12-2022 | 19-12-2022 | 19-12-2022 | 28-12-2022 | 29-12-2022 | 30-12-2022 | 30-12-2022 | 05-01-2023 | [13 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-11-2022 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | VESSEL IN AND WORKING - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | VESSEL IN AND WORKING - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | VESSEL IN AND WORKING - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | TRUCK TO LOAD AND DISPATCH TODAY | TRUCK IS AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING RIT | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT CHINGOLA IN THE QUEUE TO PROCEED TO KASUMBALESA | * VEHICLE CURRENTLY AT CHILILABOMBWE IN THE QUEUE TO PROCEED TO KASUMBALESA | * VEHICLE CURRENTLY AT CHILILABOMBWE IN THE QUEUE TO PROCEED TO KASUMBALESA | * VEHICLE CURRENTLY IN THE QUEUE BEFORE KASUMBALESA ZAMBIA | * VEHICLE CURRENTLY AT WHISKEY - DAY 1 | * VEHICLE CURRENTLY AT WHISKEY - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY - DAY 8 | * VEHICLE CURRENTLY AT KANYAKA AWAIITNG FINAL CLEARANCE AND RELEASE | * VEHICLE CURRENTLY AT LUALABA EN-ROUTE TO KOLWEZI | * VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD - DAY 5 - PLEASE ASSIST | * VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD - DAY 6 - PLEASE ASSIST | OFFLOADED 05-01-2023
BA2301 | 1 X CAT D8GC TRACTOR | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | KGX00403 | CAT000D8KKGX00403 | TXJ02395 | FML2211DSI1819 | COD 2022 355818 | ND705348 | ND184465 | ND63732 | VESSEL: GAURDIAN LEADER Boy. 106 - ETA DURBAN: 18-12-2022 | OFFLOADED 31-01-2023 | 14-12-2022 | 03-01-2023 | BV NUMBER RECEIVED. BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 09-01-2023 | 09-01-2023 | 10.01.2023 | 10.01.2023 | 10-01-2023 | 10-01-2023 | 13-01-2023 | 13-01-2023 | 14-01-2023 | 15-01-2023 | 17-01-2023 | 18-01-2023 | 18-01-2023 | 19-01-2023 | 22-01-2023 | 25-01-2023 | 25-01-2023 | 27-01-2023 | 27-01-2023 | 30-01-2023 | 30-01-2023 | 31-01-2023 | [38 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2022 | VESSEL ARRIVED - CURRENTLY WORKING | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR TOMORROW 22-12-2022 - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR TODAY 22-12-2022 - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR NEXT WEEK - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR NEXT WEEK - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR NEXT WEEK - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR NEXT WEEK - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | BV INSPECTION COMPLETE - UNIT LOADED PLANNING TO DISPATCH 05-01-2023 | BV INSPECTION COMPLETE - UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH | PERMIT RECEIVED - VEHICLE TO DISPATCH THIS AFTERNOON DUE TO BAD WEATHER | PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY MUSINA CLEARING | * VEHICLE CURRENTLY AT BEIT BRIDGE CLEARING | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE WAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY WAITING OCC | TRUCK AT CONNEX AFRICA PARKING KOLWEZI AWAITING RELEASE | TRUCK AT KOLWEZI AWAIITNG TO OFFLOAD | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023
BA2302 | 1 X CAT D8GC TRACTOR | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | KGX00404 | CAT000D8JKGX00404 | TXJ02349 | FML2211DSI1820 | COD 2022 357597 | ND142761 | ND542263 | ND63733 | VESSEL: GAURDIAN LEADER Boy. 106 - ETA DURBAN: 18-12-2022 | OFFLOADED 31-01-2023 | 14-12-2022 | 03-01-2023 | BV NUMBER RECEIVED. BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 18-12-2022 | 05-01-2023 | MIDDELBURG 09-01-2023 | MIDDELBURG 09-01-2023 | 09.01.2023 | 10.01.2023 | 12-01-2023 | 13-01-2023 | 13-01-2023 | 14-01-2023 | 18-01-2023 | 18-01-2023 | 19-01-2023 | 19-01-2023 | 22-01-2023 | 25-01-2023 | 25-01-2023 | 27-01-2023 | 27-01-2023 | 30-01-2023 | 30-01-2023 | 31-01-2023 | [38 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 17-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2022 | VESSEL ARRIVED - CURRENTLY WORKING | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR TOMORROW 22-12-2022 - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR TODAY 22-12-2022 - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR NEXT WEEK - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR NEXT WEEK - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR NEXT WEEK - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | COLLECTED FORM PORT - BV INSPECTION TO BE BOOKED FOR NEXT WEEK - TO DISPATCH FIRST WEEK IN JANUARY DUE TO EMBARGOS | BV INSPECTION COMPLETE - UNIT LOADED PLANNING TO DISPATCH 05-01-2023 | * VEHICLE CURRENTLY AT MOOIRIVER ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT VOLKSRUST ENROUTE JOHANNESBURG | GROBLERSDAL ENROUTE MUSINA | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAITING RELEASE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE - AWAITING RELEASE | * VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE WAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY WAITING OCC | TRUCK AT CONNEX AFRICA PARKING KOLWEZI AWAITING RELEASE | TRUCK AT KOLWEZI AWAIITNG TO OFFLOAD | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023
BA2301 / BA2302 | 2 X FSS TO BE FITTED TO 2 X CAT D8GC TRACTORS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | N/A | N/A | N/A | FML2211DSI1819 / FML2211DSI1820 | COD 2022 355818 / COD 2022 357597 | JZ30RYGP | N/A | FML2211DSI1819 | VESSEL: GAURDIAN LEADER Boy. 106 - ETA DURBAN: 18-12-2022 | OFFLOADED 14-02-2023 | 14-12-2022 | 03-01-2023 | BV INSPECTION COMPLETE | 18.12.2022 | 08.01.2023 | 09.01.2023 | 17-01-2023 | 18-01-2023 | 19-01-2023 | 19-01-2023 | 19-01-2023 | 20-01-2023 | 23-01-2023 | 30-01-2023 | 03-02-2023 | 03-02-2023 | 06-02-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | 09-02-2023 | 09-02-2023 | 09-02-2023 | 10-02-2023 | 14-02-2023 | [51 empty] | VEHICLE LOADING FSS TODAY | VEHICLE LOADED ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG TO PROCEED TO POLOKWANE | * VEHICLE CURRENTLY AT JOHANNESBURG TO DISPATCH TODAY FOR MUSINA | * VEHICLE CURRENTLY AT PRETORIA ENROUTE MUSINA | * VEHICLE CURRENTLY AT POLOKWANE ENROUTE MUSINA | * VEHICLE CURRENTLY AT JOHANNESBURG - DISPATCHING TOMORROW | * VEHICLE LOADED - TO DISPATCH THIS AFTERNOON | VEHICLE CURRENLTY AT POLOKWANE ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT POLOKWANE ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAMBIAN SIDE | VEHICLE AT CHIRUNDU ZAMBIAN SIDE ON BREAKDOWN | VEHICLE AT CHIRUNDU ZAMBIAN SIDE ON BREAKDOWN | VEHICLE AT CHIRUNDU ZAMBIAN SIDE ON BREAKDOWN | VEHICLE AT CHIRUNDU ON BREAKDOWN, AWAITING ESTIMATED REPAIR DATE | VEHICLE AT CHIRUNDU ON BREAKDOWN, AWAITING ESTIMATED REPAIR DATE | VEHICLE AT CHIRUNDU ON BREAKDOWN, AWAITING ESTIMATED REPAIR DATE | VEHICLE AT CHIRUNDU ON BREAKDOWN, TRUCK TO BE REPAIRED BY TOMMROW THE 03/02/2023 | VEHICLE AT NDOLA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT SAKANIA DRC SIDE - WAITING RELEASE TO PROCEED TO KASUMBALESA | VEHICLE CURRENLTY AT SAKANIA DRC SIDE - WAITING RELEASE TO PROCEED TO KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - WAITING RELEASE TO PROCEED TO WHISKEY | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD - DAY 4 | VEHICLE ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 14-02-2023 | OFFLOADED 14-02-2023
BA2338 | CAT980-14A WHEEL LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | MK900654 | CAT00980CMK900654 | P4E05119 | FML2211DSI1844 | COD 2022 355806 | ND730794 | ND443606 | ND63764 | VESSEL: RCC AFRICA Voy. 020 - ETA DURBAN: 15-01-2023 | OFFLOADED 14-02-2023 | 13-12-2022 | 18-01-2023 | BV INSPECTION COMPLETE | 15-01-2023 | 23-01-2023 | MIDDELBURG 23-01-2023 | MIDDELBURG 24-01-2023 | 24-01-2023 | 25-01-2023 | 26-01-2023 | 28-01-2023 | 30-01-2023 | 30-01-2023 | 31-01-2023 | 05-02-2023 | 05-02-2023 | 05-02-2023 | 06-02-2023 | 06-02-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | 09-02-2023 | 10-02-2023 | 14-02-2023 | [38 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN: TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN: TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN: TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN: TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN: TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN: TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN: 14-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 14-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 14-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 14-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 14-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 14-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 14-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 16-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 15-01-2023 | VESSEL ARRIVED & CURRENTLY WORKING | * COLLECTING UNIT FROM PORT TODAY | CURRENTLY LOADING UNIT IN PORT | CURRENTLY LOADING UNIT IN PORT | BV INSPECTION COMPLETE - UNIT TO DISPATCH ONCE PERMIT IS ISSUED | VEHICLE IN PIETERMARITZBURG ENROUTE JOHANNESBURG | VEHICLE IN MIDDELBURG ENROUTE MUSINA | VEHICLE CURRENTLY AT MUSINA | VEHICLE CURRENTLY AT BEIT BRIDGE CLEARING | VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | TRUCK AT CHIRUNDU ZIM SIDE AWAITING RELEASE | TRUCK AT CHIRUNDU ZAM SIDE AWAITING RELEASE | TRUCK AT KAPIRI MPOSHE ENROUTE KASUMBULESA | TRUCK ATCHILLABOMBWE EN ROUTE KASUMBULESA | TRUCK AT CHILLABOMBWE EN ROUTE KASUMBULESA | VEHICLE AT KASUMBULESA DRC SIDE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE DISPATCHING WHISKEY | VEHICLE AT CONNEX LUBUMBASHI | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD - DAY 4 | VEHICLE ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 14-02-2023 | OFFLOADED 14-02-2023
BA2426 | 1 X CAT D10T2 TRACK TYPE TRACTOR - ACCESSORIES | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01282 | CAT0D10TCRAB01282 | JZM1280 | FML2301DSI1895 | COD 2023 111066 | AJC3808 | AJC3423T / AJC3420T | 2301DSI1895 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 25-01-2023 | OFFLOADED 27-02-2023 | 21-01-2023 | 31-01-2023 | BV INSPECTION COMPLETE | 26.01.2023 | 31.01.2023 | 01.02.2023 | 02.02.2023 | 03.02.2023 | 03.02.2023 | 03-02-2023 | 04-02-2023 | 04-02-2023 | 04-02-2023 | 05-02-2023 | 06-02-2023 | 06-02-2023 | 06-02-2023 | 15-02-2023 | 18-02-2023 | 18-02-2023 | 20-02-2023 | 23-02-2023 | 24-02-2023 | 26-02-2023 | 27-02-2023 | [57 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING ACCESSORIES FROM PORT TODAY - BV INSPECTION BOOKED FOR MONDAY | BV INSPECTION BOOK FOR TODAY. TRUCK TO DISPACTH AFTER BV INSPECTION | TRUCK TO DISPATCH DURBAN TODAY EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE CURRENTLY IN JOHANNESBURG ENROUTE MUSINA | VEHICLE DISPATCHED JOHANNESBURG EN ROUTE TO BEITBRIDGE BORDER | VEHICLE AT BEITBRIDGE BORDER AWAITING CLEARANCE | VEHICLE DISPATCHED LUSAKA ENROUTE KITWE | VEHICLE IN QUEUE TO ENTER KASUMBALESA | VEHICLE IN QUEUE TO ENTER KASUMBALESA | VEHICLE CURRENLTY IN QUEUE TO ENTER KASUMBALESA | VEHICLE CURRENLTY IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE KASUMBALESA ZAMBIAN SIDE | VEHICLE KASUMBALESA ZAMBIAN SIDE | VEHICLE WHISKEY WAITING RELEASE | VEHICLE ENROUTE KANYAKA | VEHICLE ENROUTE KANYAKA | VEHICLE CLEARING AT KANYAKA | VEHICLE AT LUBUMBASHI EN-ROUTE TO SITE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 27-02-2023 | OFFLOADED 27-02-2023
BA2427 | 1 X CAT D10T2 TRACK TYPE TRACTOR - ACCESSORIES | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01326 | CATCD10TPRAB01326 | JZM01341 | FML2301DSI1896 | COD 2023 111053 | AAZ7684 | AAZ1615 / AAF6810 | 2301DSI1896 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 25-01-2023 | OFFLOADED 01-03-2023 | 21-01-2023 | 31-01-2023 | BV INSPECTION COMPLETE | 26.01.2023 | 31.01.2023 | 31.01.2023 | 01.02.2023 | 03.02.2023 | 03.02.2023 | 05-02-2023 | 05-02-2023 | 06-02-2023 | 07-02-2023 | 08-02-2023 | 08-02-2023 | 09-02-2023 | 09-02-2023 | 19-02-2023 | 20-02-2023 | 20-02-2023 | 22-02-2023 | 23-02-2023 | 24-02-2023 | 28-02-2023 | 01-03-2023 | [5 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING ACCESSORIES FROM PORT TODAY - BV INSPECTION BOOKED FOR MONDAY | BV INSPECTION BOOK FOR TODAY. TRUCK TO DISPACTH AFTER BV INSPECTION | TRUCK TO DISPATCH DURBAN TODAY EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE CURRENTLY IN JOHANNESBURG ENROUTE MUSINA | VEHICLE DISPATCHED JOHANNESBURG EN ROUTE TO BEITBRIDGE BORDER | VEHICLE AT BEITBRIDGE BORDER AWAITING CLEARANCE | VEHICLE AT HARARE TO DISPATCH FOR CHIRUNDU | VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | VEHICLE CHRUNDU ZAMBIAN SIDE | VEHICLE ENROUTE KASUMBALESA | VEHICLE CURRENLTY IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE KASUMBALESA ZAMBIAN SIDE | VEHICLE KASUMBALESA ZAMBIAN SIDE | VEHICLE AT WHISKEY WAITING RELEASE | VEHICLE AT WHISKEY WAITING RELEASE | VEHICLE CLEARING AT KANYAKA | VEHICLE AT LUBUMBASHI EN-ROUTE TO SITE | VEHICLE AT LUBUMBASHI | VEHICLE ENROUTE SITE | ON SITE WAITING TO OFFLOAD | OFFLOADED 01-03-2023
BA2337 | 1 X CAT D10T2 TRACK TYPE TRACTOR - ACCESSORIES | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01446 | CAT0D10TARAB01446 | JZM01523 | FML2301DSI1894 | COD 2023 112528 | AAZ5337 | AAZ1571 / AAZ1679 | 2301DSI1894 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 24-01-2023 | OFFLOADED 01-03-2023 | 22-01-2023 | 31-01-2023 | BV INSPECTION COMPLETE | 26.01.2023 | 31.01.2023 | 01.02.2023 | 02.02.2023 | 03.02.2023 | 03.02.2023 | 05-02-2023 | 05-02-2023 | 05-02-2023 | 06-02-2023 | 07-02-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | 15-02-2023 | 19-02-2023 | 20-02-2023 | 22-02-2023 | 23-02-2023 | 24-02-2023 | 27-02-2023 | 01-03-2023 | [5 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING ACCESSORIES FROM PORT TODAY - BV INSPECTION BOOKED FOR MONDAY | BV INSPECTION BOOK FOR TODAY. TRUCK TO DISPACTH AFTER BV INSPECTION | TRUCK TO DISPATCH DURBAN TODAY EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE CURRENTLY IN JOHANNESBURG ENROUTE MUSINA | VEHICLE DISPATCHED JOHANNESBURG EN ROUTE TO BEITBRIDGE BORDER | VEHICLE AT BEITBRIDGE BORDER AWAITING CLEARANCE | VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE UNDER CLEARANCE | VEHICLE CURRENLTY ENROUTE KITWE | VEHICLE CURRENLTY IN QUEUE TO ENTER KASUMBALESA | VEHICLE CURRENLTY IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE KASUMBALESA ZAMBIAN SIDE | VEHICLE KASUMBALESA ZAMBIAN SIDE | VEHICLE KASUMBALESA ZAMBIAN SIDE | VEHICLE WHISKEY WAITING RELEASE | VEHICLE WHISKEY WAITING RELEASE | VEHICLE CLEARING AT KANYAKA | VEHICLE AT LUBUMBASHI EN-ROUTE TO SITE | VEHICLE AT LUBUMBASHI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 01-03-2023
BA2429 | 1 X CAT D10T2 TRACK TYPE TRACTOR - MAIN UNIT | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01327 | CAT0D10TKRAB01327 | JZM01354 | FML2301DSI1898 | COD 2023 111042 | BCC5591 | ACL6505T / ACL3942T | ND59152 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 25-01-2023 | OFFLOADED 01-03-2023 | 21-01-2023 | 31-01-2023 | BV INSPECTION COMPLETE | 26.01.2023 | 06-02-2023 | 07-02-2023 | 08-02-2023 | 08-02-2023 | 09-02-2023 | 10-02-2023 | 10-02-2023 | 10-02-2023 | 11-02-2023 | 18-02-2023 | 18-02-2023 | 19-02-2023 | 20-02-2023 | 22-02-2023 | 22-02-2023 | 22-02-2023 | 25-02-2023 | 25-02-2023 | 26-02-2023 | 26-02-2023 | 01-03-2023 | [5 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR TUESDAY - ESTIMATED LOADING DATE 10-15 FEBRUARY | COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR TUESDAY - ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | LOADED - AWAITING PERMIT | LOADED - AWAITING PERMIT | TRUCK DISPATCHED DURBAN EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE AT HARRISMITH EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE DISPATCHING JOHANNESBURG FOR BEITBRIDGE BORDER | VEHICLE CURRENTLY AT BEITBRIDGE AWAITING CLEARANCE | VEHICLE CURRENTLY AT BUBI ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNIU ZAMBIAN SIDE | VEHICLE CURRENTLY AT CHIRUNIU ZAMBIAN SIDE WAITING ABNORMAL PERMIT | VEHICLE CURRENTLY AT CHIRUNIU ZAMBIAN SIDE WAITING ABNORMAL PERMIT | VEHICLE CURRENTLY AT CHIRUNIU ZAMBIAN SIDE WAITING ABNORMAL PERMIT | VEHICLE STILL AT CHIRUNIU ZAMBIAN SIDE WAITING ABNORMAL PERMIT - BACKLOG WITH PERMITS | VEHICLE STILL AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE STILL AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE AT WHISKEY DAY 1 | VEHICLE AT WHISKEY DAY 2 | VEHICLE AT KOLWEZI ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 01-03-2023
BA2429 | 1 X CAT D10T2 TRACK TYPE TRACTOR - ACCESSORIES | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01327 | CAT0D10TKRAB01327 | JZM01354 | FML2301DSI1898 | COD 2023 111042 | ABB9432 | AAZ1663 / AAZ1664 | 2301DSI1898 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 25-01-2023 | OFFLOADED 01-03-2023 | 21-01-2023 | 31-01-2023 | BV INSPECTION COMPLETE | 26.01.2023 | 31.01.2023 | 31.01.2023 | 01.02.2023 | 03.02.2023 | 03.02.2023 | 04-02-2023 | 04-02-2023 | 05-02-2023 | 05-02-202 | 06-02-2023 | 06-02-2023 | 07-02-2023 | 07-02-2023 | 15-02-2023 | 18-02-2023 | 18-02-2023 | 20-02-2023 | 23-02-2023 | 24-02-2023 | 25-02-2023 | 01-03-2023 | [5 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING ACCESSORIES FROM PORT TODAY - BV INSPECTION BOOKED FOR MONDAY | BV INSPECTION BOOK FOR TODAY. TRUCK TO DISPACTH AFTER BV INSPECTION | TRUCK TO DISPATCH DURBAN TODAY EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE CURRENTLY IN JOHANNESBURG ENROUTE MUSINA | VEHICLE DISPATCHED JOHANNESBURG EN ROUTE TO BEITBRIDGE BORDER | VEHICLE AT BEITBRIDGE BORDER AWAITING CLEARANCE | VEHICLE CURRENTY AT CHIRUNDU | VEHICLE CURRENTLY AT KABWE WNROUTE KITWE | VEHICLE IN QUEUE TO ENTER KASUMBALESA | VEHICLE CURRENLTY IN QUEUE TO ENTER KASUMBALESA | VEHICLE CURRENLTY IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE KASUMBALESA DRC SIDE | VEHICLE WHISKEY WAITING RELEASE | VEHICLE ENROUTE KANYAKA | VEHICLE ENROUTE KANYAKA | VEHICLE CLEARING AT KANYAKA | VEHICLE AT LUBUMBASHI EN-ROUTE TO SITE | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 01-03-2023
BA2337 | 1 X CAT D10T2 TRACK TYPE TRACTOR - MAIN UNIT | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01446 | CAT0D10TARAB01446 | JZM01523 | FML2301DSI1894 | COD 2023 112528 | XYP614GP | CV71JLGP / DD10RDGP | ND59150 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 24-01-2023 | OFFLOADED 02-03-2023 | 22-01-2023 | 31-01-2023 | BV INSPECTION COMPLETE | 26.01.2023 | 03.02.2022 | 07-02-2023 | 08-02-2023 | 08-02-2023 | 09-02-2023 | 11-02-2023 | 12-02-2023 | 13-02-2023 | 13-02-2023 | 19-02-2023 | 20-02-2023 | 20-02-2023 | 22-02-2023 | 23-02-2023 | 24-02-2023 | 24-02-2023 | 25-02-2023 | 25-02-2023 | 26-02-2023 | 27-02-2023 | 02-03-2023 | [5 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR TUESDAY - ESTIMATED LOADING DATE 10-15 FEBRUARY | BV INSPECTION BOOKED FOR TUESDAY - ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | TRUCK DISPATCHED DURBAN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK DISPATCHED LADYSMITH EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE AT PRETORIA EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE DISPATCHING PRETORIA FOR BEITBRIDGE BORDER | VEHICLE AT BEITBRIDGE AWAITING CLEARANCE | VEHICLE AT BEITBRIDGE AWAITING RELEASE | VEHICLE AT HARARE | VEHICLE AT CHIRUNDU ZAMBIAN SIDE | VEHICLE AT CHIRUNDU ZAMBIAN SIDE - AWAITING ABNORMAL PERMITS | VEHICLE AT CHIRUNDU ZAMBIAN SIDE - AWAITING ABNORMAL PERMITS | VEHICLE AT CHIRUNDU ZAMBIAN SIDE - AWAITING ABNORMAL PERMITS | VEHICLE AT KAPIRI MPOSHE ENROUTE KASUMBALESA | VEHICLE AT NDOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA EN ROUTE KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBALESA DRC SIDE DAY 1 | VEHICLE ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 02-03-2023 | OFFLOADED 02-03-2023
BA2428 | 1 X CAT D10T2 TRACK TYPE TRACTOR - ACCESSORIES | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01319 | CAT0D10THRAB01319 | JAM01153 | FML2301DSI1897 | COD 2023 111046 | ABB9583 | AAS7084 / AAS7085 | 2301DSI1897 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 25-01-2023 | OFFLOADED 07-03-2023 | 21-01-2023 | 30-01-2023 | BV INSPECTION COMPLETE | 26.01.2023 | 31.01.2023 | 31.01.2023 | 01.02.2023 | 03.02.2023 | 03.02.2023 | 05-02-2023 | 06-02-2023 | 06-02-2023 | 07-02-2023 | 07-02-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | 16-02-2023 | 18-02-2023 | 18-02-2023 | 22-02-2023 | 23-02-2023 | 24-02-2023 | 28-02-2023 | 07-03-2023 | [5 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING ACCESSORIES FROM PORT TODAY - BV INSPECTION BOOKED FOR MONDAY | BV INSPECTION BOOK FOR TODAY. TRUCK TO DISPACTH AFTER BV INSPECTION | TRUCK TO DISPATCH DURBAN TODAY EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE CURRENTLY IN JOHANNESBURG ENROUTE MUSINA | VEHICLE DISPATCHED JOHANNESBURG EN ROUTE TO BEITBRIDGE BORDER | VEHICLE AT BEITBRIDGE BORDER AWAITING CLEARANCE | VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE UNDER CLEARANCE | VEHICLE ENROUTE KITWE | VEHICLE CURRENLTY IN QUEUE TO ENTER KASUMBALESA | VEHICLE CURRENLTY IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE STILL IN QUEUE TO ENTER KASUMBALESA | VEHICLE AT CHILILAMBOBWE IN QUEUE TO ENTER KASUMBALESA | VEHICLE KASUMBALESA ZAMBIAN SIDE | VEHICLE WHISKEY WAITING RELEASE | VEHICLE WHISKEY WAITING RELEASE | VEHICLE WHISKEY WAITING RELEASE | VEHICLE CLEARING AT KANYAKA | VEHICLE AT LUBUMBASHI EN-ROUTE TO SITE | VEHICLE AT LUBUMBASHI | VEHICLE ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD - DAY 7 - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD - DAY 7 - PLEASE ASSIST | OFFLOADED 07-03-2023
BA2426 | 1 X CAT D10T2 TRACK TYPE TRACTOR - MAIN UNIT | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01282 | CAT0D10TCRAB01282 | JZM1280 | FML2301DSI1895 | COD 2023 111066 | DB92CWGP | DH85MCGP / DB44HVGP | ND59151 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 25-01-2023 | OFFLOADED 15-03-2023 | 21-01-2023 | 31-01-2023 | BV INSPECTION COMPLETE | 25-01-2023 | 10-02-2023 | 13-01-2023 | 20-02-2023 | 22-02-2023 | 23-02-2023 | 24-02-2023 | 25-02-2023 | 26-02-2023 | 26-02-2023 | 28-02-2023 | 28-02-2023 | 01-03-2023 | 01-03-2023 | 05-03-2023 | 09-03-2023 | 09-03-2023 | 10-03-2023 | 10-03-2023 | 12-03-2023 | 13-03-2023 | 15-03-2023 | [5 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR TUESDAY - ESTIMATED LOADING DATE 10-15 FEBRUARY | COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR TUESDAY - ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE 10-15 FEBRUARY | UNIT CURRENLTY LOADING - PLANNING TO DISPATCH THIS AFTERNOON | VEHICLE CURRENTLY AT CATO RIDGE ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT VILLIERS JOHANNESBURG | VEHICLE CURRENTLY AT PRETORIA WAITING LIMPOPO PERMITS | VEHICLE CURRENTLY AT PRETORIA WAITING LIMPOPO PERMITS | VEHICLE CURRENTLY AT PRETORIA WAITING LIMPOPO PERMITS | VEHICLE STILL IN PRETORIA WAITING LIMPOPO PERMITS - BACKLOG WITH PERMITS | VEHICLE STILL IN PRETORIA WAITING LIMPOPO PERMITS - BACKLOG WITH PERMITS | VEHICLE AT POLOKWANE ENROUTE MUSINA | VEHICLE AT POLOKWANE EN ROUTE BEITBRIDGE | VEHICLE AT BEITBRIDGE ZIM SIDE AWAITING RELEASE | VEHICLE AT CHIVHU EN-ROUTE TO CHIRUNDU | VEHICLE AT CHIRUNDU ZIM SIDE | VEHICLE AT CHIRUNDU ZIM SIDE CROSSING TO ZAM SIDE | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE AT KASUMBALESA DRC SIDE | VEHICLE AT KASUMBALESA DRC SIDE - DAY 2 | VEHICLE AT WHISKEY WAITING RELEASE | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD - DAY 2 | VEHICLE ON SITE WAITING TO OFFLOAD - DAY 3 | VEHICLE ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 15-03-2023 | OFFLOADED 15-03-2023 | OFFLOADED 15-03-2023 | OFFLOADED 15-03-2023 | OFFLOADED 15-03-2023
BA2427 | 1 X CAT D10T2 TRACK TYPE TRACTOR - MAIN UNIT | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01326 | CATCD10TPRAB01326 | JZM01341 | FML2301DSI1896 | COD 2023 111053 | KH29PBGP | JN34XCGP | 2301DSI1896-1 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 25-01-2023 | OFFLOAD (STANDING TIME APPLICABLE FOR 3 DAYS) | 21-01-2023 | 01-02-2023 | BV INSPECTION COMPLETE | 26.01.2023 | 06-02-2023 | 13-02-2023 | 16-02-2023 | 17-02-2023 | 17-02-2023 | 22-02-2023 | 24-02-2023 | 25-02-2023 | 26-02-2023 | 03-03-2023 | 05-03-2023 | 07-03-2023 | 07-03-2023 | 10-03-2023 | 12-03-2023 | 14-03-2023 | 15-03-2023 | 15-03-2023 | 16-03-2023 | 17-03-2023 | 20-03-2022 | [5 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR TUESDAY | COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR TUESDAY | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON THE 01/02/2023 | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON THE 01/02/2023 | BV COMPLETED AND TRUCK TO DISPATCH ON THE 03/02/2022 | BV COMPLETED AND TRUCK TO DISPATCH ON MONDAY THE 06/02/2022 AS THE TRUCK AWAITED FOR HIS PERMIT | VEHICLE TO DISPATCH THIS AFTERNOON | VEHICLE AT CATO-RIDGE ENROUTE PIETERMARITZBURG | VEHICLE AT DALTON ENROUTE MIDDELBURG | VEHICLE AT LADYSMITH ENROUTE JOHANNESBURG | VEHICLE AT NEWCASTLE - TO DISPATCH AS SOON AS WEATHER CLEARS | VEHICLE AT VOLKSRUST | VEHICLE AT POMONA BUSY WITH ROUTINE CHECK BEFORE DISPATCHING FOR THE BORDER | VEHICLE AT POMONA BUSY WITH ROUTINE CHECK BEFORE DISPATCHING FOR THE BORDER | VEHICLE DISPATCH POMONA ENROUTE MUSINA | VEHICLE AT PIERTERSBURG ENROUTE MUSINA | VEHICLE AT MUSINA CLEARING | VEHICLE AT BEIT BRIDGE WAITING ZIM NOTIFICATION | VEHICLE AT BEIT BRIDGE ZIM SIDE AWAITING RELEASE | VEHICLE AT MASVINGO EN-ROUTE TO CHIRUDNU | VEHICLE AT HARARE EN-ROUTE TO CHIRUDNU | VEHICLE AT CHIRUDNU ZIM SIDE | VEHICLE AT CHIRUDNU ZAM SIDE | VEHICLE AT CHIRUDNU ZIM SIDE | VEHICLE AT CHIRUDNU ZAM SIDE | VEHICLE DISPATCHING CHIRUDNU ZAM SIDE TODAY | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KABWE ENROUTE KASUMBALESA | VEHICLE AT NDOLA ENROUTE KASUMBALESA | VEHICLE AT CHILIBOMBWE IN THE QUE TO KASUMBALESA | VEHICLE DISPATCHED KASUMBALESA ENROUTE WHISKEY | VEHICLE DISPATCHED KASUMBALESA ENROUTE WHISKEY | VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | VEHICLE CURRENLTY AT LUBUMBASHI ENROUTE LIKASI | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD DAY 3(STANDING TIME APPLICABLE) | OFFLOAD (STANDING TIME APPLICABLE FOR 3 DAYS) | OFFLOAD (STANDING TIME APPLICABLE FOR 3 DAYS) | OFFLOAD (STANDING TIME APPLICABLE FOR 3 DAYS)
BA2428 | 1 X CAT D10T2 TRACK TYPE TRACTOR - MAIN UNIT | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01319 | CAT0D10THRAB01319 | JAM01153 | FML2301DSI1897 | COD 2023 111046 | KR85BVGP | NT74888 / NT79777 | 2301DSI1897-1 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 25-01-2023 | OFFLOAD (STANDING TIME APPLICABLE FOR 3 DAYS) | 21-01-2023 | 01-02-2023 | BV INSPECTION COMPLETE | 26.01.2023 | 06-02-2023 | 13-02-2023 | 16-02-2023 | 17-02-2023 | 17-02-2023 | 22-02-2023 | 24-02-2023 | 25-02-2023 | 26-02-2023 | 03-03-2023 | 05-03-2023 | 07-03-2023 | 07-03-2023 | 10-03-2023 | 12-03-2023 | 14-03-2023 | 15-03-2023 | 15-03-2023 | 16-03-2023 | 17-03-2023 | 20-03-2022 | [5 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR TUESDAY | COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR TUESDAY | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON THE 01/02/2023 | UNIT IS AT OUR FACILITY AND BV WILL BE DONE ON THE 01/02/2023 | BV COMPLETED AND TRUCK TO DISPATCH ON THE 03/02/2022 | BV COMPLETED AND TRUCK TO DISPATCH ON MONDAY THE 06/02/2022 AS THE TRUCK AWAITED FOR HIS PERMIT | VEHICLE TO DISPATCH THIS AFTERNOON | VEHICLE AT CATO-RIDGE ENROUTE PIETERMARITZBURG | VEHICLE AT DALTON ENROUTE MIDDELBURG | VEHICLE AT LADYSMITH ENROUTE JOHANNESBURG | VEHICLE AT NEWCASTLE - TO DISPATCH AS SOON AS WEATHER CLEARS | VEHICLE AT VOLKSRUST | VEHICLE AT POMONA BUSY WITH ROUTINE CHECK BEFORE DISPATCHING FOR THE BORDER | VEHICLE AT POMONA BUSY WITH ROUTINE CHECK BEFORE DISPATCHING FOR THE BORDER | VEHICLE DISPATCH POMONA ENROUTE MUSINA | VEHICLE AT PIERTERSBURG ENROUTE MUSINA | VEHICLE AT MUSINA CLEARING | VEHICLE AT BEIT BRIDGE WAITING ZIM NOTIFICATION | VEHICLE AT BEIT BRIDGE ZIM SIDE AWAITING RELEASE | VEHICLE AT MASVINGO EN-ROUTE TO CHIRUDNU | VEHICLE AT HARARE EN-ROUTE TO CHIRUDNU | VEHICLE AT CHIRUDNU ZIM SIDE | VEHICLE AT CHIRUDNU ZAM SIDE | VEHICLE AT CHIRUDNU ZIM SIDE | VEHICLE AT CHIRUDNU ZAM SIDE | VEHICLE DISPATCHING CHIRUDNU ZAM SIDE TODAY | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KABWE ENROUTE KASUMBALESA | VEHICLE AT NDOLA ENROUTE KASUMBALESA | VEHICLE AT CHILIBOMBWE IN THE QUE TO KASUMBALESA | VEHICLE DISPATCHED KASUMBALESA ENROUTE WHISKEY | VEHICLE DISPATCHED KASUMBALESA ENROUTE WHISKEY | VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | VEHICLE CURRENLTY AT LUBUMBASHI ENROUTE LIKASI | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD DAY 3(STANDING TIME APPLICABLE) | OFFLOAD (STANDING TIME APPLICABLE FOR 3 DAYS) | OFFLOAD (STANDING TIME APPLICABLE FOR 3 DAYS) | OFFLOAD (STANDING TIME APPLICABLE FOR 3 DAYS)
BA2289 | CAT366 BUCKET | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | N/A | N/A | N/A | FML2301DSI1892 | COD 2023 103294 | AJB9958 | N/A | 2301DSI1892 | VESSEL: MORNING LUCY Voy. EE233 - ETA DURBAN: 06-02-2023 | OFFLOADED 23-03-2023 | 07-01-2023 | 09-02-2023 | BV INSPECTION COMPLETE | 06-02-2023 | 16-02-2023 | 16-02-2023 | 23-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 01-03-2023 | 01-03-2023 | 07-03-2023 | 08-03-2023 | 08-03-2023 | 08-03-2023 | 10-03-2023 | 14-03-2023 | 15-03-2023 | 17-03-2023 | 18-03-2023 | 18-03-2023 | 20-03-2023 | 23-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 05-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 05-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 05-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 05-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 05-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 05-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 05-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 05-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 05-02-2023 | AWAITING VESSEL ARRIVAL 06-02-2023 | VESSEL CURRENLTY IN AND WORKING | BUCKET COLLECTED FROM PORT - BV INSPECTION BOOKED FOR THURSDAY 09-02-2023 | BUCKET COLLECTED FROM PORT - BV INSPECTION BOOKED FOR THURSDAY 09-02-2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH TOMORROW | ENROUTE JOHANNESBURG | NEW CASTLE ENROUTE JOHANNESBURG | VOLKSRUST ENROUTE JOHANNESBURG | VILLIERS ENROUTE JOHANNESBURG | JOHANNESBURG | JOHANNESBURG TO DISPATCH TODAY | VEHICLE AT POLOKWANE ENROUTE MUSINA | VEHICLE AT POLOKWANE EN ROUTE BEITBRIDGE | VEHICLE AT BEITBRIDGE AWAITING CLEARANCE | VEHICLE AT BEITBRIDGE AWAITING CLEARANCE | VEHICLE CURRENTLY DISPATCHING HARERE | VEHICLE AT CHINHOYI ENROUTE CHIRUNDU | VEHICLE AT KAROI ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZIM SIDE | VEHICLE DISPATCHING CHIRUNDU ZAM SIDE | VEHICLE AT CHIRUNDU ZAM SIDE TO DISPATCH TODAY | VEHICLE AT LUWANYA ENROUTE LUSAKA | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHCILE CURRENTLY CROSSING TO KASUMBALESA DRC SIDE | VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | VEHICLE CURRENTLY AT WHISKEY AWAITING SEGUCE - DAY 7 | VEHICLE CURRENTLY AT KCC AWAITING TO OFFLOAD | VEHICLE CURRENTLY AT KCC AWAITING TO OFFLOAD DAY 4 | OFFLOADED 23-03-2023
BA2348 | CAT CS78B VIBRATORY COMPACTOR | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | M7800601 | CATCS78BLM7800601 | E7A57701 | FML2212DSI1871 | COD 2022 366650 | SBG558GP | JXD441GP | ND63733 | VESSEL: DALIAN HIGHWAY Voy. 97 ETA DURBAN: 28-01-2023 | OFFLOADED 23-03-2023 | 29-12-2022 | 09-02-2023 | BV INSPECTION COMPLETE | 28/01/2023 | 16-02-2023 | 16-02-2023 | 23-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 01-03-2023 | 01-03-2023 | 07-03-2023 | 08-03-2023 | 08-03-2023 | 08-03-2023 | 10-03-2023 | 14-03-2023 | 15-03-2023 | 17-03-2023 | 18-03-2023 | 18-03-2023 | 20-03-2023 | 23-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 29-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 29-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 29-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 29-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 30-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 28-01-2023 | VESSEL IS IN AND WORKING. AWAITING FOR UNIT TO DISCHARGE FROM PORT | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION TO BE COMPLETED AND LOADING DATE | BV INSPECTION TO BE DONE TODAY | BV COMPLETED AWAIITNG DISPATCH DATE | TRUCK PLAN TO LOAD AND DISPATCH ON THE 08/02/2023 | VEHICLE PLANNING TO DISPATCH 08-02-2023 | VEHICLE PLANNING TO DISPATCH 08-02-2023 | VEHICLE PLANNING TO DISPATCH 09-02-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - AWAITING RETURN VEHICLE IN ORDER TO LOAD & DISPATCH | BV INSPECTION COMPLETE - AWAITING RETURN VEHICLE IN ORDER TO LOAD & DISPATCH - LOADING PLANNED FOR THIS WEEK | BV INSPECTION COMPLETE - AWAITING RETURN VEHICLE IN ORDER TO LOAD & DISPATCH - LOADING PLANNED FOR THIS WEEK | LOADING PLANNED FOR TOMORROW | DISPATCHING DURBAN FOR JOHANNESBURG | JOHANNESBURG | JOHANNESBURG WAITING LIMPOPO PERMITS | JOHANNESBURG WAITING LIMPOPO PERMITS | JOHANNESBURG WAITING LIMPOPO PERMITS | TRUCK TO DISPATCH JNB TODAY EN-ROUTE TO BEITBRIDGE | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | TRUCK AT HARARE | HARARE WORKSHOP BUSY WITH MAINTANANCE CHECK | VEHICLE DISPATCHING HARARE | VEHICLE AT CHRUNDU ZIM SIDE CLEARING | VEHICLE AT CHRUNDU ZAM SIDE CLEARING | VEHICLE AT CHRUNDU ZAM SIDE UNDER CUSTOMS INSPECTION | VEHICLE AT CHRUNDU ZAM SIDE UNDER CUSTOMS INSPECTION | VEHICLE AT KAFUE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE KASUMBALESA | VEHCILE CURRENTLY CROSSING TO KASUMBALESA DRC SIDE | VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | VEHICLE CURRENTLY AT WHISKEY AWAITING SEGUCE - DAY 7 | VEHICLE CURRENTLY AT KCC AWAITING TO OFFLOAD | VEHICLE CURRENTLY AT KCC AWAITING TO OFFLOAD DAY 4 | OFFLOADED 23-03-2023
BA2291 | 1 X CAT777-05B OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | 7W802623 | CAT00777A7W802623 | ZRK00533 | FML2209DSI1776 | COD 2023 112530 | KK84NZGP | CK44FRGP / CK06VYGP | ND63629 | REMOVAL FROM BONDED FACILITY | OFFLOADED 01-04-2023 | 23-01-2023 | 30-01-2023 | BV INSPECTION COMPLETE | 08/10/2022 | 07-02-2023 | 17-02-2023 | 20-02-2023 | 22-02-2023 | 24-02-2023 | 23-02-2023 | 25-02-2023 | 12-03-2023 | 13-03-2023 | 22-03-2023 | 23-03-2023 | 23-03-2023 | 26-03-2023 | 26-03-2023 | 28-03-2023 | 28-03-2023 | 29-03-2023 | 29-03-2023 | 30-03-2023 | 31-03-2023 | 01-04-2023 | [5 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER & COLLECTION OF FSS | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR 25-01-2023 | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV INSPECTION BOOKED FOR MONDAY 30-01-2023 - LOADING 1ST WEEK IN FEBRUARY | BV INSPECTION BOOKED FOR MONDAY 30-01-2023 - LOADING 1ST WEEK IN FEBRUARY | BV COMPLETED. ESTIMATED LOADING DATE 07/02/2023 | LOADING TODAY | TRUCK LOADED AND TO DISPATCH ON THE 03/02/2023 | TRUCK LOADED AND TO DISPATCH ON THE 06/02/2023 | TRUCK LOADED AND TO DISPATCH ON THE 06/02/2023 | VEHICLE CURRENLTY AT CAMPERDOWN ENROUTE PIETERMARITZBURG | VEHICLE AT CAMPERDOWN WAITING POLICE ESCORTS | VEHICLE CURRENTLY AT GREYTOWN ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT GREYTOWN AWAING METRO POLICE ESCOURT | VEHICLE CURRENTLY AT GREYTOWN AWAING METRO POLICE ESCOURT | VEHICLE CURRENTLY AT COLENSO ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT COLENSO ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT VAN REENEN ENROUTE JOHANNESBURG | VEHICLE STILL AT VAN REENEN WAITING POLICE ESCORT | VEHICLE STILL AT VAAL MARINA WAITING POLICE ESCORT | VEHICLE AT GROBLERSDAL ENROUTE MUSINA | VEHICLE AT GROBLERSDAL ENROUTE MUSINA | VEHICLE AT MUSINA EN-ROUTE | VEHICLE AT BEITBRIDGE RSA SIDE | VEHICLE AT HARARE | VEHICLE DISPATCHING HARARE | VEHICLE DISPATCHING HARARE - WAITED FOR POLICE ESCORTS | VEHICLE AT CHINOYI ENROUTE CHIRUNDU | VEHICLE AT HARARE WITH MINOR BREAKDOWN | VEHICLE AT HARARE WITH MINOR BREAKDOWN | VEHICLE AT HARARE WITH MINOR BREAKDOWN | VEHICLE AT HARARE WITH MINOR BREAKDOWN | VEHICLE AT HARARE WITH MAJOR BREAKDOWN - ESTIMATED DEPARTURE 17-03-2023 | VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING PERMIT | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING PERMIT, TO DISPATCH TOMMROW THE 21/03/2023 | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING PERMIT AND RELEASE | VEHICLE CURRENLTY AT LUSAKA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT NDOLA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT WHISKEY WAITING DUTIES TO BE PAID | VEHICLE CURRENTLY DISPATCHING LUBUMBASHI | VEHICLE CURRENTLY AT KOLWEZI PARKING | OFFLOADED 01-04-2023 | OFFLOADED 01-04-2023
BA2292 | 1 X CAT777-05B OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | 7W802624 | CAT00777L7W802624 | ZRK00578 | FML2209DSI1776 | COD 2023 112524 | FS26XSGP | KB37RRGP / KB35KCGP | ND63630 | REMOVAL FROM BONDED FACILITY | OFFLOADED 01-04-2023 | 23-01-2023 | 30-01-2023 | BV INSPECTION COMPLETE | 08/10/2022 | 22/02/2023 | 08-03-2023 | 08-03-2023 | 13-03-2023 | 15-03-2023 | 16-03-2023 | 16-03-2023 | 17-03-2023 | 20-03-2023 | 22-03-2023 | 23-03-2023 | 23-03-2023 | 26-03-2023 | 26-03-2023 | 29-03-2023 | 29-03-2023 | 29-03-2023 | 29-03-2023 | 30-03-2023 | 31-03-2023 | 01-04-2023 | [5 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER & COLLECTION OF FSS | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR 25-01-2023 | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV INSPECTION BOOKED FOR MONDAY 30-01-2023 - LOADING 1ST WEEK IN FEBRUARY | BV INSPECTION BOOKED FOR MONDAY 30-01-2023 - LOADING 1ST WEEK IN FEBRUARY | BV COMPLETED. ESTIMATED LOADING DATE 09/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 09/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 09/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 09/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 09/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 16/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 16/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 16/02/2023 | LOADING TOMORROW 17-02-2023 | LOADING TODAY | LOADED WAITING POLICE ESCORT | VEHICLE AWAITING POLICE ESCORT | TRUCK TO DISPATCH AT 10H00 TODAY, AWAITING POLICE ESCORTS | TRUCK AT CAMPERDOWN EN-ROUTE TO HARRISMITH | TRUCK AT PIETERMARITZBURG EN-ROUTE TO HARRISMITH | TRUCK AT GREYTOWN ENROUTE MIDDELBURG | TRUCK AT WEENEN ENROUTE MIDDELBURG | TRUCK AT VAN REENEN ENROUTE MIDDELBURG | TRUCK AT VAN REENEN WAITING POLICE ESCORTS | TRUCK AT VAN REENEN WAITING POLICE ESCORTS | TRUCK AT SWINBURNE WAITING POLICE ESCORTS | TRUCK AT VILLIERS ENROUTE MIDDELBURG | VEHICLE AT VILLIERS WAITING POLICE ESCORTS | VEHICLE AT BRONKHORSPRUIT WAITING POLICE ESCORTS | VEHCILE CURRENTLY AT POLOKWANE ENROUTE BEITHBRIDGE | VEHCILE CURRENTLY AT DENDRON ENROUTE BEITHBRIDGE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHITUNGIZWA ENROUTE HARARE | VEHCILE CURRNELTY AT MAKUTI ENROUTE CHIRUNDU | VEHCILE CURRNELTY AT CHIRUNDU ZIM SIDE, BRIDGE UNDER MAINTANCE AND TRUCKS CAN NOT CROSS AS YET. AWAITING ESTIMATED REPAIR TIME ON BRIDGE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING PERMIT AND RELEASE | VEHICLE CURRENLTY AT KAFUE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILANGA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE WAITING RELEASE | VEHICLE CURRENTLY DISPATCHING LUBUMBASHI | VEHICLE CURRENTLY AT KOLWEZI PARKING | OFFLOADED 01-04-2023 | OFFLOADED 01-04-2023
BA2293 | 1 X CAT777-05B OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | 7W802625 | CAT00777H7W802625 | ZRK00429 | FML2209DSI1776 | COD 2023 112526 | ND760431 | ND760424 / ND760428 | ND63631 | REMOVAL FROM BONDED FACILITY | OFFLOADED | 23-01-2023 | 30-01-2023 | BV INSPECTION COMPLETE | 08/10/2022 | 17/02/2023 | MIDDELBURG 01-03-2023 | MIDDELBURG 02-03-2023 | 08-03-2023 | 13-03-2023 | 14-03-2023 | 16-03-2023 | 17-03-2023 | 20-03-2023 | 24-03-2023 | 26-03-2023 | 27-03-2023 | 28-03-2023 | 30-03-2023 | 01-04-2023 | 01-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 04-04-2023 | 05-04-2023 | [5 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER & COLLECTION OF FSS | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR 25-01-2023 | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV INSPECTION BOOKED FOR MONDAY 30-01-2023 - LOADING 1ST WEEK IN FEBRUARY | BV INSPECTION BOOKED FOR MONDAY 30-01-2023 - LOADING 1ST WEEK IN FEBRUARY | BV COMPLETED. ESTIMATED LOADING DATE 09/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 09/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 09/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 09/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 09/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. LOADING TODAY | LOADED - AWAITING POLICE ESCORT TO DISPATCH | VEHICLE CURRENTLY AT CAMPERDOWN WAITING POLICE ESCORTS | VEHICLE CURRENTLY AT CAMPERDOWN WAITING POLICE ESCORTS | VEHICLE CURRENTLY AT DALTON ENROUTE MUSINA | VEHICLE CURRENTLY AT GREYTOWN ENROUTE MUSINA | VEHICLE CURRENTLY AT WEENEN EN-ROUTE TO COLENSO | VEHICLE CURRENTLY AT LADYSMITH EN-ROUTE TO HARRISMITH | VEHICLE CURRENTLY AT VOLKSRUST ENROUTE MIDDELBURG | VEHICLE CURRENTLY AT ERMELO ENROUTE MIDDELBURG | VEHICLE CURRENTLY AT ERMELO WAITING FOR POLICE ESCORTS | VEHICLE CURRENTLY AT MIDDELBURG WAITING FOR POLICE ESCORTS | VEHICLE CURRENTLY AT ROEDTAN ENROUTE MUSINA | VEHICLE CURRENTLY AT ROEDTAN WAITING EXCORTS | VEHICLE CURRENTLY AT ROEDTAN WAITING ESCORTS | VEHICLE CURRENTLY AT ROEDTAN WAITING ESCORTS | VEHICLE CURRENTLY AT POLOKWANE WAITING ESCORTS | VEHICLE CURRENTKY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | VEHICLE CURRENTKY AT BUBI ENROUTE HARARE | VEHICLE CURRENTLY AT BEATRICE ENROUTE HARARE | VEHICLE CURRENTLY DISPATCHING BEATRICE ENROUTE HARARE | VEHCILE CURRNELTY AT KAROI ENROUTE CHIRUNDU | VEHCILE CURRNELTY AT CHIRUNDU ZIM SIDE, BRIDGE UNDER MAINTANCE AND TRUCKS CAN NOT CROSS AS YET. AWAITING ESTIMATED REPAIR TIME ON BRIDGE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING PERMIT AND RELEASE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING PERMIT | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING PERMIT - TO DISPATCH TODAY | VEHICLE CURRENLTY AT CHISAMBA ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT KITWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | VEHICLE CURRENLTY AT KANYAKA | ENROUTE SITE | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED AWAITING POD | OFFLOADED | OFFLOADED
BA2294 | 1 X CAT777-05B OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | 7W802626 | CAT00777E7W802626 | ZRK00581 | FML2209DSI1776 | COD 2023 112577 | KJ50ZLGP | YMB114GP / YMB118GP | ND63632 | REMOVAL FROM BONDED FACILITY | OFFLOADED | 23-01-2023 | 30-01-2023 | BV INSPECTION COMPLETE | 08/10/2022 | 07-03-2023 | 16-03-2023 | 16-03-2023 | 17-03-2023 | 18-03-2023 | 20-03-2023 | 22-03-2023 | 23-03-2023 | 22-03-2023 | 24-03-2023 | 27-03-2023 | 28-03-2023 | 29-03-2023 | 31-03-2023 | 01-04-2023 | 01-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 03-04-2023 | 05-04-2023 | [5 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER & COLLECTION OF FSS | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR 25-01-2023 | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV NUMBER RECEIVED - WAITING FIRE SUPPRESSION SYSTEM TO ARRANGE BV INSPECTION | BV INSPECTION BOOKED FOR MONDAY 30-01-2023 - LOADING 1ST WEEK IN FEBRUARY | BV INSPECTION BOOKED FOR MONDAY 30-01-2023 - LOADING 1ST WEEK IN FEBRUARY | BV COMPLETED. ESTIMATED LOADING DATE 16/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 16/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 16/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 16/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 16/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 15/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 21/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 21/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 21/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 21/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 21/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 27/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 27/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 27/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 27/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 27/02/2023 | BV COMPLETED. ESTIMATED LOADING DATE 02/03/2023 | BV COMPLETED. ESTIMATED LOADING DATE 02/03/2023 | BV COMPLETED. ESTIMATED LOADING DATE 02/03/2023 | LOADING TODAY | LOADED WAITING ABNORMAL PERMIT | LOADED WAITING ABNORMAL PERMIT | DURBAN WAITING POLICE ESCORTS | VEHICLE AT CAMPERDOWN WAITING POLICE ESCORTS | VEHICLE AT GREYTOWN WAITING POLICE ESCORTS | VEHICLE AT COLENSO WAITING POLICE ESCORTS | VEHICLE CURRENLTY AT VAN REENEN'S PASS ENROUTE JOHANNESBURG | VEHICLE CURRENLTY AT WARDEN ENROUTE JOHANNESBURG | VEHICLE CURRENLTY AT HEIDELBERG ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT POLOKWANE ENROUTE BEITBRIDGE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE | VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | VEHICLE CURRENTLY AT MAKUTI EN-ROUTE TO CHIRUNDU | VEHICLE CURRENTLY AT CHILANGA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT LUSAKA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KITWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | VEHICLE ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 05/04/2023 | OFFLOADED | OFFLOADED
BA2461 | 1 X CAT980-14A WHEEL LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | MK900730 | CAT00980VMK900730 | P4E05702 | FML2303DSI2013 | COD 2023 192707 PT01 | ND142761 | ND542263 | ND63856 | VESSEL: MORNING CAMILLA Voy. 141 - ETA DURBAN: 02-05-2023 | OFFLOADED 06-06-2023 | 08-05-2023 | 09-05-2023 | BV INSPECTION COMPLETED | 02.05.2023 | 10-05-2023 | MIDDELBURG 11-05-2023 | MIDDELBURG 11-05-2023 | 12-02-2023 | 13-05-2023 | 16-05-2023 | 16-05-2023 | 17-05-2023 | 19-05-2023 | 20-05-2023 | 20-05-2023 | 21-05-2023 | 21-05-2023 | 27-05-2023 | 27-05-2023 | 27-05-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 03-06-2023 | 06-06-2023 | [67 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | VESSEL CURRENLTY IN AND WORKING | VESSEL CURRENLTY IN AND WORKING | LOADING PLANNED FOR MONDAY 08-05-2023 | AWAITING BV NUMBER AND INSPECTION | BV TO BE DONE TODAY.TRUCK TO LOAD AND DISPATCH TOMMROW THE 10/05/2023 | BV INSPECTION COMPLETED - DISPATCHING DURBAN TODAY | DISPATCHED DURBAN - CURRENTLY AT LADYSMITH ENROUTE JOHANNESBURG | GROBLESDAL ENROUTE MUSINA | BEIT BRIDGE RSA SIDE | CHIVHU ENROUTE HARARE | HARARE | CHINYOI ENROUTE CHIRUNDU | CHIRUNDU ZAMBIAN SIDE CLEARING | VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT CHINGOLA IN QUEUE TO KASUMBALESA | VEHICLE CURRENLTY AT CHINGOLA IN QUEUE TO KASUMBALESA | VEHICLE CURRENLTY AT CHINGOLA IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING T1 AND RELEASE DAY 3 | VEHICLE AT WHISKEY AWAITING T1 AND RELEASE DAY 4 | VEHICLE AT WHISKEY AWAITING T1 AND RELEASE DAY 5 | DISPATCHING WHISKEY | TRUCK AT DANGELO EN-ROUTE TO SITE | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 06-06-2023 | OFFLOADED 06-06-2023
BA2457 | 1 X CAT 428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | LD01470 | CAT00428CL7D01470 | TBA | FML2303DSI2009 | COD 2023 197507 | BCD4142M | DRS624MP | 2303DSI2012 | VESSEL: BLUE MASTER II Voy. 231207 - ETA DURBAN: 18-05-2023 | OFFLOADED 19-06-2023 | 18-05-2023 | 22-05-2023 | BV INSPECTION COMPLETED | 18-05-2023 | 23-05-2023 | 29-05-2023 | 29-05-2023 | 29-05-2023 | GRB 29-05-2023 | GRB 30-05-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 02-06-2023 | 02-06-2023 | 08-06-2023 | 08-06-2023 | MOKAMBO 08-06-2023 | MOKAMBO 09-06-2023 | 09-06-2023 | 10-06-2023 | 10-06-2023 | 13-06-2023 | 14-06-2023 | 19-06-2023 | [67 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | VESSEL CURRENLTY IN AND WORKING | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 16-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 17-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 17-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 17-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | VESSEL IN AND WORKING - BV INSPECTION PLANNED FOR MONDAY 22-05-2023 | BV INSPECTION BOOKED FOR TODAY | VEHICLE LOADING TODAY PLANNING TO DISPATCH THIS AFTERNOON | VEHICLE AT MARIANHILLTOLL ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT JOHANNESBURG WAREHOUSE UNDERGOING FINAL TRIP CHECK | TRUCK DISPATCHING JOHANNESBURG EN-ROUTE TO GROBLERS BRIDGE BORDER | TRUCK DISPATCHING GROBLES BRIDGE EN-ROUTE TO KAZUNGULA BORDER | TRUCK AT KASANGULA BORDER CLEARING | TRUCK DISPATCHING KASANGULA BORDER EN-ROUTE TO LUSAKA | TRUCK AT NDOLA EN-ROUTE TO KASUMBALESA BORDER | TRUCK AT NDOLA IN THE QUEUE TO KASUMBALESA BORDER | DISPATCHING NDOLA FOR KASUMBALESA BORDER | NDOLA IN THE QUEUE TO KASUMBALESA | DISPATCHING NDOLA FOR KASUMBALESA | AT MOKAMBO BORDER CLEARING | AT CONNEX LUBUMBASHI WAITING RELEASE | AT LUBUMBASHI | LIKASI ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2023
BA2419 | 1 X CAT18-15A MOTOR GRADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | NN600220 | CAT00018HNN600220 | TXX04998 | FML2304DSI2020 | COD 2023 181140 | AGJ0085 | AGB2549 | ND63815 | VESSEL: CARNATION ACE Voy. 0083A - ETA DURBAN: 19-04-2023 | OFFLOADED 05-07-2023 | 21-04-2023 | 25-04-2023 | BV INSPECTION COMPLETED | 19-04-2023 | 15-05-2023 | 31-05-2023 | 03-06-2023 | 04-06-2023 | 04-06-2023 | 07-06-2023 | 08-06-2023 | 12-06-2023 | 19-06-2023 | 22-06-2023 | 22-06-2023 | 22-06-2023 | 23-06-2023 | 26-06-2023 | 30-06-2023 | 30-06-2023 | 30-06-2023 | 01-07-2023 | 01-07-2023 | 01-07-2023 | 05-07-2023 | [58 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-04-2023 LATE PM | VESSEL IN AND WORKING | UNIT TO BE COLLECTED FROM PORT - AWAITING BV NUMBER | UNIT AT OUR FACILITY - AWAITING VALIDATION OF BV NUMBER IN ORDER TO ARRANGE FOR THE BV INSPECTION | BV INSPECTION TO BE DONE TODAY - LOADING PLANNED FOR FRIDAY 28-04-2023 | BV INSPECTION TO BE DONE TODAY - LOADING PLANNED FOR FRIDAY 28-04-2023 | BV INSPECTION TO BE DONE TODAY - LOADING PLANNED FOR TODAY 28-04-2023 | BV INSPECTION TO BE DONE TODAY - LOADING PLANNED FOR THURSDAY 04-05-2023 | LOADING PLANNED FOR THURSDAY 04-05-2023 | LOADING PLANNED FOR FRIDAY 05-05-2023 | LOADING PLANNED FOR MONDAY 08-05-2023 | TRUCK DELAYED COMING SOUTH BOUND TO LOAD-ESTIMATED LOADING DATE 15-05-2023 | TRUCK DELAYED COMING SOUTH BOUND TO LOAD-ESTIMATED LOADING DATE 15-05-2023 | TRUCK DELAYED COMING SOUTH BOUND TO LOAD-ESTIMATED LOADING DATE 15-05-2023 | TRUCK DELAYED COMING SOUTH BOUND TO LOAD-ESTIMATED LOADING DATE 15-05-2023 | TRUCK DELAYED COMING SOUTH BOUND TO LOAD-ESTIMATED LOADING DATE 15-05-2023 | DISPATCHING DURBAN TODAY | PIETERMARITZBURG ENROUTE JOHANNESBURG | MOOIREVIER ENROUTE JOHANNESBURG | JOHANNESBURG IN WORKSHOP BUSY WITH MAINTANCE CHECK | JOHANNESBURG IN WORKSHOP BUSY WITH MAINTANCE CHECK | UNIT LOADED - PLANNING TO DISPATCH TUESDAY 23-05-2023 | UNIT LOADED - PLANNING TO DISPATCH WEDNESDAY 24-05-2023 | WAITING POLICE ESCORT IN ORDER TO DISPATCH | WAITING POLICE ESCORT IN ORDER TO DISPATCH | VEHICLE CURRENTLY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT PIETERMARITZBURG AWAITING METRO TO ESCORT US TO JOHANNESBURG | VEHICLE CURRENTLY AT PIETERMARITZBURG AWAITING METRO TO ESCORT US TO JOHANNESBURG | VEHICLE CURRENTLY AT HOWICK EN-ROUTE TO MIDDLEBURG | VEHICLE CURRENTLY AT VOLKSRUST EN-ROUTE TO MIDDLEBURG | VEHICLE CURRENTLY AT DOORNKOP EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE AT BEITBRIDGE BORDER RSA SIDE CLEARING | VEHICLE AT BEITBRIDGE BORDER RSA SIDE TO CROSS TO ZIM SIDE | VEHICLE AT BEITBRIDGE BORDER ZIM SIDE | VEHICLE AT MASVINGO ENROUTE HARARE | VEHICLE AT HARARE ENROUTE CHIRUNDU | VEHICLE AT HARARE TO DISPATCH TODAY | VEHICLE AT NYABIRA ENROUTE CHIRUNDU | VEHICLE AT CHINHYOI ON BREAKDOWN - WAITING FOR PARTS | VEHICLE AT CHINHYOI TO DISPATCH TODAY | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | VEHICLE CURRENTLY AT KABWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHILLABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT CONNEX AFRICA KOLWEZI WAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 05-07-2023 | OFFLOADED 05-07-2023
BA2457 | 1 X CAT 428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | LD01470 | CAT00428CL7D01470 | TBA | FML2303DSI2009 | COD 2023 197507 | BCD4142M | DRS624MP | 2303DSI2012 | VESSEL: BLUE MASTER II Voy. 231207 - ETA DURBAN: 18-05-2023 | OFFLOADED 19-06-2023 | 18-05-2023 | 22-05-2023 | BV INSPECTION COMPLETED | 18-05-2023 | 23-05-2023 | 29-05-2023 | 29-05-2023 | 29-05-2023 | GRB 29-05-2023 | GRB 30-05-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 02-06-2023 | 02-06-2023 | 08-06-2023 | 08-06-2023 | MOKAMBO 08-06-2023 | MOKAMBO 09-06-2023 | 09-06-2023 | 10-06-2023 | 10-06-2023 | 13-06-2023 | 14-06-2023 | 19-06-2023 | [67 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-05-2023 | VESSEL CURRENLTY IN AND WORKING | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 16-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 17-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 17-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 17-05-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA 18-05-2023 | VESSEL IN AND WORKING - BV INSPECTION PLANNED FOR MONDAY 22-05-2023 | BV INSPECTION BOOKED FOR TODAY | VEHICLE LOADING TODAY PLANNING TO DISPATCH THIS AFTERNOON | VEHICLE AT MARIANHILLTOLL ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT JOHANNESBURG WAREHOUSE UNDERGOING FINAL TRIP CHECK | TRUCK DISPATCHING JOHANNESBURG EN-ROUTE TO GROBLERS BRIDGE BORDER | TRUCK DISPATCHING GROBLES BRIDGE EN-ROUTE TO KAZUNGULA BORDER | TRUCK AT KASANGULA BORDER CLEARING | TRUCK DISPATCHING KASANGULA BORDER EN-ROUTE TO LUSAKA | TRUCK AT NDOLA EN-ROUTE TO KASUMBALESA BORDER | TRUCK AT NDOLA IN THE QUEUE TO KASUMBALESA BORDER | DISPATCHING NDOLA FOR KASUMBALESA BORDER | NDOLA IN THE QUEUE TO KASUMBALESA | DISPATCHING NDOLA FOR KASUMBALESA | AT MOKAMBO BORDER CLEARING | AT CONNEX LUBUMBASHI WAITING RELEASE | AT LUBUMBASHI | LIKASI ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023 | OFFLOADED 19-06-2023
BA2472 | 1 X CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | JZ200182 | CAT00426EJZ200182 | CC207110 | FML2305DSI2053 | COD 2023 201647 | ACJ1507 | BK04NGGP | 2305DSI2053 | VESSEL: MSC VANESSA Voy. IA319R - ETA DURBAN: 25-05-2023 | OFFLOADED 28-07-2023 | 08-06-2023 | 12-06-2023 | BV COMPLETED | 02-06-2023 | 15-06-2023 | 16-06-2023 | 20-06-2023 | 22-06-2023 | 23-06-2023 | 24-06-2023 | 25-06-2023 | 25-06-2023 | 26-06-2023 | 26-06-2023 | 30-06-2023 | 05-07-2023 | 05-07-2023 | 06-07-2023 | 10-07-2023 | 11-07-2023 | 14-07-2023 | 15-07-2023 | 25-07-2023 | 26-07-2023 | 28-07-2023 | [80 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-05-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-05-2023 | VESSEL IS IN AND WORKING, AWAITING CONTAINER TO DISCHARGE IN ORDER TO COLLECT FROM PORT | VESSEL IS IN AND WORKING, AWAITING CONTAINER TO DISCHARGE IN ORDER TO COLLECT FROM PORT | VESSEL IS IN AND WORKING, AWAITING CONTAINER TO DISCHARGE IN ORDER TO COLLECT FROM PORT | VESSEL IS IN AND WORKING, AWAITING CONTAINER TO DISCHARGE IN ORDER TO COLLECT FROM PORT | UNIT IS AT OUR FACILITY AWAITING UNPACK | UNIT IS AT OUR FACILITY AWAITING BV NUMBER | UNIT IS AT OUR FACILITY AWAITING BV NUMBER | UNIT IS AT OUR FACILITY AWAITING BV NUMBER | UNIT IS AT OUR FACILITY AWAITING BV NUMBER | UNIT IS AT OUR FACILITY - BV INSPECTION BOOKED FOR TUESDAY 13-06-2023 | UNIT IS AT OUR FACILITY - BV INSPECTION BOOKED FOR TUESDAY 13-06-2023 | UNIT IS AT OUR FACILITY - BV INSPECTION BOOKED FOR TUESDAY 13-06-2023 | UNIT IS AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR NEXT WEEK MONDAY | LOADING TODAY FROM BONDED FACILITY | VEHICLE CURRENLTY AT JOHANNESBURG ENROUTE GROBLERSBRIDGE | VEHICLE DISPATCHING JOHANNESBURG ENROUTE POLOKWANE | VEHICLE CURRENTLY AT BELA-BELA ENROUTE GROBLERSBIDGE | VEHICLE CURRENLTY AT GROBLERSBRIDGE AWAITING CLEARANCE | VEHICLE CURRENLTY AT GROBLERSBRIDGE AWAITING CLEARANCE | VEHICLE CURRENLTY AT VIC FALLS EN-ROUTE TO LUSAKA | VEHICLE DISPATCHING AT VIC FALLS TO POCEED TO LUSAKA | VEHICLE DISPATCHING AT VIC FALLS TO POCEED TO LUSAKA-TRUCK HAD MINOR DELAY | VEHICLE DISPATCHED VIC FALLS EN-ROUTE TO CHIRUNDU | VEHICLE AT CHOMA EN-ROUTE TO LUSAKA | VEHICLE AT NDOLA | VEHICLE DISPATCHED NDOLA FOR KASUMBALESA | VEHICLE ONLY DISPATCHING NDOLA TODAY | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA CLEARING | VEHICLE AT KASUMBALESA UNDER CLEARANCE | VEHICLE AT KASUMBALESA UNDER CLEARANCE | VEHICLE CURRENTLY AT WHISKEY - AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY - UNDER CLEARANCE | VEHICLE CURRENTLY AT WHISKEY - UNDER CLEARANCE AND WAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 3 - PLEASE ASSIST | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 4 - PLEASE ASSIST | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 - PLEASE ASSIST | VEHICLE CURRENTLY AT CE AWAITING TO OFFLOAD BA2473 | VEHICLE CURRENTLY AT CE AWAITING TO OFFLOAD BA2473 | VEHICLE CURRENTLY AT KOLWEZI PARKING PAYING PARKING FEE BEFORE PROCEEDING TO SITE FOR OFFLOADING | VEHICLE CURRENTLY AT KCC SITE AWAITING TO BE OFFLOADED | VEHICLE CURRENTLY AT KCC SITE AWAITING TO BE OFFLOADED | OFFLOADED 28-07-2023
BA2476 | 1 X CAT 980-14A WHEEL LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | MK900752 | CAT00980CMK900752 | TBA | FML2305DSI2063 | COD 2023 192707 | ND919955 | ND140841 | 2305DSI2063 | VESSEL: GUANGZHOU HIGHWAY V. 172 - ETA DURBAN: 03-07-2023 | OFFLOADED 28-07-2023 | 08-05-2023 | 07-07-2023 | BV NUMBER RECEIVED | 03-07-2023 | 11-07-2023 | 12-07-2023 | 12-07-2023 | 13-07-2023 | 13-07-2023 | 18-07-2023 | 19-07-2023 | 19-07-2023 | 19-07-2023 | 21-07-2023 | 24-07-2023 | 24-07-2023 | 25-07-2023 | 25-07-2023(MOKAMBO) |  | 26-07-2023 | 27-07-2023 | 27-07-2023 | 27-07-2023 | 28-07-2023 | 28-07-2023 | [107 empty] | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 03-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | LOADING FROM PORT TODAY | LOADED FROM PORT - WAITING PERMIT - BV INSPECTION BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO DISPATCH 11-07-2023 | VEHICLE CURRENTLY AT VOLKSRUST ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAITING CLEARANCE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE | VEHICLE DISPATCH BEITBRIDGE ENROUTE HARARE | VEHICLE AT CHIRUNDU BORDER CLEARING | VEHICLE AT CHIRUNDU BORDER ZAM SIDE CLEARING | VEHICLE AT MUFULIRA ZAMBIA EN-ROUTE TO MOKAMBO BORDER | VEHICLE AT MOKAMBO BORDER CLEARING | VEHICLE AT MOKAMBO BORDER CLEARING | VEHICLE AT KOMBOVE EN-ROUTE TO KOLWEZI | VEHICLE AT MUTSHATASHA KOLWEZI | OFFLOADED 28-07-2023
BA2477 | 1 X CAT 980-14A WHEEL LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | MK900761 | CAT00980VMK900761 | TBA | FML2305DSI2078 | COD 2023 192707 | ND919945 | ND133379 | 2305DSI2078 | VESSEL: GUANGZHOU HIGHWAY V. 172 - ETA DURBAN: 03-07-2023 | OFFLOADED 28-07-2023 | 08-05-2023 | 07-07-2023 | BV NUMBER RECEIVED | 03-07-2023 | 11-07-2023 | 11-07-2023 | 12-07-2023 | 13-07-2023 | 14-07-2023 | 18-07-2023 | 19-07-2023 | 19-07-2023 | 19-07-2023 | 21-07-2023 | 24-07-2023 | 24-07-2023 | 25-07-2023 | 25-07-2023(MOKAMBO) |  | 26-07-2023 | 27-07-2023 | 27-07-2023 | 27-07-2023 | 28-07-2023 | 28-07-2023 | [107 empty] | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 03-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | AWAITING VESSEL ARRIVAL - CURRENT ETA DURBAN 04-07-2023 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | LOADING FROM PORT TODAY | LOADED FROM PORT - WAITING PERMIT - BV INSPECTION BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO DISPATCH 11-07-2023 | VEHICLE DISPATCHED DURBAN ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT VOLKSRUST ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT LEEUFONTEIN ENROUTE BEITBRIDGE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE | VEHICLE DISPATCH BEITBRIDGE ENROUTE HARARE | VEHICLE AT CHIRUNDU BORDER CLEARING | VEHICLE AT CHIRUNDU BORDER ZAM SIDE CLEARING | VEHICLE AT MUFULIRA ZAMBIA EN-ROUTE TO MOKAMBO BORDER | VEHICLE AT MOKAMBO BORDER CLEARING | VEHICLE AT MOKAMBO BORDER CLEARING | VEHICLE AT KOMBOVE EN-ROUTE TO KOLWEZI | VEHICLE AT MUTSHATASHA KOLWEZI | OFFLOADED 28-07-2023
BA2430 | 1 X CAT D10T2 TRACK TYPE TRACTOR - MAIN UNIT | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01318 | CAT0D10TLRAB01318 | JZM01334 | FML2301DSI1899 | COD 2023 234217 PT01 | ND754967 | ND654346 | ND63991 | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 25-01-2023 | OFFLOADED 23-08-2023 | 05-07-2023 | 21-07-2023 | BV INSPECTION COMPLETED | 26.01.2023 | 27-07-2023 | MIDDELBURG 01-08-2023 | MIDDELBURG 01-08-2023 | 02-08-2023 | 02-08-2023 | 04-08-2023 | 05-08-2023 | 07-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 11-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 13-08-2023 | 14-08-2023 | 17-08-2023 | 17-08-2023 | 18-08-2023 | 23-08-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING FROM PORT TODAY - AWAITING BV NUMBER - LOADING DATE TO BE CONFIRMED | COLLECTING FROM PORT TODAY - AWAITING BV NUMBER - LOADING DATE TO BE CONFIRMED | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR MONDAY 10-07-2023 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR MONDAY 10-07-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION TO BE DONE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION BOOKED FOR TOMORROW - 21-07-2023 - PLANNING TO LOAD AND DISPATCH 25-07-2023 | BV INSPECTION BOOKED FOR TODAY - 21-07-2023 - PLANNING TO LOAD AND DISPATCH 25-07-2023 | BV INSPECTION DONE & TRUCK TO LOAD TOMMROW THE 25-07-2023 | TRUCK LOADED AWAITING PERMIT TO DISPATCH | TRUCK LOADED AWAITING PERMIT TO DISPATCH | TRUCK AT MARIAN HILL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT NEW CASTLE EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT VOLKSRUST EN-ROUTE TO BEITBRIDGE BORDER | TRUCK DISPATCHING VOLKSRUST THIS MORNING | TRUCK AT ROEDTAN ENROUTE BEIT BRIDGE BORDER | TRUCK AT BEIT BRIDGE BORDER | TRUCK AT BEIT BRIDGE BORDER RSA SIDE TO CROSS TO ZIM SIDE | VEHICLE DISPATCHING HARARE ENROUTE CHIRUNDU | VEHICLE CURRENLTY AT KAROI ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM - DISPATCHING FOR LUSAKA | VEHICLE CURRENTLY AT KABWE ENROUTE KITWE | VEHICLE CURRENTLY AT GOMES EN-ROUTE TO KCC SITE | VEHICLE CURRENTLY AT GOMES AWAITING RELEASE TO PROCEED TO SITE | VEHICLE CURRENTLY AT GOMES AWAITING RELEASE TO PROCEED TO SITE | VEHICLE CURRENTLY AT LIKASI EN-ROUTE TO SITE | VEHICLE CURRENTLY AT KCC AWAITING TO OFFLOAD | VEHICLE CURRENTLY AT KCC AWAITING TO OFFLOAD - DAY 4 PLEASE ASSIST | KOLWEZI HOLDING YARD WAITING RELEASE | ON SITE, WAITING FINAL CLEARANCE AND OFFLOADING | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2430 | 1 X CAT D10T2 TRACK TYPE TRACTOR - ACCESSORIES | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | RAB01318 | CAT0D10TLRAB01318 | JZM01334 | FML2301DSI1899 | COD 2023 234217 PT02 | LH12MYGP | YSN849GP / YSN855GP | 2301DSI1899A | VESSEL: SWAN ACE Voy. 0119A - ETA DURBAN: 25-01-2023 | OFFLOADED | 05-07-2023 | 03-08-2023 | BV INSPECTION COMPLETED | 26.01.2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 11-08-2023 | 14-08-2023 | 16-08-2023 | 17-08-2023 | 18-08-2023 | 18-08-2023 | 19-08-2023 | 19-08-2023 | 19-08-2023 | 20-08-2023 | 20-08-2023 | 05-09-2023 | 06-09-2023 | 07-08-2023 | 07-08-2023 | 07-08-2023 | 10-09-2023 | 12-09-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 24-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 25-01-2023 | VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING FROM PORT TODAY - AWAITING BV NUMBER - LOADING DATE TO BE CONFIRMED | COLLECTING FROM PORT TODAY - AWAITING BV NUMBER - LOADING DATE TO BE CONFIRMED | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE FSS AND BV IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING TRUCK TO RETURN FROM DRC.ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | ESTIMATED LOADING DATE TBC ONCE BV NUMBER IS READY | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER AND PO | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR MONDAY 10-07-2023 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR MONDAY 10-07-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION TO BE DONE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION TO BE DONE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION TO BE DONE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION TO BE DONE - ESTIMATED LOADING DATE TO BE ADVISE / ONGOING INVESTIGATION REGARDING FSS | BV INSPECTION TO BE DONE - NEW FIRE SUPPRESION SYSTEM ORDERED LEAD TIME 10 DAYS- MAIN UNIT AND SPARES TO ARRIVE ON SITE AT THE SAME TIME FOR ASSEMBLY | BV INSPECTION TO BE DONE - NEW FIRE SUPPRESION SYSTEM ORDERED LEAD TIME 10 DAYS- MAIN UNIT AND SPARES TO ARRIVE ON SITE AT THE SAME TIME FOR ASSEMBLY | BV TO BE DONE ON MONDAY THE 31/07/2023, LOADING THE 02/08/2023 | BV TO BE DONE ON MONDAY THE 31/07/2023, LOADING THE 02/08/2023 | BV TO BE DONE ON MONDAY THE 31/07/2023, LOADING THE 02/08/2023 | BV TO BE DONE ON TOMORROW 02/08/2023, LOADING THE 03/08/2023 | BV TO BE DONE - AWAITING BV DRC TO RE-OPEN THE LICENSE | BV INSPECTION TO BE DONE TODAY - LOADING TOMORROW | BV INSPECITON COMPLETED - LOADING TODAY | LOADED - TO DISPATCH DURBAN THIS MORNING | VEHICLE CURRENTLY AT JOHANNESBURG WORKSHOP UNDERGOING FINAL TRIP CHECK | VEHICLE DISPATCHING JOHANNESBURG THIS MORNING - ENROUTE BEITBRIDGE | VEHICLE CURRENTLY AT MONTSOLE ENROUTE BEITBRIDGE | VEHICLE CURRENTLY AT BEITBRIDGE BORDER CLEARING | VEHICLE CURRENTLY AT BEITBRIDGE BORDER CLEARING | VEHICLE CURRENTLY DISPATCHING BEITBRIDGE BORDER EN-ROUTE TO CHIRUNDU | VEHICLE CURRENTLY AT HARARE EN ROUTE TO CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU CLEARING | VEHICLE CURRENTLY AT SAKANIA ZAMSIDE CLEARING | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - WAITING RELEASE | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - WAITING RELEASE | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - WAITING RELEASE | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - WAITING RELEASE - DAY 8 | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - WAITING RELEASE - DAY 9 | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - WAITING RELEASE - DAY 10 | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - WAITING RELEASE - DAY 11 | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - WAITING RELEASE - DAY 12 | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - WAITING RELEASE - DAY 15 | VEHICLE CURRENTLY ENROUTE WHISKEY | VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE | VEHICLE CURRENTLY AT WHISKEY - WAITING DOCUMENTS IN ORDER TO DISPATCH | VEHICLE AT TENKE ENROUTE KOLWEZI | VEHICLE AT KCC AWAITING TO OFFLOAD | VEHICLE AT KCC AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2276 & BA2276A | 1 X CAT992-12A WHEEL LOADER IN CKD - MAIN UNIT | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | AP700445 | CAT00922VAP70045 | XTG00152 | FML2308DSI2196 | COD 2023 288588 | ND737412 | ND647660 / ND647016 | 2308DSI2196-1 | VESSEL: GRACIOUS ACE Voy. 0088A - ETA DURBAN 16-09-2023 | OFFLOADED 10-10-2023 | 12-09-2023 | 20-09-2023 | BV COMPLETED | 15-09-2023 | 20-09-2023 | MIDDELBURG 26-09-2023 | MIDDELBURG 26-09-2023 | 26-09-2023 | 26-09-2023 | 28-09-2023 | 01-10-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 04-10-2023 | 04-10-2023 | 05-10-2023 | MOKAMBO 05-10-2023 | MOKAMBO 06-10-2023 | 07-10-2023 | 08-10-2023 | 08-10-2023 | 08-10-2023 | 09-10-2023 | 10-10-2023 | [155 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CARGO | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TOMORROW | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TODAY | LADYSMITH ENROUTE MUSINA | VOLKSRUST ENROUTE MUSINA | MIDDELBURG ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | SEKE ENROUTE HARARE | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHILANGA ENROUTE MOKAMBO BORDER | NDOLA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAM SIDE CLEARING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2276 & BA2276A | 1 X CAT992-12A WHEEL LOADER IN CKD - 4 X TIRE/RIMS, 1 X BUCKET | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | AP700445 | CAT00922VAP70045 | XTG00152 | FML2308DSI2196 | COD 2023 288588 | ND407254 | ND671055 | 2308DSI2196-2 | VESSEL: GRACIOUS ACE Voy. 0088A - ETA DURBAN 16-09-2023 | OFFLOADED 10-10-2023 | 12-09-2023 | 20-09-2023 | BV COMPLETED | 15-09-2023 | 20-09-2023 | MIDDELBURG 26-09-2023 | MIDDELBURG 26-09-2023 | 26-09-2023 | 26-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 04-10-2023 | 04-10-2023 | 05-10-2023 | MOKAMBO 05-10-2023 | MOKAMBO 06-10-2023 | 07-10-2023 | 08-10-2023 | 08-10-2023 | 08-10-2023 | 09-10-2023 | 10-10-2023 | [155 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CARGO | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TOMORROW | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TODAT | LADYSMITH ENROUTE MUSINA | VOLKSRUST ENROUTE MUSINA | MIDDELBURG ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | HARARE ENROUTE CHIRUDNU | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | LUSAKA ENROUTE MOKAMBO BORDER | NDOLA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAM SIDE CLEARING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2276 & BA2276A | 1 X CAT992-12A WHEEL LOADER IN CKD - CAB, CANOPY, HANDRAILS, PARTS, LIFT ARM | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | AP700445 | CAT00922VAP70045 | XTG00152 | FML2308DSI2196 | COD 2023 288588 | FZ72CXGP | HTR310MP / LH12NSGP | 2308DSI2196-3 | VESSEL: GRACIOUS ACE Voy. 0088A - ETA DURBAN 16-09-2023 | OFFLOADED 10-10-2023 | 12-09-2023 | 20-09-2023 | BV COMPLETED | 15-09-2023 | 21-09-2023 | 21-09-2023 | 22-09-2023 | 22-09-2023 | 22-09-2023 | 23-09-2023 | 25-09-2023 | 26-09-2023 | 27-09-2023 | 27-09-2023 | 28-09-2023 | 29-09-2023 | 29-09-2023 | MOKAMBO 02-10-2023 | MOKAMBO 04-10-2023 | 04-10-2023 | 06-10-2023 | 06-10-2023 | 07-10-2023 | 08-10-2023 | 10-10-2023 | [155 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CARGO | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TODAY | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TODAY | DISPATCHING DURBAN TODAY | JOHANNESBURG | HARARE ENROUTE CHIRUNDU | DISPATCHING FROM HARARE THIS MORNING | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZIM SIDE CLEARING | MOKAMBO BORDER | TRUCK AT MOKAMBO CLEARING | TRUCK AT MOKAMBO ZAMBIAN SIDE CLEARING | TRUCK AT WHISKEY AWAITING RELEASE | TRUCK AT KANYAKA | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2276 & BA2276A | 1 X CAT992-12A WHEEL LOADER IN CKD - CYLINDERS, FRONT AXLE, REAR AXLE, WHEEL BOLTS, STAIRWAY, ROAD FENDER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | AP700445 | CAT00922VAP70045 | XTG00152 | FML2308DSI2196 | COD 2023 288588 | BAD7416 | AKB2576T | 2308DSI2196-4 | VESSEL: GRACIOUS ACE Voy. 0088A - ETA DURBAN 16-09-2023 | OFFLOADED 10-10-2023 | 12-09-2023 | 20-09-2023 | BV COMPLETED | 15-09-2023 | 21-09-2023 | 21-09-2023 | 22-09-2023 | 22-09-2023 | 22-09-2023 | 23-09-2023 | 24-09-2023 | 24-09-2023 | 25-09-2023 | 26-09-2023 | 27-09-2023 | 28-09-2023 | 02-10-2023 | 03-10-2023 | 03-10-2023 | 03-10-2023 | 04-10-2023 | 05-10-2023 | 05-10-2023 | 06-10-2023 | 10-10-2023 | [155 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CARGO | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TODAY | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TODAY | DISPATCHING DURBAN TODAY | JOHANNESBURG | VIC FALLS CLEARING | KAFUE ENROUTE LUSAKA | LUSAKA ENROUTE KASUMBALESA | DISPATCHING LUSAKA FOR KASUMBALESA | NDOLA | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT WHISKEY DUE TO DISPATCH | TRUCK AT KANYALA | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2126 | 1 X CAT18 MOTOR GRADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | NN600251 | CAT00018HNN600251 | TXX05283 | FML2304DSI2029 | COD 2023 181140 | LG14TMGP | LG13YZGP | ND64526 | VESSEL: GRACIOUS ACE Voy. 0088A - ETA DURBAN 16-09-2023 | OFFLOADED 11-10-2023 | 21-04-2023 | 19-09-2023 | BV COMPLETED | 15-09-2023 | 20-09-2023 | 21-09-2023 | 22-09-2023 | 22-09-2023 | 23-09-2023 | 26-09-2023 | 27-09-2023 | 27-09-2023 | 28-09-2023 | 02-10-2023 | 03-10-2023 | 03-10-2023 | 03-10-2023 | 04-10-2023 | 05-10-2023 | 05-10-2023 | 07-10-2023 | 07-10-2023 | 08-10-2023 | 09-10-2023 | 11-10-2023 | [154 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 16-09-2023 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CARGO | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - DISPATCHING DURBAN | JOHANNESBURG TO DISPATCH FOR MUSINA | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | MASVINGO ENROUTE HARARE | CHINHOY ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KABWE EN-ROUTE TO KASUMBALESA | CHILILIBOMWE ENROUTE KASUMBULESA | KASUMBULESA ZAM SIDE CLEARING | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 - PLEASE ASSIST | OFFLOADED 11-10-2023
BA2604 | 1 X CAT980-14A WHEEL LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY SARL | MK900812 | CAT00980AMK900812 |  | FML2308DSI2193 | COD 2023 297917 | ND919945 | ND133379 | 132226 | VESSEL: GUANGZHOU HIGHWAY Voy. 173 - ETA DURBAN: 29-09-2023 | OFFLOADED | 21-09-2023 | 05-10-2023 | BV NUMBER RECEIVED | 29-09-2023 | 06-10-2023 | MIDDELBURG 09-10-2023 | MIDDELBURG 10-10-2023 | 10-10-2023 | 11-10-2023 | 12-10-2023 | 12-10-2023 | 14-10-2023 | 16-10-2023 | 16-10-2023 | 16-10-2023 | 17-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN TO BE CONFIRMED | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-09-2023 | VESSEL ARRIVED AND CURRENTLY WORKING | LOADED FROM PORT - BV INSPECTION TO BE DONE WEDNESDAY 04-10-2023 | LOADED FROM PORT - BV INSPECTION TO BE DONE WEDNESDAY 04-10-2023 | LOADED FROM PORT - BV INSPECTION TO BE DONE FRIDAY 06-10-2023 | LOADED FROM PORT - BV INSPECTION BOOKED FOR TODAY 05-10-2023 | BV INSPECTION COMPLETED - DISPATCHED DURBAN, CURRENTLY AT PIETERMARITZBURG AWAITING ESCORT | LADYSMITH ENROUTE BEIT BRIDGE BORDER | MIDDELBURG ENROUTE BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | HARARE ENROUTE CHIRUNDU | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIMOMBA ENROUTE KITWE | VEHICLE CURRENTLY AT KITWE ENROUTE LUBUMBASHI | VEHCILE CURRENTLY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | OFFLOADED
BA2410 | 1 X CAT336GC-07C HYDRAULIC EXCAVATOR | KAMOTO COPPER COMPANY | JFW22274 | CAT00336KJFW22274 | E7A56816 | FML2212DSI1862 | COD 2023 331712 PT02 | ND730794 | ND443606 | ND61126 | VESSEL: RCC AFRICA Voy. 020 - ETA DURBAN: 16-01-2023 | OFFLOADED 12-12-2023 | 17-11-2023 | 21-11-2023 | BV NUMBER RECEIVED | 16-01-2023 | 24-11-2023 | MIDDELBURG 24-11-2023 | MIDDELBURG 27-11-2023 | 28-11-2023 | 28-11-2023 | 29-11-2023 | 30-11-2023 | 02-12-202 | 02-12-2023 | 04-12-2023 | 04-12-2023 | 05-12-2023 | 05-12-2023 | 05-12-2023 | 07-12-2023 | 07-12-2023 | 09-10-2023 | 10-12-2023 | 10-12-2023 | 11-12-2023 | 12-12-2023 | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 21-11-2023 | BV INSPECTION TO BE DONE TODAY - LOADING FRIDAY 24-11-2023 | BV INSPECTION COMPLETE - LOADING FRIDAY 24-11-2023 | BV INSPECTION COMPLETE - LOADING FRIDAY 24-11-2023 | LOADED - DISPATCHING DURBAN TODAY | MIDDELBURG AWAITING PERMITS | MARBLE HALL ENROUTE BEIT BRIDGE | BEIT BRIDGE ZIM SIDE WAITING RELEASE | MVUMA ENROUTE HARARE | HARARE | CHIRUNDU ZAMBIAN SIDE CLEARING | KABWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | ON SITE WAITING FINAL CLEARANCE AND OFFLOADING | ON SITE WAITING FINAL CLEARANCE AND OFFLOADING | OFFLOADED 12-12-2023 | OFFLOADED 12-12-2023
BA2409 | 1 X CAT336GC-07C HYDRAULIC EXCAVATOR | KAMOTO COPPER COMPANY | JFW22275 | CAT00336JJFW22275 | E7A56848 | FML2212DSI1870 | COD 2023 331712 PT01 | ND706468 | ND476150 | ND61125 | VESSEL: DALIAN HIGHWAY Voy. 97 - ETA DURBAN: 29-01-2023 | OFFLOADED 15 DECEMBER 2023 | 17-11-2023 | 21-11-2023 | BV NUMBER RECEIVED | 29-01-2023 | 27-11-2023 | MIDDELBURG 27-11-2023 | MIDDELBURG 29-11-2023 | 29-11-2023 | 30-11-2023 | 01-12-2023 | 02-12-2023 | 04-12-2023 | 05-12-2023 | 07-12-2023 | 07-12-2023 | 08-12-2023 | 08-12-2023 | 08-12-2023 | 10-12-2023 | 10-12-2023 | 12-12-2023 | 12-12-2023 | 13-12-2023 | 14-12-2023 | 15-12-2023 | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 21-11-2023 | BV INSPECTION TO BE DONE TODAY - LOADING FRIDAY 24-11-2023 | BV INSPECTION COMPLETE - LOADING FRIDAY 24-11-2023 | BV INSPECTION COMPLETE - LOADING FRIDAY 24-11-2023 | VEHICLE IN WORKSHOP DOING MAINTANANACE CHECKS BEFORE LOADING | VEHICLE AT PIETERMARITZBURG ENROUTE JOHANNESBURG | VEHICLE AT MIDDELBURG ENROUTE BEIT BRIDGE | VEHICLE AT MIDDELBURG AWAITING PERMIT | VEHICLE AT MUSINA TO PROCEED TO BEIT BRIDGE | VEHICLE AT BUBI ENROUTE HARARE | HARARE | CHINHOYI ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHISAMBA ENROUTE KASUMBALESA | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | DISPATCHED WISKEY ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 15 DECEMBER 2023
BA2579 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - CHASSIS | KAMOTO COPPER COMPANY | FDB02207 | CAT0793DKFDB02207 | EXM00246 | FML2310DSI2242 | COD 2023 339169 | ND750229 | ND710695 | 2310DSI2242-1 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 12-12-2023 | 14-12-2023 | 16-12-2023 | 18-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | UNIT LOADED FROM PORT YESTERDAY - AWAITING PERMIT AND POLICE ESCORT | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | MOOI RIVER ENROUTE BEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | BEIT BRIDGE ZIM SIDE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | DISPATCHING CHIRUNDU ZAM THIS MORNING | KABWE ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2579 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - BOX INTAKE, AIR CLEANER, SKID BANJO | KAMOTO COPPER COMPANY | FDB02207 | CAT0793DKFDB02207 | EXM00246 | FML2310DSI2242 | COD 2023 339169 | ND407254 | ND64742 | 2310DSI2242-2 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 11-12-2023 | 14-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VOLKSRUST ENROUTE BEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | BEIT BRIDGE ZIM SIDE | CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHISAMBA ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2579 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID CAB, SKID OUTRIGGERS, SKID RIMS, SKID RIMS, SKID RIM TOPY, SKID FSTRUT, BOX HARDWARE, BOX BODY, BOX PIPING | KAMOTO COPPER COMPANY | FDB02207 | CAT0793DKFDB02207 | EXM00246 | FML2310DSI2242 | COD 2023 339169 | HN26CPGP | DD83NLGP / DD83NPGP | 2310DSI2242-3 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 12-12-2023 | 14-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 18-12-2023 | 20-12-2023 | MOKAMBO 20-12-2023 | MOKAMBO 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VILLIERS ENROUTE JOHANNESBURG | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE HARARE | MVUMA ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | HARARE ENROUTE CHIRUNDU | DISPATCHING KABWE FOR MOKAMBO BORDER | KAFULAFUTA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | TRUCK IS AT KANYAKHA EN-ROUTE TO KCC SITE | ON SITE AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2579 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID FSTRUT, SKID PH PLATFORM, SKID FUEL TANK, SKID HANDRAILS, SKID RIM TROPHY | KAMOTO COPPER COMPANY | FDB02207 | CAT0793DKFDB02207 | EXM00246 | FML2310DSI2242 | COD 2023 339169 | JZ76ZKGP | XSW614GP / XSW590GP | 2310DSI2242-4 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 12-12-2023 | 15-12-2023 | 17-12-2023 | 19-12-2023 | 20-12-2023 | 21-12-2023 | 21-12-2023 | 23-12-2023 | MOKAMBO 23-12-2023 | MOKAMBO 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | HEIDELBERG ENROUTE JOHANNESBURG | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE HARARE | CHIVHU ENROUTE HARARE | CHIVHU ENROUTE HARARE | CHIVHU ENROUTE HARARE | VEHICLE TO DISPATCH VUTI TODAY | CHIRUNDU ZAM SIDE CLEARING | KAFUE ENROUTE MOKAMBO BORDER | KAFULAFUTA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | TRUCK IS AT KANYAKHA EN-ROUTE TO KCC SITE | ON SITE AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2579, BA2580, BA2581, BA2582, BA2583, BA2584, BA2585, BA2586 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - FILM & HOSES, CYLINDERS, FUEL TANK, FIRE SUPPRESSION SYSTEMS | KAMOTO COPPER COMPANY | FDB02207 FDB02208 FDB02209 FDB02210 FDB02211 FDB02212 FDB02213 FDB02214 | CAT0793DKFDB02207 CAT0793DJFDB02208 CAT0793DCFDB02209 CAT0793DKFDB02210 CAT0793DJFDB02211 CAT0793DCFDB02212 CAT0793DVFDB02213 CAT0793DAFDB02214 | EXM00246 EXM00243 | FML2310DSI2242 | COD 2023 339169 | KC83WRGP | BG75PHGP / BG75PJGP | 2310DSI2242-5 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 08-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 11-12-2023 | 12-12-2023 | 14-12-2023 | 15-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 19-12-2023 | 19-12-2023 | 21-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | MOKAMBO 22-12-2023 | MOKAMBO 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | LOADING FROM WAREHOUSE TODAY | LOADED TO DISPATCH TO BV SITE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY | CATO RIGDGE ENROUTE JOHANNESBURG | ESTCOURT ENROUTE JOHANNESBURG | JOHANNESBURG - IN WORKSHOP BUSY WITH TRIP CHECK BEFORE VEHICLE DISPATCH FOR BEIT BRIDGE | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE | VEHICLE CURRENTLY AT NYABIRA ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | DISPATCHED FROM CHIRUNDU ENROUTE MOKAMBO BORDER | MUBANGA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | TRUCK IS AT KANYAKHA EN-ROUTE TO KCC SITE | ON SITE AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2580 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - CHASSIS | KAMOTO COPPER COMPANY | FDB02208 | CAT0793DJFDB02208 | EXM00243 | FML2310DSI2251 | COD 2023 339169 | ND754713 | ND715801 / ND718488 | 2310DSI2251-1 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 12-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | UNIT LOADED FROM PORT YESTERDAY - AWAITING PERMIT AND POLICE ESCORT | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TODAY TOMORROW | MOOI RIVER ENROUTEBEIT BRIDGE BORDER | MIDDELBURG ENROUTE BEIT BRIDGE | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | DISPATCHING CHIRUNDU ZAM THIS MORNING | CHIBOMBO ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2580 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - BOX INTAKE, AIR CLEANER, SKID BANJO | KAMOTO COPPER COMPANY | FDB02208 | CAT0793DJFDB02208 | EXM00243 | FML2310DSI2251 | COD 2023 339169 | ND57281 | CD55YJGP | 2310DSI2251-2 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 11-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2026 | 27-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | BANJO LOADED - WAITING TO LOAD BALANCE OF CARGO - DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VOLKSRUST ENROUTE BEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | MUSINA/BEIT BRIDGE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | BEIT BRIDGE ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | DISPATCHED FROM CHIRUNDU ENROUTE MOKAMBO BORDER | KAPIRI MPHOSHI ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2580 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID CAB, SKID OUTRIGGERS, SKID RIMS, SKID RIMS, SKID RIM TOPY, SKID FSTRUT, BOX HARDWARE, BOX BODY, BOX PIPING | KAMOTO COPPER COMPANY | FDB02208 | CAT0793DJFDB02208 | EXM00243 | FML2310DSI2251 | COD 2023 339169 | LF88XHGP | BG75PMGP / BG75PPGP | 2310DSI2251-3 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | 08-12-2023 | 12-12-2023 | 12-12-2023 | 12-12-2023 | 14-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 22-12-2023 | 26-12-2023 | 26-12-2023 | MOKAMBO 22-12-2023 | MOKAMBO 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | HEIDELBERG ENROUTE JOHANNESBURG | JOHANNESBURG | BELA BELA ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | NGUNDU ENROUTE HARARE | NGUNDU ENROUTE HARARE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | LUSAKA ENROUTE MOKAMBO BORDER | LUSAKA TO DISPATCH FOR MOKAMBO BORDER | MOKAMBO BORDER CLEARING | MOKAMBO ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | TRUCK IS AT KANYAKHA EN-ROUTE TO KCC SITE | ON SITE AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2581 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - CHASSIS | KAMOTO COPPER COMPANY | FDB02209 | CAT0793DCFDB02209 | EXM00264 | FML2310DSI2252 | COD 2023 339169 | ND436314 | ND646811 / ND644688 | 2310DSI2252-1 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 12-12-2023 | 14-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | UNIT LOADED FROM PORT YESTERDAY - AWAITING PERMIT AND POLICE ESCORT | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TODAY TOMORROW | MOOI RIVER ENROUTEBEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | BEIT BRIDGE ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | DISPATCHING CHIRUNDU ZAM THIS MORNING | KABWE ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2581 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - BOX INTAKE, AIR CLEANER, SKID BANJO | KAMOTO COPPER COMPANY | FDB02209 | CAT0793DCFDB02209 | EXM00264 | FML2310DSI2252 | COD 2023 339169 | ND919955 | ND140841 | 2310DSI2252-2 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 11-12-2023 | 14-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | BANJO LOADED - WAITING TO LOAD BALANCE OF CARGO - DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VOLKSRUST ENROUTE BEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | MUSINA/BEIT BRIDGE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | BEIT BRIDGE ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | DISPATCHED FROM CHIRUNDU ENROUTE MOKAMBO BORDER | KABWE ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2582 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - CHASSIS | KAMOTO COPPER COMPANY | FDB02210 | CAT0793DKFDB02210 | EXM00248 | FML2310DSI2253 | COD 2023 339169 | ND437412 | ND647660 / ND647016 | 2310DSI2253-1 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 12-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | UNIT LOADED FROM PORT YESTERDAY - AWAITING PERMIT AND POLICE ESCORT | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TODAY TOMORROW | MOOI RIVER ENROUTEBEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | DISPATCHING CHIRUNDU ZAM THIS MORNING | KABWE ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2582 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - BOX INTAKE, AIR CLEANER, SKID BANJO | KAMOTO COPPER COMPANY | FDB02210 | CAT0793DKFDB02210 | EXM00248 | FML2310DSI2253 | COD 2023 339169 | HFR427FS | ND708640 | 2310DSI2253-2 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 11-12-2023 | 14-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 21-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 03-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | BANJO LOADED - WAITING TO LOAD BALANCE OF CARGO - DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VOLKSRUST ENROUTE BEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | MUSINA/BEIT BRIDGE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | BEIT BRIDGE ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | DISPATCHED FROM CHIRUNDU ENROUTE MOKAMBO BORDER | KAPIRI MPHOSHI ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2583 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - CHASSIS | KAMOTO COPPER COMPANY | FDB02211 | CAT0793DJFDB02211 | EXM00270 | FML2310DSI2254 | COD 2023 339169 | ND747407 | ND692809 / ND692831 | 2310DSI2254-1 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 12-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 03-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | UNIT LOADED FROM PORT YESTERDAY - AWAITING PERMIT AND POLICE ESCORT | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | MOOI RIVER ENROUTEBEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | DISPATCHING CHIRUNDU ZAM THIS MORNING | KABWE ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2583 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - BOX INTAKE, AIR CLEANER, SKID BANJO | KAMOTO COPPER COMPANY | FDB02211 | CAT0793DJFDB02211 | EXM00270 | FML2310DSI2254 | COD 2023 339169 | ND919953 | ND823540 | 2310DSI2254-2 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 11-12-2023 | 14-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 03-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | BANJO LOADED - WAITING TO LOAD BALANCE OF CARGO - DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VOLKSRUST ENROUTE BEIT BRIDGE BORDER | MIDDELBURG ENROUTE BEIT BRIDGE | MUSINA/BEIT BRIDGE CLEARING | MUSINA/BEIT BRIDGE CLEARING | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | DISPATCHED FROM CHIRUNDU ENROUTE MOKAMBO BORDER | KABWE ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2583 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID CAB, SKID OUTRIGGERS, SKID RIMS, SKID RIMS, SKID RIM TOPY, SKID FSTRUT, BOX HARDWARE, BOX BODY, BOX PIPING | KAMOTO COPPER COMPANY | FDB02211 | CAT0793DJFDB02211 | EXM00270 | FML2310DSI2254 | COD 2023 339169 | KB53LGGP | ZKZ032GP / ZKZ031GP | 2310DSI2254-3 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | 08-12-2023 | 09-10-2023 | 10-12-2023 | 10-12-2023 | 12-12-2023 | 12-12-2023 | 13-12-2023 | 14-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 22-12-2023 | MOKAMBO 22-12-2023 | MOKAMBO 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 30-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | JOHANNESBURG | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | KAFULAFUTA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | TRUCK IS AT KANYAKHA EN-ROUTE TO KCC SITE | ON SITE AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2583 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID FSTRUT, SKID RH PLATFORM, SDIK FUEL TANK, SKID HANDRAILS, SKID RIM TROPHY | KAMOTO COPPER COMPANY | FDB02211 | CAT0793DJFDB02211 | EXM00270 | FML2310DSI2254 | COD 2023 339169 | JZ76YWGP | CD19GLGP / WKP377GP | 2310DSI2254-4 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 12-12-2023 | 12-12-2023 | 13-12-2023 | 14-12-2023 | 19-12-2023 | 20-12-2023 | 21-12-2023 | 22-12-2023 | MOKAMBO 29-12-2023 | MOKAMBO 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 30-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | JOHANNESBURG | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT LUSAKA ENROUTE MOKAMBO BORDER | KAFULAFUTA ENROUTE MOKAMBO BORDER | KITWE ENROUTE MOKAMBO BORDER | KITWE TO DISPATCH FOR MOKAMBO BORDER | KITWE, BUSY WITH VEHICLE CHECKS | KITWE, BUSY WITH VEHICLE CHECKS | AT MOKAMBO BORDER AWAITING CLEARANCE | ON SITE AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2584 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - CHASSIS | KAMOTO COPPER COMPANY | FDB02212 | CAT0793DCFDB02212 | EXM00241 | FML2310DSI2255 | COD 2023 339169 | ND870909 | ND692813 / ND692828 | 2310DSI2255-1 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 12-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 03-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | UNIT LOADED FROM PORT YESTERDAY - AWAITING PERMIT AND POLICE ESCORT | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | MOOI RIVER ENROUTEBEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | DISPATCHING CHIRUNDU ZAM THIS MORNING | CHIBOMBO ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2584 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - BOX INTAKE, AIR CLEANER, SKID BANJO | KAMOTO COPPER COMPANY | FDB02212 | CAT0793DCFDB02212 | EXM00241 | FML2310DSI2255 | COD 2023 339169 | ND538366 | ND806160 | 2310DSI2255-2 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 11-12-2023 | 14-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 03-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | BANJO LOADED - WAITING TO LOAD BALANCE OF CARGO - DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VOLKSRUST ENROUTE BEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | MUSINA/BEIT BRIDGE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | BEIT BRIDGE ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE CLEARING | DISPATCHED FROM CHIRUNDU ENROUTE MOKAMBO BORDER | KABWE ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2584 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID CAB, SKID OUTRIGGERS, SKID RIMS, SKID RIMS, SKID RIM TOPY, SKID FSTRUT, BOX HARDWARE, BOX BODY, BOX PIPING | KAMOTO COPPER COMPANY | FDB02212 | CAT0793DCFDB02212 | EXM00241 | FML2310DSI2255 | COD 2023 339169 | KT12LHGP | KT40NYGP / KT40PBGP | 2310DSI2255-3 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | 08-12-2023 | 13-12-2023 | 15-12-2023 | 15-12-2023 | 16-12-2023 | 16-12-2023 | 17-12-2023 | 19-12-2023 | 21-12-2023 | 22-12-2023 | 22-12-2023 | 22-12-2023 | MOKAMBO 23-12-2023 | MOKAMBO 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 30-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VILLIERS ENROUTE JOHANNESBURG | JOHANNESBURG | JOHANNESBURG - IN WORKSHOP | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE | BELA BELA ENROUTE BEIT BRIDGE | BELA BELA ENROUTE BEIT BRIDGE | VEHICLE CURRENTLY AT NYABIRA ENROUTRE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZIM SIDE CLEARING | LUSAKA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | TRUCK IS AT KANYAKHA EN-ROUTE TO KCC SITE | ON SITE AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2584 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID FSTRUT, SKID RH PLATFORM, SDIK FUEL TANK, SKID HANDRAILS, SKID RIM TROPHY | KAMOTO COPPER COMPANY | FDB02212 | CAT0793DCFDB02212 | EXM00241 | FML2310DSI2255 | COD 2023 339169 | KC44KMGP | BW54XWGP / BW54XFGP | 2310DSI2255-4 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 10-12-2023 | 12-12-2023 | 12-12-2023 | 13-12-2023 | 14-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 26-12-2023 | MOKAMBO 26-12-2023 | MOKAMBO 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 30-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VILLIERS ENROUTE JOHANNESBURG | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | MAKUTI ENROUTE CHIRUNDU | MAKUTI ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | KAPIRI ENROUTE MOKAMBO BORDER | NDOLA, BUSY WITH VEHICLE CHECKS | MOKAMBO BORDER CLEARING | MOKAMBO ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | TRUCK IS AT KANYAKHA EN-ROUTE TO KCC SITE | ON SITE AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2585 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - CHASSIS | KAMOTO COPPER COMPANY | FDB02213 | CAT0793DVFDB02213 | EXM00268 | FML2310DSI2256 | COD 2023 339169 | ND431993 | ND923084 | 2310DSI2256-1 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 12-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 03-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | UNIT LOADED FROM PORT YESTERDAY - AWAITING PERMIT AND POLICE ESCORT | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TODAY TOMORROW | MOOI RIVER ENROUTEBEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | DISPATCHING CHIRUNDU ZAM THIS MORNING | KABWE ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2585 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - BOX INTAKE, AIR CLEANER, SKID BANJO | KAMOTO COPPER COMPANY | FDB02213 | CAT0793DVFDB02213 | EXM00268 | FML2310DSI2256 | COD 2023 339169 | ND243768 | ND105494 | 2310DSI2256-2 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 12-12-2023 | 12-12-2023 | 12-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 03-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | BANJO LOADED - WAITING TO LOAD BALANCE OF CARGO - DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | NEW CASTLE ENROUTE BEIT BRIDGE BORDER | MIDDELBURG AWAITING PERMIT | MIDDELBURG AWAITING PERMIT | MUSINA/BEIT BRIDGE CLEARING | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | DISPATCHED FROM CHIRUNDU ENROUTE MOKAMBO BORDER | KAPIRI MPHOSHI ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2585 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID CAB, SKID OUTRIGGERS, SKID RIMS, SKID RIMS, SKID RIM TOPY, SKID FSTRUT, BOX HARDWARE, BOX BODY, BOX PIPING | KAMOTO COPPER COMPANY | FDB02213 | CAT0793DVFDB02213 | EXM00268 | FML2310DSI2256 | COD 2023 339169 | KY87BVGP | YSN885GP / YSY203GP | 2310DSI2256-3 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | 08-12-2023 | 09-10-2023 | 10-12-2023 | 10-12-2023 | 12-12-2023 | 12-12-2023 | 13-12-2023 | 14-12-2023 | 21-12-2023 | 22-12-2023 | 22-12-2023 | 22-12-2023 | MOKAMBO 23-12-2023 | MOKAMBO 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 30-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | IN PORT WAITING TO LOAD - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | HEIDELBERG ENROUTE JOHANNESBURG | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | KAPIRI ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | TRUCK IS AT KANYAKHA EN-ROUTE TO KCC SITE | ON SITE AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2585 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID FSTRUT, SKID RH PLATFORM, SDIK FUEL TANK, SKID HANDRAILS, SKID RIM TROPHY | KAMOTO COPPER COMPANY | FDB02213 | CAT0793DVFDB02213 | EXM00268 | FML2310DSI2256 | COD 2023 339169 | KX69FNGP | FS47DCGP / FS47DLGP | 2310DSI2256-4 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | 08-12-2023 | 09-10-2023 | 10-12-2023 | 10-12-2023 | 12-12-2023 | 12-12-2023 | 14-12-2023 | 14-12-2023 | 19-12-2023 | 20-12-2023 | 21-12-2023 | 26-12-2023 | MOKAMBO 26-12-2023 | MOKAMBO 29-12-2023 | 29-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 30-12-2023 | 02-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | IN PORT WAITING TO LOAD - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | JOHANNESBURG | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | KAROI ENROUTE CHIRUNDU | KAROI ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT KAPIRI ENROUTE MOKAMBO BORDER | NDOLA ENROUTE MOKAMBO BORDER | NDOLA ENROUTE MOKAMBO BORDER | NDOLA, BUSY WITH VEHICLE CHECKS | MOKAMBO BORDER CLEARING | MOKAMBO ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | TRUCK IS AT KANYAKHA EN-ROUTE TO KCC SITE | ON SITE AWAITING TO OFFLOAD |  | OFFLOADED | OFFLOADED | OFFLOADED
BA2586 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - CHASSIS | KAMOTO COPPER COMPANY | FDB02214 | CAT0793DAFDB02214 | EXM00271 | FML2310DSI2257 | COD 2023 339169 | ND681744 | ND822365 / ND821906 | 2310DSI2257-1 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 12-12-2023 | 15-12-2023 | 16-12-2023 | 17-12-2023 | 18-12-2023 | 21-12-2023 | 21-12-2023 | 21-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 03-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | UNIT LOADED FROM PORT YESTERDAY - AWAITING PERMIT AND POLICE ESCORT | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TODAY TOMORROW | MOOI RIVER ENROUTEBEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | DISPATCHING CHIRUNDU ZAM THIS MORNING | CHIBOMBO ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2586 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - BOX INTAKE, AIR CLEANER, SKID BANJO | KAMOTO COPPER COMPANY | FDB02214 | CAT0793DAFDB02214 | EXM00271 | FML2310DSI2257 | COD 2023 339169 | ND616983 | BK14YXGP | 2310DSI2257-2 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED | 15-11-2023 | 07-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 07-12-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 11-12-2023 | 14-12-2023 | 17-12-2023 | 18-12-2023 | 18-12-2023 | 20-12-2023 | 21-12-2023 | 21-12-2023 | 21-12-2023 | 23-12-2023 | MOKAMBO 24-12-2023 | MOKAMBO 25-12-2023 | 25-12-2023 | 26-12-2023 | 26-12-2023 | 26-12-2023 | 27-12-2023 | 03-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED FROM PORT - AWAITING POLICE ESCORT - DUE TO WEATHER CONDITIONS ABNORMAL LOADS MOVE - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VOLKSRUST ENROUTE BEIT BRIDGE BORDER | BETHAL ENROUTE BEIT BRIDGE | MUSINA/BEIT BRIDGE CLEARING | MUSINA/BEIT BRIDGE CLEARING | MUSINA WEIGHBRIDGE | MUSINA WEIGHBRIDGE | VEHICLE CURRENTLY HURUNGWE ENROUTE CHIRUNDU | VEHICLE CURRENTLY HURUNGWE ENROUTE CHIRUNDU | DISPATCHED FROM CHIRUNDU ENROUTE MOKAMBO BORDER | KAPIRI MPHOSHI ENROUTE MOKAMBO BORDER | DISPATCHED WHISKEY ENROUTE LUBUMBASHI | LIKASI ENROUTE KOLWEZI | CONNEX KOLWEZI, AWAITING RELEASE | CONNEX KOLWEZI, AWAITING RELEASE | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD |  | TRUCK IS ON SITE SINCE THE 29/12/2023 AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2581 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID FSTRUT, SKID RH PLATFORM, SKID FUEL TANK, SKID HANDRAILS, SKID RIM TROPHY | KAMOTO COPPER COMPANY | FDB02209 | CAT0793DCFDB02209 | EXM00264 | FML2310DSI2252 | COD 2023 339169 | BCE9055ZM | ACZ3735T / ACZ3741T | 2310DSI2252-4 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED 08-01-2024 | 15-11-2023 | 08-12-2023 | BV NUMBER RECEIVED | 03-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 10-12-2023 | 16-12-2023 | 16-12-2023 | 16-12-2023 | 17-12-2023 | 20-12-2023 | 20-12-2023 | 21-12-2023 | 26-12-2023 | MOKAMBO 27-12-2023 | 30-12-2023 | 30-12-2023 | 30-12-2023 | 05-01-2024 | 05-01-2024 | 06-01-2023 | 08-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE PREPARING TO DISPATCH | KABWE ENROUTE MOKAMBO BORDER | NDOLA ENROUTE MOKAMBO BORDER | NDOLA, BUSY WITH VEHICLE CHECKS | CHAMBISHI ENROUTE MOKAMBO BORDER | MOKAMBO BORDER | TRUCK IS AT MOKAMBO ZAM SIDE AWAITING TO CROSS | TRUCK IS AT KABEMBA PARKED FOR SAFTY |  | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK ARE AT LUBUMBASHI EN-ROUTE TO KCC SITE | ON SITE WAITING TO OFFLOAD | OFFLOADED 08-01-2024 | OFFLOADED 08-01-2024
BA2580 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID FSTRUT, SKID RH PLATFORM, SKID FUEL TANK, SKID HANDRAILS, SKID RIM TROPHY | KAMOTO COPPER COMPANY | FDB02208 | CAT0793DJFDB02208 | EXM00243 | FML2310DSI2251 | COD 2023 339169 | BCE5042ZM | AEB1961ZM / AEB1959ZM | 2310DSI2251-4 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED 09-01-2024 | 15-11-2023 | 08-12-2023 | BV COMPLETED | 03-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 10-12-2023 | 16-12-2023 | 16-12-2023 | 16-12-2023 | 17-12-2023 | 20-12-2023 | 21-12-2023 | 22-12-2023 | 27-12-2023 | 28-12-2023 | 29-12-2023 | 29-12-2023 | 30-12-2023 | 05-01-2023 | 06-01-2024 | 06-01-2023 | 09-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE PREPARING TO DISPATCH | LUSAKA ENROUTE MOKAMBO BORDER | LUSAKA ENROUTE MOKAMBO BORDER | NDOLA, BUSY WITH VEHICLE CHECKS | NDOLA, BUSY WITH VEHICLE CHECKS | NDOLA, BUSY WITH VEHICLE CHECKS | NDOLA, BUSY WITH VEHICLE CHECKS | TRUCK IS AT KABEMBA PARKED FOR SAFTY |  | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | VEHICLE AT KOLWEZI - WAITING TO PROCEED TO SITE | ON SITE WAITING TO OFFLOAD | OFFLOADED 09-01-2024
BA2581 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID CAB, SKID OUTRIGGERS, SKID RIMS, SKID RIMS, SKID RIM TOPY, SKID FSTRUT, BOX HARDWARE, BOX BODY, BOX PIPING | KAMOTO COPPER COMPANY | FDB02209 | CAT0793DCFDB02209 | EXM00264 | FML2310DSI2252 | COD 2023 339169 | BCE5037ZM | ACZ3745T / ACZ3734T | 2310DSI2252-3 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED 09-01-2024 | 15-11-2023 | 08-12-2023 | BV COMPLETED | 03-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 10-12-2023 | 16-12-2023 | 16-12-2023 | 16-12-2023 | 17-12-2023 | 20-12-2023 | 21-12-2023 | 22-12-2023 | 28-12-2023 | MOKAMBO 29-12-2023 | 30-12-2023 | 30-12-2023 | 30-12-2023 | 05-01-2024 | 05-01-2024 | 06-01-2023 | 09-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE PREPARING TO DISPATCH | LUSAKA ENROUTE MOKAMBO BORDER | LUSAKA ENROUTE MOKAMBO BORDER | NDOLA, BUSY WITH VEHICLE CHECKS | NDOLA, BUSY WITH VEHICLE CHECKS | NDOLA, BUSY WITH VEHICLE CHECKS | TRUCK IS AT MOKAMBO ZAM SIDE AWAITING TO CROSS | TRUCK IS AT KABEMBA PARKED FOR SAFTY |  | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK ARE AT LUBUMBASHI EN-ROUTE TO KCC SITE | VEHICLE AT KOLWEZI - WAITING TO PROCEED TO SITE | ON SITE WAITING TO OFFLOAD | OFFLOADED 09-01-2024
BA2582 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID CAB, SKID OUTRIGGERS, SKID RIMS, SKID RIMS, SKID RIM TOPY, SKID FSTRUT, BOX HARDWARE, BOX BODY, BOX PIPING | KAMOTO COPPER COMPANY | FDB02210 | CAT0793DKFDB02210 | EXM00248 | FML2310DSI2253 | COD 2023 339169 | BCD9044ZM | BCD1761ZM / BCD1779ZM | 2310DSI2253-3 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED 09-01-2024 | 15-11-2023 | 08-12-2023 | BV COMPLETED | 03-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 10-12-2023 | 16-12-2023 | 16-12-2023 | 16-12-2023 | 17-12-2023 | 20-12-2023 | 20-12-2023 | 21-12-2023 | 27-12-2023 | MOKAMBO 27-12-2023 | 27-12-2023 | 27-12-2023 | 30-12-2023 | 05-01-2024 | 05-01-2024 | 06-01-2023 | 09-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE PREPARING TO DISPATCH | KABWE ENROUTE MOKAMBO BORDER | NDOLA ENROUTE MOKAMBO BORDER | NDOLA, BUSY WITH VEHICLE CHECKS | NDOLA, BUSY WITH VEHICLE CHECKS | MOKAMBO BORDER | TRUCK IS AT MOKAMBO ZAM SIDE AWAITING TO CROSS | TRUCK IS AT KABEMBA PARKED FOR SAFTY |  | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK ARE AT LUBUMBASHI EN-ROUTE TO KCC SITE | VEHICLE AT KOLWEZI - WAITING TO PROCEED TO SITE | ON SITE WAITING TO OFFLOAD | OFFLOADED 09-01-2024
BA2582 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID FSTRUT, SKID RH PLATFORM, SDIK FUEL TANK, SKID HANDRAILS, SKID RIM TROPHY | KAMOTO COPPER COMPANY | FDB02210 | CAT0793DKFDB02210 | EXM00248 | FML2310DSI2253 | COD 2023 339169 | BCF3322ZM | BAL867ZM / BBA163ZM | 2310DSI2253-4 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED 09-01-2024 | 15-11-2023 | 08-12-2023 | BV COMPLETED | 03-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 10-12-2023 | 16-12-2023 | 16-12-2023 | 16-12-2023 | 17-12-2023 | 20-12-2023 | 21-12-2023 | 22-12-2023 | 27-12-2023 | 27-12-2023 | 28-12-2023 | 30-12-2023 | 30-12-2023 | 05-01-2024 | 05-01-2024 | 06-01-2023 | 09-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | LOADED IN PORT AND WILL PROCEED TO THE BV SITE TOMORROW - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | LUSAKA ENROUTE MOKAMBO BORDER | LUSAKA ENROUTE MOKAMBO BORDER | NDOLA, BUSY WITH VEHICLE CHECKS | NDOLA, BUSY WITH VEHICLE CHECKS | NDOLA, BUSY WITH VEHICLE CHECKS | NDOLA, BUSY WITH VEHICLE CHECKS | TRUCK IS AT KABEMBA PARKED FOR SAFTY |  | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK ARE AT LUBUMBASHI EN-ROUTE TO KCC SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 09-01-2024
BA2586 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID CAB, SKID OUTRIGGERS, SKID RIMS, SKID RIMS, SKID RIM TOPY, SKID FSTRUT, BOX HARDWARE, BOX BODY, BOX PIPING | KAMOTO COPPER COMPANY | FDB02214 | CAT0793DAFDB02214 | EXM00271 | FML2310DSI2257 | COD 2023 339169 | BCE5039ZM | BCA4540T / BCA4541T | 2310DSI2257-3 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED 09-01-2024 | 15-11-2023 | 08-12-2023 | BV COMPLETED | 03-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 10-12-2023 | 16-12-2023 | 16-12-2023 | 17-12-2023 | 17-12-2023 | 20-12-2023 | 20-12-2023 | 21-12-2023 | 27-12-2023 | MOKAMBO 27-12-2023 | MOKAMBO 27-12-2023 | 28-12-2023 | 29-12-2023 | 30-12-2023 | 05-01-2024 | 06-01-2023 | 09-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | IN PORT WAITING TO LOAD - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY & TOMORROW | VEHICLE AT DEPOT, WAITING BV INSPECTION - BV INSPECTION BOOKED FOR TODAY | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE PREPARING TO DISPATCH | KABWE ENROUTE MOKAMBO BORDER | NDOLA ENROUTE MOKAMBO BORDER | NDOLA, BUSY WITH VEHICLE CHECKS | NDOLA, BUSY WITH VEHICLE CHECKS | MOKAMBO BORDER | TRUCK IS AT MOKAMBO ZAM SIDE AWAITING TO CROSS | TRUCK IS AT KABEMBA PARKED FOR SAFTY |  | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK ARE AT LUBUMBASHI EN-ROUTE TO KCC SITE | VEHICLE AT KOLWEZI - WAITING TO PROCEED TO SITE | ON SITE WAITING TO OFFLOAD | OFFLOADED 09-01-2024
BA2586 | 1 X CAT793D OFF HIGHWAY TRUCK IN CKD FORM - SKID FSTRUT, SKID RH PLATFORM, SKID HANDRAILS, SKID RIM TROPHY | KAMOTO COPPER COMPANY | FDB02214 | CAT0793DAFDB02214 | EXM00271 | FML2310DSI2257 | COD 2023 339169 | BCE5052ZM | BAL809ZM / BAL829ZM | 2310DSI2257-4 | VESSEL: GOLDEN ISLE Voy. 233210 - ETA DURBAN: 03-12-2023 | OFFLOADED 09-01-2024 | 15-11-2023 | 08-12-2023 | BV COMPLETED | 03-12-2023 | 08-12-2023 | 09-12-2023 | 10-12-2023 | 10-12-2023 | 10-12-2023 | 16-12-2023 | 16-12-2023 | 17-12-2023 | 17-12-2023 | 21-12-2023 | 21-12-2023 | 22-12-2023 | 22-12-2023 | MOKAMBO 23-12-2023 | MOKAMBO 23-12-2023 | 25-12-2023 | 29-12-2023 | 30-12-2023 | 05-01-2024 | 06-01-2023 | 09-01-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 25-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 01-12-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 03-12-2023 | VESSEL IN AND WORKING - VEHICLE IN PORT TO LOAD | DUE TO WEATHER CONDITIONS DISCHARGING OF THE VESSEL HAS STOPPED, AWAITING WEATHER TO CLEAR INORDER TO PROCEED WITH DISCHARGE AND LOADING | IN PORT WAITING TO LOAD - BV INSPECTION BOOKED FOR TOMORROW AND FRIDAY | LOADED IN PORT AND WILL PROCEED TO THE BV SITE T - BV INSPECTION BOOKED FOR TODAY AND TOMORROW | LOADED IN PORT AND WILL PROCEED TO THE BV SITE T - BV INSPECTION BOOKED FOR TODAY | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE PREPARING TO DISPATCH | LUSAKA ENROUTE MOKAMBO BORDER | KAFULAFUTA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CLEARING | TRUCK IS AT MOKAMBO ZAM SIDE AWAITING TO CROSS | TRUCK IS AT KABEMBA PARKED FOR SAFTY |  | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK IS AT KABEMBA PARKED FOR SAFTY PLANNING TO DISPATCH TO SITE TODAY | TRUCK ARE AT LUBUMBASHI EN-ROUTE TO KCC SITE | VEHICLE AT KOLWEZI - WAITING TO PROCEED TO SITE | ON SITE WAITING TO OFFLOAD | OFFLOADED 09-01-2024
BA2530 | CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / MUTANDA MINING SARP - DELIVER TO KAMOTO KOPPER COMPANY | 3F606122 | CAT00745T3F606122 | TBA | FML2311DSI2286 | COD 2023 350010 | ND919953 | ND823540 | 2311DSI2286 | VESSEL: GREY FOX Voy. 241201 - ETA DURBAN: 17-01-2024 | OFFLOADED 06-02-2024 | 04-12-2023 | 22-12-2023 | BV COMPLETED | 22-01-2024 | 23-01-2024 | 24-01-2024 | 24-01-2024 | 25-01-2024 | 26-01-2024 | 27-01-2024 | 27-01-2024 | 28-01-2024 | 28-01-2024 | 30-01-2024 | 30-01-2024 | 31-01-2024 | 31-01-2024 | MOKAMBO 01-02-2024 | 02.02.2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 06-02-2024 | [24 empty] | AWAITING VESSEL DETAILS | AWAITING VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 |  | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 13-01-2024 | AWAITING VESSEL ARRIVAL ON THE 16-01-2024 | AWAITING VESSEL ARRIVAL ON THE 16-01-2024 | AWAITING VESSEL ARRIVAL ON THE 16-01-2024 | AWAITING VESSEL ARRIVAL ON THE 16-01-2024 | AWAITING VESSEL ARRIVAL ON THE 16-01-2024 | AWAITING VESSEL ARRIVAL ON THE 16-01-2024 | AWAITING VESSEL ARRIVAL ON THE 17-01-2024 | AWAITING VESSEL ARRIVAL ON THE 17-01-2024 | AWAITING VESSEL ARRIVAL ON THE 17-01-2024 | AWAITING VESSEL ARRIVAL ON THE 17-01-2024 | UNIT WILL BE COLLECTED FROM PORT TOMMOROW THE 23/01/2024 | UNIT IS AT TRANSPORTERS DEPO AWAITING BV AND TRIP CHECK BEFORE DISPATCH | UNIT IS AT NEW CASTLE EN-ROUTE TO BEITBRIDGE BORDER | UNIT IS AT GROBLERSDAL EN-ROUTE TO BEITBRIDGE BORDER | UNIT IS AT BEITBRIDGE BORDER AWAITING CLEARANCE | CHIRUNDU ZIM SIDE | CHIRUNDU ZAM SIDE WAITING ESCORT | KABWE ENROUTE MOKAMBO BORDER | MUFULIRA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER | ON SITE WAIITNG TO OFFLOAD | ON SITE WAIITNG TO OFFLOAD - PLEASE ASSIST | ON SITE WAIITNG TO OFFLOAD - PLEASE ASSIST | OFFLOADED 06-02-2024 | OFFLOADED 06-02-2024
BA2531 | CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / MUTANDA MINING SARP - DELIVER TO KAMOTO KOPPER COMPANY | 3F606123 | CAT00745P3F606123 | TBC | FML2310DSI2266 | COD 2023 350010 | ND919950 | ND820122 | 2310DSI2266 | VESSEL: GOLDEN KAROO Voy. 231220 - ETA DURBAN: 18-12-2023 | OFFLOADED 06-02-2024 | 04-12-2023 | 22-12-2023 | BV COMPLETED | 18-12-2023 | 19-01-2024 | 21-01-2024 | 22-01-2024 | 23-01-2024 | 24-01-2024 | 24-01-2024 | 24-01-2024 | 26-01-2024 | 27-01-2024 | 29-01-2029 | 29-01-2024 | 29-01-2024 | 30-01-2024 | MOKAMBO 31-01-2024 | MOKAMBO 01-02-2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 06-02-2024 |  | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL:- ETA DURBAN 24-11-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 10-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | AWAITING VESSEL ARRIVAL ON THE 18-12-2023 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR FRIDAY 22-12 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR FRIDAY 22-12 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR FRIDAY 22-12 - DUE TO FULL EMBARGO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | BV INSPECTION COMPLETED - DUE TO FULL EMBARGO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | BV INSPECTION COMPLETED - DUE TO FULL EMBARGO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | BV INSPECTION COMPLETED - DUE TO FULL EMBARGO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | BV INSPECTION COMPLETED - DUE TO FULL EMBARGO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | BV INSPECTION COMPLETED - DUE TO FULL EMBARGO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 |  | BV INSPECTION COMPLETED - DUE TO FULL EMBARGO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | BV INSPECTION COMPLETED - DUE TO FULL EMBARGO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | BV INSPECTION COMPLETED - DUE TO FULL EMBARGO'S THE VEHICLE WILL ONLY DISPATCH IN JANUARY 2024 | BV INSPECTION COMPLETED - AWAITING FOR A VEHICLE TO ARRIVE BACK FROM DRC - LOADING NEXT WEEK | BV INSPECTION COMPLETED - AWAITING FOR A VEHICLE TO ARRIVE BACK FROM DRC - LOADING NEXT WEEK | BV INSPECTION COMPLETED - AWAITING FOR A VEHICLE TO ARRIVE BACK FROM DRC - LOADING NEXT WEEK | BV INSPECTION COMPLETED - AWAITING FOR A VEHICLE TO ARRIVE BACK FROM DRC - LOADING NEXT WEEK | LOADING MONDAY 15-01-2024 | LOADING PM TODAY | LOADED - AWAITING PERMIT | VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - DELAY DUE TO BAD WEATHER CONDITIONS | VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - DELAYED DUE TO BAD WEATHER CONDITIONS | VEHCILE CURRENTLY AT GLENCOE ENROUTE JOHANNESBURG | VEHCILE CURRENTLY AT ERMELO EN-ROUTE JOHANNESBURG | VEHCILE CURRENTLY AT POLOKWANE EN-ROUTE TO BEITBRIDGE | VEHCILE CURRENTLY AT BEITBRIDGE ZIM SIDE | VEHCILE CURRENTLY AT CHIVU ZIM EN-ROUTE TO CHIRUNDU | VEHCILE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | CHIRUNDU ZAM SIDE | KAPIRI MPHOSHI ENROUTE MOKAMBO BORDER | MUFULIRA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER | WHISKEY | ON SITE WAIITNG TO OFFLOAD | ON SITE WAIITNG TO OFFLOAD - PLEASE ASSIST | ON SITE WAIITNG TO OFFLOAD - PLEASE ASSIST | OFFLOADED 06-02-2024 | OFFLOADED 06-02-2024
BA2409B & BA2410B | HOOKS & COUPLERS FOR BA2409 & BA2410 | KAMOTO COPPER COMPANY | N/A | N/A | N/A | FML2311DSI2299 | COD 2023 331712 PT03 | BCD9085ZM | BCD723ZM | 2311DSI2299 | VESSEL: HOEGH TRANSPORTER V.169 - ETA DURBAN: 28-12-2023 | OFFLOADED | 17-11-2023 | 10-01-2024 | BV COMPLETED | 28-12-2023 | 16-01-2024 | 16-01-2024 | 17-01-2024 | 18-01-2024 | 19-01-2024 | 22-01-2024 | 22-01-2024 | 24-01-2024 | 25-01-2024 | 25-01-2024 | 26-01-2024 | 26-01-2024 | 30-01-2024 | 31-01-2024 | 06-02-2024 | 07-02-2024 | 11-02-2024 | 11-02-2024 | 11-02-2024 | 13-02-2024 | 14-02-2024 | [24 empty] | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 26-12-2023 | AWAITING VESSEL ARRIVAL ON THE 26-12-2023 | AWAITING VESSEL ARRIVAL ON THE 26-12-2023 | AWAITING VESSEL ARRIVAL ON THE 28-12-2023 | AWAITING VESSEL ARRIVAL ON THE 28-12-2023 | AWAITING VESSEL ARRIVAL ON THE 28-12-2023 | VESSEL DUE TO ARRIVE PM TODAY | VESSEL IN AND WORKING | UNITS TO BE DELIVERED TODAY TO OUR FACILITY |  | UNITS IS AT OUR FACILITY AWAITING BALANCE PIECES TO BE DELIVERED IN ORDER TO DISPATCH TO SITE-ESTIMATED DISPATCH DATE THE 15-01-2024 | UNITS IS AT OUR FACILITY AWAITING BALANCE PIECES TO BE DELIVERED IN ORDER TO DISPATCH TO SITE-ESTIMATED DISPATCH DATE THE 15-01-2024 | UNITS IS AT OUR FACILITY AWAITING BALANCE PIECES TO BE DELIVERED IN ORDER TO DISPATCH TO SITE-ESTIMATED DISPATCH DATE THE 15-01-2024 | UNITS IS AT OUR FACILITY AWAITING BALANCE PIECES TO BE DELIVERED IN ORDER TO DISPATCH TO SITE - BV INSPECTION TO BE BOOKED FOR WEDNESDAY 10-01-2024 - ESTIMATED DISPATCH DATE THE 15-01-2024 | BV INSPECTION BOOKED FOR 10-01-2024 - AWAITING COMPLETION - ESTIMATED LOADING DATE 15-01-2024 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 15-01-2024 | BV INSPECTION COMPLETED - ESTIMATED LOADING DATE 15-01-2024 | BV INSPECTION COMPLETED - ESTIMATED LOADING DATE 15-01-2024 | LOADING TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | VEHICLE CURRENLTY AT HILTON ENROUTE GROBLERSBRIDGE BORDER | VEHICLE CURRENLTY AT MOOKGOPONG ENROUTE GROBLERSBRIDGE BORDER | VEHICLE CURRENLTY AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | VEHICLE CURRENLTY AT LIVINGSTONE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT LIVINGSTONE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT CHISAMBA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT NDOLA UNDERGOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING CLEARANCE AND IN THE QUEUE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING CLEARANCE AND IN THE QUEUE TO KASUMBALESA | VEHICLE BEFORE KASUMBALESA AND SHOULD CROSS TO DRC SIDE PM TODAY | VEHICLE AT KASUMBALESA BORDER | VEHICLE AT KASUMBALESA ZAM SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARNACE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARNACE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT KOLWEZI EN-ROUTE TO SITE | VEHICLE CURRENTLY AT KOLWEZI AWAITING TO OFFLOAD | OFFLOADED
BA2409B & BA2410B | HAMMERS & LINERS FOR BA2409 & BA2410 | KAMOTO COPPER COMPANY | N/A | N/A | N/A | FML2312DSI2323 | COD 2023 331712 PT03 | BCD9085ZM | BCD723ZM | 2311DSI2299 | VESSEL: HOEGH TARGET V.50 - ETA DURBAN: 04-01-2024 | OFFLOADED | 17-11-2023 | 10-01-2024 | BV COMPLETED | 04-01-2024 | 16-01-2024 | 16-01-2024 | 17-01-2024 | 18-01-2024 | 19-01-2024 | 22-01-2024 | 22-01-2024 | 24-01-2024 | 25-01-2024 | 25-01-2024 | 26-01-2024 | 26-01-2024 | 30-01-2024 | 31-01-2024 | 06-02-2024 | 07-02-2024 | 11-02-2024 | 11-02-2024 | 11-02-2024 | 13-02-2024 | 14-02-2024 | [32 empty] | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 23-12-2023 | AWAITING VESSEL ARRIVAL ON THE 06-01-2023 | AWAITING VESSEL ARRIVAL ON THE 06-01-2023 | AWAITING VESSEL ARRIVAL ON THE 06-01-2023 | AWAITING VESSEL ARRIVAL ON THE 06-01-2023 | AWAITING VESSEL ARRIVAL ON THE 04-01-2023 | AWAITING VESSEL ARRIVAL ON THE 04-01-2023 | AWAITING VESSEL ARRIVAL ON THE 04-01-2023 | AWAITING VESSEL ARRIVAL ON THE 04-01-2023 | AWAITING VESSEL ARRIVAL ON THE 04-01-2023 |  | AWAITING VESSEL ARRIVAL ON THE 04-01-2023 | AWAITING VESSEL ARRIVAL ON THE 04-01-2023 | COLLECTING FROM PORT TODAY | COLLECTED FROM PORT - TO BE DELIVERED TO THE BONDED FACILITY TODAY - BV INSPECTION TO BE BOOKED FOR WEDNESDAY 10-01-2024 - ESTIMATED DISPATCH DATE 15-01-2024 | BV INSPECTION BOOKED FOR 10-01-2024 - AWAITING COMPLETION - ESTIMATED LOADING DATE 15-01-2024 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 15-01-2024 | BV INSPECTION COMPLETED - ESTIMATED LOADING DATE 15-01-2024 | BV INSPECTION COMPLETED - ESTIMATED LOADING DATE 15-01-2024 | LOADING TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | VEHICLE CURRENLTY AT HILTON ENROUTE GROBLERSBRIDGE BORDER | VEHICLE CURRENLTY AT MOOKGOPONG ENROUTE GROBLERSBRIDGE BORDER | VEHICLE CURRENLTY AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | VEHICLE CURRENLTY AT LIVINGSTONE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT LIVINGSTONE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT CHISAMBA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT NDOLA UNDERGOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING CLEARANCE AND IN THE QUEUE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING CLEARANCE AND IN THE QUEUE TO KASUMBALESA | VEHICLE BEFORE KASUMBALESA AND SHOULD CROSS TO DRC SIDE PM TODAY | VEHICLE AT KASUMBALESA BORDER | VEHICLE AT KASUMBALESA ZAM SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARNACE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARNACE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT KOLWEZI EN-ROUTE TO SITE | VEHICLE CURRENTLY AT KOLWEZI AWAITING TO OFFLOAD | OFFLOADED
BA2530 | CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / MUTANDA MINING SARP - DELIVER TO KAMOTO KOPPER COMPANY | 3F606122 | CAT00745T3F606122 | TBA | FML2311DSI2286 | COD 2023 350010 | ND919953 | ND823540 | 2311DSI2286 | VESSEL: GREY FOX Voy. 241201 - ETA DURBAN: 17-01-2024 | OFFLOADED 06-02-2024 | 04-12-2023 | 22-12-2023 | BV COMPLETED | 22-01-2024 | 23-01-2024 | 24-01-2024 | 24-01-2024 | 25-01-2024 | 26-01-2024 | 27-01-2024 | 27-01-2024 | 28-01-2024 | 28-01-2024 | 30-01-2024 | 30-01-2024 | 31-01-2024 | 31-01-2024 | MOKAMBO 01-02-2024 | 02.02.2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 06-02-2024 | [20 empty] | OFFLOADED 06-02-2024
BA2531 | CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / MUTANDA MINING SARP - DELIVER TO KAMOTO KOPPER COMPANY | 3F606123 | CAT00745P3F606123 | TBC | FML2310DSI2266 | COD 2023 350010 | ND919950 | ND820122 | 2310DSI2266 | VESSEL: GOLDEN KAROO Voy. 231220 - ETA DURBAN: 18-12-2023 | OFFLOADED 06-02-2024 | 04-12-2023 | 22-12-2023 | BV COMPLETED | 18-12-2023 | 19-01-2024 | 21-01-2024 | 22-01-2024 | 23-01-2024 | 24-01-2024 | 24-01-2024 | 24-01-2024 | 26-01-2024 | 27-01-2024 | 29-01-2029 | 29-01-2024 | 29-01-2024 | 30-01-2024 | MOKAMBO 31-01-2024 | MOKAMBO 01-02-2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 06-02-2024 | [20 empty] | OFFLOADED 06-02-2024
BA2682 | CAT 6060 BUCKET - BUCKET GP-BOWL 97501001 - 577-7494 | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | N/A | N/A | N/A | FML2402DSI2414 | COD 2024 137553 | ND57281 | CD55YJGP | 2402DSI2414A | VESSEL: TOMBARRA Voy. 037 - ETA DURBAN: 09-03-2024 | OFFLOADED 01-04-2024 | 29-02-2024 | 05/04/2024 | BV NUMBER RECEIVED | 09-03-2024 | 14-03-2024 | 16-03-2024 | 17-03-2024 | 18-03-2024 | 19-03-2024 | 20-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 24-03-2024 | 24-03-2024 | 24-03-2024 | 24-03-2024 | MOKAMBO 25-03-2024 | MOKAMBO 25-03-2024 | 26-03-2024 | 26-03-2024 | 27-03-2024 | 27-03-2024 | 29-03-2024 | 01-04-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 09-03-2024 | AWAITING VESSEL ARRIVAL - ETA 09-03-2024 | AWAITING VESSEL ARRIVAL - ETA 09-03-2024 | VESSEL ARRIVED 09-03-2024 - TO BE LOADED FROM PORT TODAY - BV ISNPECTION TO BE BOOKED FOR WEDNESDAY | LOADED FROM PORT YESTERDAY - AWAITING POLICE ESCORT - BV INSPECTION BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | DISPATCHED DURBAN ENROUTE MUSINA | VEHILCLE AT VOLKSRUST ENROUTE MUSINA | VEHILCLE AT POLOKWANE ENROUTE MUSINA | VEHILCLE AT BEITBRIDGE RSA SIDE | VEHILCLE DISPATCH BEITBRIDGE EN-ROUTE TO HARARE | VEHILCLE AT HARARE EN-ROUTE TO CHIRUNDU | VEHILCLE AT CHIRUNDU ZIM SIDE CLEARING | VEHILCLE AT MUFULIRA ZAMBIA ENROUTE MOKAMBO BORDER | VEHILCLE AT WHISKEY AWAITING RELEASE | VEHILCLE AT LUBUMBASHI ENROUTE KOLWEZI | VEHILCLE PASSING LIKASI ENROUTE KOLWEZI | OFFLOADED 01-04-2024 | OFFLOADED 01-04-2024
BA2682 | CAT 6060 BUCKET - BUCKET GP - BW 97401001 - 463-9277 | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | N/A | N/A | N/A | FML2402DSI2414 | COD 2024 137553 | ND260597 | BB47XBZN | 2402DSI2414B | VESSEL: TOMBARRA Voy. 037 - ETA DURBAN: 09-03-2024 | OFFLOADED 01-04-2024 | 29-02-2024 | 05/04/2024 | BV NUMBER RECEIVED | 09-03-2024 | 14-03-2024 | 16-03-2024 | 17-03-2024 | 18-03-2024 | 19-03-2024 | 20-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 24-03-2024 | 24-03-2024 | 24-03-2024 | 24-03-2024 | MOKAMBO 25-03-2024 | MOKAMBO 25-03-2024 | 26-03-2024 | 26-03-2026 | 27-03-2024 | 27-03-2024 | 29-03-2024 | 01-04-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA 09-03-2024 | AWAITING VESSEL ARRIVAL - ETA 09-03-2024 | AWAITING VESSEL ARRIVAL - ETA 09-03-2024 | VESSEL ARRIVED 09-03-2024 - TO BE LOADED FROM PORT TODAY - BV ISNPECTION TO BE BOOKED FOR WEDNESDAY | LOADED FROM PORT YESTERDAY - AWAITING POLICE ESCORT - BV INSPECTION BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | DISPATCHED DURBAN ENROUTE MUSINA | VEHILCLE AT VOLKSRUST ENROUTE MUSINA | VEHILCLE AT POLOKWANE ENROUTE MUSINA | VEHILCLE AT BEITBRIDGE RSA SIDE | VEHILCLE DISPATCH BEITBRIDGE EN-ROUTE TO HARARE | VEHILCLE AT HARARE EN-ROUTE TO CHIRUNDU | VEHILCLE AT CHIRUNDU ZIM SIDE CLEARING | VEHILCLE AT MUFULIRA ZAMBIA ENROUTE MOKAMBO BORDER | VEHILCLE AT WHISKEY AWAITING RELEASE | VEHILCLE AT LUBUMBASHI ENROUTE KOLWEZI | VEHILCLE PASSING LIKASI ENROUTE KOLWEZI | OFFLOADED 01-04-2024 | OFFLOADED 01-04-2024
BA2662 | COBRA LUBE SERVICE UNIT FOR CAT745 BARE CHASSIS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | N/A | N/A | N/A | FML2402DRE2436 | COD 2024 158098 | ND923885 | ND184465 | ND64752 | EX RSA | OFFLOADED 27-04-2024 | 08/04/2024 | 10/05/2024 | BV COMPLETED | N/A | N/A | EX JHB | 12-04-2024 | 15-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 18-04-2024 | 18-04-2024 | 20-04-2024 | 20-04-2024 | 21-04-2024 | 22-04-2024 | 22-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 26-04-2024 | 26-04-2024 | 26-04-2024 | 27-04-2024 | [23 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED, AWAITING BV INSPECTION DATE AND LOADING DATE | TRUCK LOADING TODAY AND TO DISPATCH TOMMROW THE 11/04/2024 | TRUCK TO DISPATCH TODAY ONCE PERMITS RECEIVED | TRUCK IS AT PRETOTIA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IS AT MODI MOLE EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IS AT MVUMA ENROUTE HARARE | TRUCK IS AT HARARE TO DISPATCH FOR CHIRUNDU | BV NUMBER RECEIVED, AWAITING BV INSPECTION DATE AND LOADING DATE | CHIRUNDU ZAM SIDE | KASUMBALESA ZAM SIDE | TRUCK AT WHISKEY AWAITING RELEASE | TRUCK AT WHISKEY AWAITING RELEASE | TRUCK AT WHISKEY DISPATCHING TO KANYAKA | TRUCK AT LUBUMBASHI ENROUTE SITE | OFFLOADED 27-04-2024
BA2663 | COBRA FLAT DECK WITH CRANE | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | N/A | N/A | N/A | FML2404DRE2489 | COD 2024 232416 | ND919947 | BL00YBZN | MFSTD001889 | EX RSA | OFFLOADED 26-07-2024 | 11-07-2024 |  | BV COMPLETED | N/A | N/A | N/A | 17-07-2024 | 17-07-2024 | 18-07-2024 | 20-07-2024 | 20-07-2024 | 21-07-2024 | 21-07-2024 | 22-07-2024 | 22-07-2024 | 23-07-2024 | 23-07-2024 | MOKAMBO 24-07-2024 | MOKAMBO 24-07-2024 | 25-07-2024 | 25-07-2024 | 25-07-2024 | 25-07-2024 | 25-07-2024 | 26-07-2024 | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | AWAITING BV NUMBER AND COLLECTION DATE FROM SUPPLIER | BV NUMBER RECEIVED - INSPECTION BOOKED FOR MONDAY 15-07-2024 - LOADING PLANNED FOR 16-07-2024 | BV NUMBER RECEIVED - INSPECTION BOOKED FOR MONDAY 15-07-2024 - LOADING PLANNED FOR 16-07-2024 | BV INSPECTION COMPLETED - LOADING TODAY | LOADED - ENROUTE BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | CHIRUNDU ZAM SIDE CLEARING | CHIBOMBO ZAMBIA ENROUTE MOKAMBO BORDER | MUFULIRA ENROUTE MOKAMBO BORDER | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 26-07-2024
BA2683 | CAT950-14A WHEEL LOADER | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | CM200213 | CAT00950CCM200213 | D7E00865 | FML2404DSI2513 | COD 2024 263491 | BL64MKZN | ND702944 | ND61889 | VESSEL: CALIFORNIA HIGHWAY Voy. 139 - ETA DURBAN: 04-06-2024 | OFFLOADED 28-09-2024 | 28-08-2024 |  | BV NUMBER RECEIVED | 04-06-2024 | 05-09-2024 | 05-09-2024 | 06-09-2024 | 06-09-2024 | 10-09-2024 | 11-09-2024 | 12-09-2024 | 13-09-2024 | 15-09-2024 | 18-09-2024 | 18-09-2024 | 19-09-2024 | 19-09-2024 | 20-09-2024 | 22-09-2024 | 23-09-2024 | 25-09-2024 | 25-09-2024 | 25-09-2024 | 26-09-2024 | 28-09-2024 | [8 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN 31-05-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 31-05-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 31-05-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 01-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 04-06-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN 04-06-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING | UNIT TO BE DELIVERED TO BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | BV INSPECTION BOOKED FOR TODAY - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING NEXT WEEK | LOADING WEDNESDAY 04-09-2024 | LOADING WEDNESDAY 04-09-2024 | LOADING TODAY | HOWICK ENROUTE BEIT BRIDGE BORDER | DISPATCHING JOHANNESBURG TO PROCEED TO BEIT BRIDGE BORDER | MUSINA TO PROCEED TO BEIT BRIDGE BORDER | MUSINA AWAITING CROSS BORDER PERMIT | BEIT BRIDGE ZIM SIDE | MASVINGO ENROUTE HARARE | HARARE TO DISPATCH FOR CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE - AWAITING ZAMBIAN PERMIT | KAPIRI MPOSHI ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | DISPATCHING FROM WHISKEY FRO SITE | LIKASI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 28-09-2024
BA2683A | CAT950-14A BUCKET | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | N/A | N/A | N/A | FML2407DSI2559 | COD 2024 263491 | BL64MKZN | ND702944 | ND61889 | VESSEL: HOEGH TROOPER V. 207 - ETA DURBAN: 21-08-2024 | OFFLOADED 28-09-2024 | 28-08-2024 |  | BV NUMBER RECEIVED | 21-08-2024 | 05-09-2024 | 05-09-2024 | 06-09-2024 | 06-09-2024 | 10-09-2024 | 11-09-2024 | 12-09-2024 | 13-09-2024 | 15-09-2024 | 18-09-2024 | 18-09-2024 | 19-09-2024 | 19-09-2024 | 20-09-2024 | 22-09-2024 | 23-09-2024 | 25-09-2024 | 25-09-2024 | 25-09-2024 | 26-09-2024 | 28-09-2024 | [55 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | VESSEL ARRIVED AND WORKING | VESSEL ARRIVED AND WORKING | BUCKET TO BE COLLECTED FROM PORT | BUCKET TO BE COLLECTED FROM PORT TOMORROW | COLLECTING BUCKET FROM PORT TODAY | BUCKET AT BONDED FACILITY - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING NEXT WEEK | LOADING WEDNESDAY 04-09-2024 | LOADING WEDNESDAY 04-09-2024 | LOADING TODAY | HOWICK ENROUTE BEIT BRIDGE BORDER | DISPATCHING JOHANNESBURG TO PROCEED TO BEIT BRIDGE BORDER | MUSINA TO PROCEED TO BEIT BRIDGE BORDER | MUSINA AWAITING CROSS BORDER PERMIT | BEIT BRIDGE ZIM SIDE | MASVINGO ENROUTE HARARE | HARARE TO DISPATCH FOR CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE - AWAITING ZAMBIAN PERMIT | KAPIRI MPOSHI ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | DISPATCHING FROM WHISKEY FRO SITE | LIKASI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 28-09-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - ABNORMAL LOAD 1 - FRAME AR (LH) P/N 5129196 | 9,000 x 2,200 x 2,100 - 49500KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | BJ30GWZN - PH221 | BK71FYZN / BK71HCZN | 2409DSI2585-1 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 04-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 18-10-2024 | 18-10-2024 | 21-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2025 | 28-10-2024 | MOKAMBO 30-10-2024 | MOKAMBO 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD | LOADED FROM PORT - AWAITING BV NUMBER | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | WARDEN ENROUTE BEIT BRIDGE BORDER | MOOKGOPHONG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE IN QUE TO CROSS TO ZIM SIDE | CHIVI ZIM ENROUTE HARARE | MAKONDE ZIM ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | LUANSHA ENROUTE MOKAMBO BORDER | KITWE AWAITING DIESEL TO REFUEL | MUFULIRA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE - AWAITING CUSTOMS OFFICER - DOCUMENTS RECEIVED | CONNEX KOLWEZI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - ABNORMAL LOAD 2 - FRAME AR (RH) P/N 5129918 | 9,000 x 2,200 x 2,100 - 49500KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | BF94MDZN - PH220 | BJ29XJZN / BJ30BBZN | 2409DSI2585-2 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 04-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 18-10-2024 | 18-10-2024 | 21-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2025 | 28-10-2024 | MOKAMBO 30-10-2024 | MOKAMBO 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD | LOADED FROM PORT - AWAITING BV NUMBER | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | VILLIERS ENROUTE BEIT BRIDGE | MOOKGOPHONG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE IN QUE TO CROSS TO ZIM SIDE | CHIVI ZIM ENROUTE HARARE | MAKONDE ZIM ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | LUANSHA ENROUTE MOKAMBO BORDER | KITWE AWAITING DIESEL TO REFUEL | MUFULIRA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE - AWAITING CUSTOMS OFFICER - DOCUMENTS RECEIVED | CONNEX KOLWEZI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - ABNORMAL LOAD 3 - CAR BODY AR (P/N5126830) | 6,730 x 3,870 x 2,440 - 50645KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | BC02BWZN - PH218 | ND822365 / ND821906 | 2409DSI2585-3 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 04-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 18-10-2024 | 18-10-2024 | 21-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2025 | 28-10-2024 | MOKAMBO 30-10-2024 | MOKAMBO 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD | LOADED FROM PORT - AWAITING BV NUMBER | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | HARRISMITH ENROUTE BEIT BRIDGE | PIENAARSRIVIER ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE IN QUE TO CROSS TO ZIM SIDE | CHIVI ZIM ENROUTE HARARE | MAKONDE ZIM ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | LUANSHA ENROUTE MOKAMBO BORDER | KITWE AWAITING DIESEL TO REFUEL | MUFULIRA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE - AWAITING CUSTOMS OFFICER - DOCUMENTS RECEIVED | CONNEX KOLWEZI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - ABNORMAL LOAD 5 - MODULE AR POWER (P/N 5154039) - N8R00277 (RH) & N8R00275 (LH) | 7,140 x 4,550 x 4,400 - 48591KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | BJ59ZYZN - PH210 | BN39FRZN / BN54JSZN | 2409DSI2585-5 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 04-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 18-10-2024 | 18-10-2024 | 21-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2025 | 28-10-2024 | MOKAMBO 30-10-2024 | MOKAMBO 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD | LOADED FROM PORT - AWAITING BV NUMBER | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | VAN REENEN ENROUTE BEIT BRIDGE | MOOKGOPHONG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | CHIVI ZIM ENROUTE HARARE | MAKONDE ZIM ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | LUANSHA ENROUTE MOKAMBO BORDER | KITWE AWAITING DIESEL TO REFUEL | MUFULIRA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE - AWAITING CUSTOMS OFFICER - DOCUMENTS RECEIVED | CONNEX KOLWEZI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - ABNORMAL LOAD 6 - RISER AR (P/N 5116258) COOLER AR (P/N 5149098) CAB | 4,210 x 2,530 x 3,700 - 6884KGS 4,100 x 2,010 x 3,850 - 10901KGS 3,581 x 2,760 x 2,940 - 3581KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | ND919947 - PH206 | BL00YBZN | 2409DSI2585-6 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 04-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 17-10-2024 | 18-10-2024 | 21-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2025 | 28-10-2024 | MOKAMBO 30-10-2024 | MOKAMBO 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD | LOADED FROM PORT - AWAITING BV NUMBER | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | BETHAL ENROUTE BEIT BRIDGE | APPROCHING BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE IN QUE TO CROSS TO ZIM SIDE | GUTU ZIM ENROUTE HARARE | HURUNGWE ZIM ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | LUANSHA ENROUTE MOKAMBO BORDER | KITWE AWAITING DIESEL TO REFUEL | MUFULIRA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE - AWAITING CUSTOMS OFFICER - DOCUMENTS RECEIVED | CONNEX KOLWEZI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - ABNORMAL LOAD 7 - COUNTERWEIGHT AR LOWER | 7,000 x 1,580 x 1,750 - 36055KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | BJ60GTZN - PH211 | BN39DMZN / BN54MHZN | 2409DSI2585-7 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 04-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 18-10-2024 | 18-10-2024 | 21-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2025 | 28-10-2024 | MOKAMBO 30-10-2024 | MOKAMBO 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD | LOADED FROM PORT - AWAITING BV NUMBER | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | VILLIERS ENROUTE BEIT BRIDGE | MOOKGOPHONG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE IN QUE TO CROSS TO ZIM SIDE | CHIVI ZIM ENROUTE HARARE | HURUNGWE ZIM ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | LUANSHA ENROUTE MOKAMBO BORDER | KITWE AWAITING DIESEL TO REFUEL | MUFULIRA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE - AWAITING CUSTOMS OFFICER - DOCUMENTS RECEIVED | CONNEX KOLWEZI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - ABNORMAL LOAD 8 - BOOM AR (P/N 5149097) | 9,064 x 3,060 x 2,913 - 50824KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | BJ30JHZN - PH222 | BK79LJZN / BK79JYZN | 2409DSI2585-8 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 04-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 18-10-2024 | 18-10-2024 | 21-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2025 | 28-10-2024 | MOKAMBO 30-10-2024 | MOKAMBO 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD TOMORROW AND SATURDAY | LOADED FROM PORT - AWAITING BV NUMBER | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | VILLIERS ENROUTE BEIT BRIDGE | MOOKGOPHONG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE IN QUE TO CROSS TO ZIM SIDE | CHIVI ZIM ENROUTE HARARE | MAKONDE ZIM ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | LUANSHA ENROUTE MOKAMBO BORDER | KITWE AWAITING DIESEL TO REFUEL | MUFULIRA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE - AWAITING CUSTOMS OFFICER - DOCUMENTS RECEIVED | CONNEX KOLWEZI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - ABNORMAL LOAD 9 - HYDRAULIC FOR BOOM | 5,590 x 2,440 x 2,230 - 6415KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | AEZ7782 |  | 2409DSI2585-16 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 04-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 22-10-2024 | 23-10-2024 | 25-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2024 | 27-10-2024 | 29-10-2024 | 29-10-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | MOKAMBO 04-11-2024 | MOKAMBO 04-11-2024 | 04-11-2024 | 04-11-2024 | 04-11-2024 | 04-11-2024 | 04-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD TOMORROW AND SATURDAY | LOADING TODAY | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | DURBAN TO DISPATCH TODAY | TO DISPATCH DURBAN ON MONDAY | DISPATCHING DURBAN TODAY | ENROUTE JOHANNESBURG | VILLIERS ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG WAITING ABNORMAL PERMIT | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE BORDER | HARARE ENROUTE CHIRUNDU | CHINHOYI ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER ZAMBIA SIDE AWAITING RELEASE | MOKAMBO BORDER CLEARING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - LINK LOAD 1 - TRACK 1 (P/N 5120710) TRACK 1 (P/N5120710) TRACK 1 (P/N 5120710) TRACK 2 (P/N 5120711) | 6,400 x 1,400 x 0,330 - 9827KGS 6,400 x 1,400 x 0,300 - 9827KGS 6,400 x 1,400 x 0,300 - 9827KGS 1,900 x 1,600 x 0,600 - 2267KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | KB53MBGP - J92 | DD83NXGP / DD83NZGP | 2409DSI2858-9 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 06-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-204 | 16-10-2024 | 17-10-2024 | 18-10-2024 | 21-10-2024 | 21-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 24-10-2024 | 25-10-2024 | 26-10-2024 | 26-10-2024 | 26-10-2024 | 01-11-2024 | 02-11-2024 | 04-11-2024 | 04-11-2024 | 05-11-2024 | 05-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD TOMORROW AND SATURDAY | LOADED FROM PORT - AWAITING BV NUMBER | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | BELA BELA ENROUTE BEIT BRIDGE BORDER | POLOKWANE ENROUTE BEIT BRIDGE BORDER | MUSINA ENROUTE BEIT BRIDGE BORDER FOR CLEARANCE | HARARE ENROUTE CHIRUNDU | BANKET ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAM SIDE CLEARING | KAFUE ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE AWAITING CLEARANCE | KASUMBALESA ZAM SIDE AWAITING CLEARANCE | KASUMBALESA ZAM SIDE AWAITING CLEARANCE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | WHISKEY AWAITING RELEASE | GUBA ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - LINK LOAD 2 - TRACK 1 (P/N 5120710) TRACK 1 (P/N 5120710) TRACK 1 (P/N 5120710) TRACK 2 (P/N 5120711) | 6,400 x 1,400 x 0,330 - 9827KGS 6,400 x 1,400 x 0,300 - 9827KGS 6,400 x 1,400 x 0,300 - 9827KGS 1,900 x 1,600 x 0,600 - 2267KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | KX69DXGP - J112 | DD83NLGP / DD83NPGP | 2409DSI2585-10 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 06-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 17-10-2024 | 18-10-2024 | 18-10-2024 | 18-10-2024 | 19-10-2024 | 19-10-2024 | 20-10-2024 | 21-10-2024 | 24-10-2024 | 25-10-2024 | 27-10-2024 | 27-10-2024 | 28-10-2024 | 01-11-2024 | 02-11-2024 | 04-11-2024 | 04-11-2024 | 05-11-2024 | 05-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD TOMORROW AND SATURDAY | LOADING TODAY | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | MANTSOLE ENROUTE BEIT BRIDGE BORDER | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING | CHIRUNDU ZAM SIDE CLEARING | KAFUE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE AWAITING CLEARANCE | KASUMBALESA DRC SIDE AWAITING CLEARANCE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | WHISKEY AWAITING RELEASE | FUNGURUME ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - LINK LOAD 3 - BOLTS, BOLTS 2, EMERGENCY SHUT DOWN, STICK CYLINDER 1, (PN5892696) STICK CYLINDER 2, (PN5892696) SHOVEL CYLINDER 1 (PN 5892696) SHOVEL CYLINDER 2 (PN 5892696) | 3,000 x 1,650 x 0,800 - 4594KGS 1,700 X 1,500 X 1,100 - 1186KGS 1,620 x 1,450 x 0,930 - 218KGS 5,360 x 0,740 x 1,160 - 3148KGS 5,360 x 0,740 x 1,160 - 3148KGS 4,900 x 0,800 x 1,070 - 3148KGS 4,900 x 0,800 x 1,070 - 3148KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | KB53KGGP - J93 | DD83NGGP / DD83NFGP | 2409DSI2585-11 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 06-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 16-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 19-10-2024 | 19-10-2024 | 20-10-2024 | 21-10-2024 | 22-10-2024 | 22-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 01-11-2024 | 02-11-2024 | 04-11-2024 | 04-11-2024 | 05-11-2024 | 05-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD TOMORROW AND SATURDAY | LOADING TODAY / TOMORROW | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING - DAY 4 | KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 5 | KASUMBALESA DRC SIDE AWAITING CLEARANCE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | WHISKEY AWAITING RELEASE | GUBA ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - LINK LOAD 4 - STICK AR (PN 5088449), SLEWING GEAR, GREASE CONTAINERS, CATWALK, WATER COOLER 1, WATER COOLER 2 | 6,020 x 2,200 x 2,313 - 15382KGS 2,720 x 0,980 x 2,000 - 4867KGS 1,860 x 1,400 x 2,180 - 692KGS 4,400 x 2,300 x 1,500 - 2340KGS 3,160 x 2,080 x 0,800 - 1200KGS 3,160 x 2,080 x 0,800 - 1200KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | JZ76YXGP - J80 | DJ67LWGP / DJ67LTGP | 2409DSI2585-12 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 06-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 17-10-2024 | 19-10-2024 | 20-10-2024 | 21-10-2024 | 22-10-2024 | 24-10-2024 | 24-10-2024 | 27-10-2024 | 27-10-2024 | 28-10-2024 | 01-11-2024 | 02-11-2024 | 04-11-2024 | 04-11-2024 | 05-11-2024 | 05-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD TOMORROW AND SATURDAY | LOADING TODAY | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | HEIDELBERG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | HARARE ENROUTE CHIRUNDU | HURUNGUWE ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | CHIRUNDU ZAM SIDE CLEARING | KAFUE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE AWAITING CLEARANCE | KASUMBALESA DRC SIDE AWAITING CLEARANCE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | WHISKEY AWAITING RELEASE | GUBA ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - LINK LOAD 5 - AIR FILTER, SLEW RING COVER, HOSES, RETRACTABLE LADDER, EMERGENCY LADDER, BOOM CYLINDER 1 (PN 5981519) BOOM CYLINDER 2 )PN 5981519) | 3,560 x 1,700 x 1,780 - 1924KGS 2,360 x 1,320 x 1,300 - 411KGS 4,200 x 1,600 x 0,800 - 2073KGS 7,000 x 1,000 x 2,650 - 1470KGS 5,580 x 2,200 x 2,300 - 551KGS 6,480 x 0,900 x 1,200 - 4222KGS 6,480 x 0,900 x 1,200 - 4222KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | KY87BKGP - J109 | CP48VLGP / CP48VXGP | 2409DSI2585-13 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 06-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 18-10-2024 | 20-10-2024 | 20-10-2024 | 21-10-2024 | 21-10-2024 | 22-10-2024 | 22-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 01-11-2024 | 02-11-2024 | 04-11-2024 | 04-11-2024 | 05-11-2024 | 05-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD TOMORROW AND SATURDAY | LOADING TOMORROW | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | JOHANNESBURG DURBAN ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | MAKUTI ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING - DAY 4 | KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 5 | KASUMBALESA DRC SIDE AWAITING CLEARANCE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | WHISKEY AWAITING RELEASE | FUNGURUME ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - LINK LOAD 6 - HANDRAIL 1, HANDRAIL 2, CATWALK FOR BOOM, EXHAUST, 6 PKGS OF FIRE SUPPRESSION SYSTEM, 1 PKGS CONDITIONER GP | 4,860 x 1,700 x 1,500 - 610KGS 3,000 x 1,500 x 1,500 - 522KGS 4,470 x 1,960 x 1,500 - 1479KGS 3,560 x 1,700 x 1,000 - 1667KGS 4 OF 0,970 x 0,680 x 1,300 - 135KGS EACH 1 OF 1,100 x 1,100 x 0,990 - 729KGS 1 OF 1,000 x 1,000 x 1,000 - 387KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | KC44KMGP - J100 | KT40NJGP / KT40NSGP | 2409DSI2585-14 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 06-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 17-10-2024 | 17-10-2024 | 21-10-2024 | 21-10-2024 | 21-10-2024 | 24-10-2024 | 24-10-2024 | 25-10-204 | 26-10-2024 | 27-10-2024 | 27-10-2024 | 28-10-2024 | 29-10-2024 | 29-10-2024 | 01-11-2024 | 02-11-2024 | 04-11-2024 | 04-11-2024 | 05-11-2024 | 05-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD TOMORROW AND SATURDAY | LOADDING TOMORROW | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE BEIT BRIDGE | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | MASVINGO ENROUTE HARARE | MAKUTI ENROUTE CHIRUNDU | NDOLA ENROUTE KASUMBALESA | NDOLA ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE AWAITING CLEARANCE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | WHISKEY AWAITING RELEASE | FUNGURUME ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - LINK LOAD 7 - COUNTERWEIGHT AR (UPPER) PN 5120711, PIN CONDITIONER GP | 7,000 x 1,540 x 2,700 - 20000KGS 2,800 x 1,000 x 0,800 - 3056KGS 0,078 x 0,248 x 0,095 - 364KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | KX69FFGP - J110 | BV92FYGP / BV92FTGP | 2409DSI2585-15 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 07-11-2024 | 06-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 18-10-2024 | 19-10-2024 | 21-10-2024 | 22-10-2024 | 22-10-2024 | 24-10-2024 | 24-10-2024 | 25-10-2024 | 26-10-2024 | 26-10-2024 | 27-10-2024 | 27-10-2024 | 28-10-2024 | 28-10-2024 | 01-11-2024 | 02-11-2024 | 04-11-2024 | 04-11-2024 | 05-11-2024 | 05-11-2024 | 07-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD TOMORROW AND SATURDAY | LOADING TODAY | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | DURBAN TO DISPATCH TODAY | DISPATCHING DURBAN TODAY | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE BORDER | POLOKWANE ENROUTE BEIT BRIDGE | BEIT BRIDGE BORDER CLEARING | NGOMAHURU ENROUTE HARARE | LIONS DEN ENROUTE CHIRUNDU | NDOLA ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE AWAITING CLEARANCE | KASUMBALESA ZAM SIDE AWAITING CLEARANCE | KASUMBALESA ZAM SIDE AWAITING CLEARANCE | KASUMBALESA DRC SIDE AWAITING CLEARANCE & RELEASE | WHISKEY AWAITING RELEASE | FUNGURUME ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 07-11-2024
BA2768 | CAT6060FS HYDRAULIC MINING SHOVEL IN CKD FORM - ABNORMAL LOAD 4 - CHASSIS AR (P/N 5071686) | 10,600 x 3,730 x 3,470 - 65220KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 6P600128 | CAT6060E6P600128 | N8R00277 / N8R00275 | FML2409DSI2585 | COD 2024 306325 | BJ59WJZN - PH207 | BN39GLZN / BN54KRZN | 2409DSI2585-4 | VESSEL: BOSPORUS HIGHWAY Voy. 148A - ETA DURBAN: 09-10-2024 | OFFLOADED 11-12-2024 | 04-11-2024 | 14-10-2024 | BV COMPLETED | 09-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 18-10-2024 | 18-10-2024 | 21-10-2024 | 22-10-2024 | 23-10-2024 | 23-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2025 | 28-10-2024 | MOKAMBO 30-10-2024 | MOKAMBO 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | 11-11-2024 | [100 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2024 | VESSEL ARRIVED 09-10-2024 - CURRENTLY DISCHARGING CARGO - VEHICLE STANDING BY TO LOAD | LOADED FROM PORT - AWAITING BV NUMBER | LOADED - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 16-10-2024 | BV INSPECTION TO BE DONE TODAY | WARDEN ENROUTE BEIT BRIDGE BORDER | MOOKGOPHONG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE IN QUE TO CROSS TO ZIM SIDE | CHIVI ZIM ENROUTE HARARE | MAKONDE ZIM ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | LUANSHA ENROUTE MOKAMBO BORDER | KITWE AWAITING DIESEL TO REFUEL | MUFULIRA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE - AWAITING CUSTOMS OFFICER - DOCUMENTS RECEIVED | CONNEX KOLWEZI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 7 | OFFLOADED 11-12-2024 | OFFLOADED 11-12-2024
BA2760 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02227 - ABNORMAL LOAD BANJO BOX INTAKE AIR CLEANER | ABNORMAL LOAD 7,010 x 3,250 x 1,570 - 24494KGS 2,460 x 1,270 x 1,390 - 548KGS 1,570 x 1,270 x 1,720 - 471KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02227 | CAT0793DVFDB02227 | EXM00352 | FML2409DSI2599 | COD 2024 307498 | BL64MKZN | ND702944 | ND61046-1 | VESSEL: RUBY ACE Voy. 0119A - ETA DURBAN: 19-10-2024 | OFFLOADED 19-11-2024 | 15-11-2024 | 15-10-2024 | BV COMPLETE | 20-10-2024 | 28-10-2024 | MIDDELBURG 28-10-2024 | MIDDELBURG 28-10-2025 | 29-10-2024 | 29-10-2024 | 01-11-2024 | 02-11-2024 | 04-11-2024 | 05-11-2024 | 07-11-2024 | 07-11-2024 | 07-11-2024 | 08-11-2024 | 09-11-2024 | 12-11-2024 | 12-11-2024 | 14-11-2024 | 14-11-2024 | 14-11-2024 | 15-11-2024 | 19-11-2024 | [110 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | VESSEL IN AND WORKING | LOADING FROM PORT LATER TODAY OR TOMORROW MORNING | LOADING TODAY FROM PORT | LOADED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING PERMIT TO DISPATCHED MONDAY | HOWICK ENROUTE BEIT BRIDGE BORDER | KRANSKOP ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | NGUNDU ENROUTE HARARE | HARARE TO DISPATCH FOR CHIRUNDU | KAROI ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | DISPATCHED CHIRUNDU ENROUTE KAFUE | KAPIRI MPOSHE ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE | DISPATCHING KASUMBALESA DRC FOR WHISKEY | WHISKEY - AWAITING RELESAE | WHISKEY - AWAITING RELESAE - DAY 2 | WHISKEY - AWAITING RELESAE - DAY 3 | TENKE ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 19-11-2024 | OFFLOADED 19-11-2024
BA2760 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02227 - LINK LOAD SKID FUEL TANK SKID RIMS SKID RIMS SKID RIM TOPY SKID FSTRUT RH PLATFORM BOX HARDWARE BOX PIPING | LINK LOAD 2,430 x 1,650 x 2,230 - 1597KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 0,91 - 1950KGS 3,300 x 1,520 x 1,520 - 6506KGS 4,260 x 2,510 x 2,790 - 2676KGS 2,280 x 1,210 x 0,450 - 511KGS 2,180 x 0,700 x 0,500 - 295KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02227 | CAT0793DVFDB02227 | EXM00352 | FML2409DSI2599 | COD 2024 307498 | BCF3321ZM | BCA4052T / BCA4053T | 2409DSI2599-1 | VESSEL: RUBY ACE Voy. 0119A - ETA DURBAN: 19-10-2024 | OFFLOADED 19-11-2024 | 16-11-2024 | 15-10-2024 | BV COMPLETE | 20-10-2024 | 24-10-2024 | 24-10-2024 | 24-10-2024 | 25-10-2024 | 26-10-2024 | 31-10-2024 | 31-10-2024 | 01-11-2024 | 01-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | 09-11-2024 | 11-11-2024 | 14-11-2024 | 14-11-2024 | 15-11-2024 | 15-11-2024 | 16-11-2024 | 16-11-2024 | 19-11-2024 | [110 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | VESSEL IN AND WORKING | LOADING TODAY FROM PORT | LOADING TODAY FROM PORT | LOADED - BV INSPECTION BOOKED FOR TODAY | BELA BELA ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING - AWAITING RELEASE | RUTENGA ENROUTE HARARE | KAROI ENROUTE CHIRUNDU | NDOLA - BUSY WITH MAINTENANCE CHECKS | NDOLA - BUSY WITH MAINTENANCE CHECKS | NDOLA - FINALIZING MAINTENANCE CHECKS | DISPATCHING NDOLA TODAY | ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 23 | WHISKEY - AWAITING RELESAE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 19-11-2024 | OFFLOADED 19-11-2024
BA2760 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02227 - LINK LOAD SKID CAB SKID BODY SKID RIM TROPHY SKID OUTRIGGERS SKID HANDRAILS SKID FSTRUT | LINK LOAD 3,250 x 2,260 x 1,930 - 2514KGS 2,130 x 0,760 x 1,290 - 1125KGS 1,820 x 1,820 x 0,910 - 1950KGS 2,460 x 2,230 x 0,760 - 1288KGS 3,960 x 2,260 x 1,880 - 1515KGS 3,300 x 1,520 x 1,520 - 6505KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02227 | CAT0793DVFDB02227 | EXM00352 | FML2409DSI2599 | COD 2024 307498 | BCE5039ZM | BCA4540T / BCA4541T | 2409DSI2599-2 | VESSEL: RUBY ACE Voy. 0119A - ETA DURBAN: 19-10-2024 | OFFLOADED 19-11-2024 | 16-11-2024 | 15-10-2024 | BV COMPLETE | 20-10-2024 | 24-10-2024 | 24-10-2024 | 24-10-2024 | 25-10-2024 | 26-10-2024 | 31-10-2024 | 31-10-2024 | 01-11-2024 | 01-11-2024 | 02-11-2024 | 02-11-2024 | 03-11-2024 | 09-11-2024 | 11-11-2024 | 14-11-2024 | 14-11-2024 | 15-11-2024 | 15-11-2024 | 16-11-2024 | 16-11-2024 | 19-11-2024 | [110 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | VESSEL IN AND WORKING | LOADING TODAY FROM PORT | LOADING TODAY FROM PORT | LOADED - BV INSPECTION BOOKED FOR TODAY | BELA BELA ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING - AWAITING RELEASE | RUTENGA ENROUTE HARARE | MAKUTI ENROUTE CHIRUNDU | NDOLA - BUSY WITH MAINTENANCE CHECKS | NDOLA - BUSY WITH MAINTENANCE CHECKS | NDOLA - FINALIZING MAINTENANCE CHECKS | DISPATCHING NDOLA TODAY | ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 23 | WHISKEY - AWAITING RELESAE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 19-11-2024 | OFFLOADED 19-11-2024
BA2761 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02228 - ABNORMAL LOAD CHASSIS | ABNORMAL LOAD 10,080 x 3,880 x 3,50 - 43985KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02228 | CAT0793DAFDB02228 | EXM00337 | FML2409DSI2600 | COD 2024 307498 | ND705348 | ND926113 | ND61047 | VESSEL: RUBY ACE Voy. 0119A - ETA DURBAN: 19-10-2024 | OFFLOADED 19-11-2024 | 15-11-2024 | 15-10-2024 | BV COMPLETE | 20-10-2024 | 25-10-2024 | 25-10-2024 | 28-10-2024 | 28-10-2024 | 28-10-2024 | 01-11-2024 | 02-11-2024 | 04-11-2024 | 04-11-2024 | 05-11-2024 | 05-11-2024 | 07-11-2024 | 08-11-2024 | 08-11-2024 | 12-11-2024 | 12-11-2024 | 14-11-2024 | 14-11-2024 | 14-11-2024 | 15-11-2024 | 19-11-2024 | [110 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | VESSEL IN AND WORKING | LOADING FROM PORT LATER TODAY OR TOMORROW MORNING | LOADING TODAY FROM PORT | LOADED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING PERMIT TO DISPATCHED MONDAY | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | HARARE TO DISPATCH FOR CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | LUSAKA ENROUTE KASUMBALESA BORDER | DISPATCHING LUSAKA | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAM SIDE | DISPATCHING KASUMBALESA DRC FOR WHISKEY | WHISKEY - AWAITING RELESAE | WHISKEY - AWAITING RELESAE - DAY 2 | WHISKEY - AWAITING RELESAE - DAY 3 | TENKE ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 19-11-2024 | OFFLOADED 19-11-2024
BA2761 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02228 - ABNORMAL LOAD BANJO BOX INTAKE AIR CLEANER | ABNORMAL LOAD 7,010 x 3,250 x 1,570 - 24494KGS 2,460 x 1,270 x 1,390 - 548KGS 1,570 x 1,270 x 1,720 - 471KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02228 | CAT0793DAFDB02228 | EXM00337 | FML2409DSI2600 | COD 2024 307498 | ND730794 | BJ85MZZN | NA61047-1 | VESSEL: RUBY ACE Voy. 0119A - ETA DURBAN: 19-10-2024 | OFFLOADED 19-11-2024 | 15-11-2024 | 15-10-2024 | BV COMPLETE | 20-10-2024 | 25-10-2024 | 25-10-2024 | 28-10-2024 | 28-10-2024 | 28-10-2024 | 01-11-2024 | 02-11-2024 | 04-11-2024 | 04-11-2024 | 07-11-2024 | 07-11-2024 | 07-11-2024 | 08-11-2024 | 08-11-2024 | 12-11-2024 | 12-11-2024 | 14-11-2024 | 14-11-2024 | 14-11-2024 | 15-11-2024 | 19-11-2024 | [110 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | VESSEL IN AND WORKING | LOADING FROM PORT LATER TODAY OR TOMORROW MORNING | LOADING TODAY FROM PORT | LOADED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING PERMIT TO DISPATCHED MONDAY | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | NGUNDU ENROUTE HARARE | HARARE TO DISPATCH FOR CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | DISPATCHED CHIRUNDU ENROUTE KAFUE | KAPIRI MPOSHE ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE | DISPATCHING KASUMBALESA DRC FOR WHISKEY | WHISKEY - AWAITING RELESAE | WHISKEY - AWAITING RELESAE - DAY 2 | WHISKEY - AWAITING RELESAE - DAY 3 | TENKE ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 19-11-2024 | OFFLOADED 19-11-2024
BA2761 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02228 - LINK LOAD SKID CAB SKID RIMS SKID RIMS SKID FSTRUT SKID FTRUT SKID OUTRIGGERS SKID HANDRAILS | LINK LOAD 3,250 x 2,260 x 1,93 - 2514KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 0,91 - 1950KGS 3,300 x 1,520 x 1,520 - 6506KGS 3,300 x 1,520 x 1,520 - 6506KGS 2,460 x 2,230 x 0,760 - 1288KGS 3,960 x 2,260 x 1,880 - 1515KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02228 | CAT0793DAFDB02228 | EXM00337 | FML2409DSI2600 | COD 2024 307498 | BCG6028ZM | AEB1922ZM / AEB1923ZM | 2409DSI2600-1 | VESSEL: RUBY ACE Voy. 0119A - ETA DURBAN: 19-10-2024 | OFFLOADED 19-11-2024 | 16-11-2024 | 15-10-2024 | BV COMPLETE | 20-10-2024 | 24-10-2024 | 24-10-2024 | 24-10-2024 | 25-10-2024 | 26-10-2024 | 31-10-2024 | 31-10-2024 | 01-11-2024 | 01-11-2024 | 02-11-2024 | 02-11-2024 | 05-11-2024 | 11-11-2024 | 11-11-2024 | 14-11-2024 | 14-11-2024 | 15-11-2024 | 15-11-2024 | 16-11-2024 | 16-11-2024 | 19-11-2024 | [110 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | VESSEL IN AND WORKING | LOADING TODAY FROM PORT | LOADED YESTERDAY - AWATING BV INSPECTION - INSPECTION BOOKED FOR TOMORROW | LOADED - BV INSPECTION BOOKED FOR TODAY | BELA BELA ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING - AWAITING RELEASE | RUTENGA ENROUTE HARARE | KAROI ENROUTE CHIRUNDU | LUMANO ENROUTE NDOLA | LUSAKA ENROUTE NDOLA | NDOLA - BUSY WITH MAINTENANCE CHECKS | DISPATCHING NDOLA TODAY | ENROUTE KASUMBALESA BORDER | TO DISPATCH NDOLA FOR KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | WHISKEY - AWAITING RELESAE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 19-11-2024 | OFFLOADED 19-11-2024
BA2761 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02228 - LINK LOAD RH PLATFORM SKID FUEL TANK SKID RIM TROPHY SKID RIM TROPHY BOX PIPING BOX HARDWARE BOX BODY | LINK LOAD 4,260 x 2,510 x 2,790 - 2676KGS 2,430 x 1,650 x 2,230 - 1597KGS 1,820 x 1,820 x 0,910 - 1950KGS 2,180 x 0,700 x 0,500 - 295KGS 2,280 x 1,210 x 0,450 - 511KGS 2,130 x 0,760 x 1,290 - 1125KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02228 | CAT0793DAFDB02228 | EXM00337 | FML2409DSI2600 | COD 2024 307498 | BCG6143ZM | BCA4051T / BCA4057T | 2409DSI2600-2 | VESSEL: RUBY ACE Voy. 0119A - ETA DURBAN: 19-10-2024 | OFFLOADED 19-11-2024 | 16-11-2024 | 15-10-2024 | BV COMPLETE | 20-10-2024 | 24-10-2024 | 24-10-2024 | 24-10-2024 | 25-10-2024 | 26-10-2024 | 31-10-2024 | 31-10-2024 | 01-11-2024 | 02-11-2024 | 03-11-2024 | 03-11-2024 | 04-11-2024 | 09-11-2024 | 11-11-2024 | 14-11-2024 | 14-11-2024 | 15-11-2024 | 15-11-2024 | 16-11-2024 | 16-11-2024 | 19-11-2024 | [110 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | VESSEL IN AND WORKING | LOADING TODAY FROM PORT | LOADED YESTERDAY - AWATING BV INSPECTION - INSPECTION BOOKED FOR TOMORROW | LOADED - BV INSPECTION BOOKED FOR TODAY | BELA BELA ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING - AWAITING RELEASE | RUTENGA ENROUTE HARARE | KAROI ENROUTE CHIRUNDU | LUSAKA ENROUTE NDOLA | NDOLA - BUSY WITH MAINTENANCE CHECKS | NDOLA - BUSY WITH MAINTENANCE CHECKS | DISPATCHING NDOLA TODAY | ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | WHISKEY - AWAITING RELESAE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 19-11-2024 | OFFLOADED 19-11-2024
BA2760 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02227 - ABNORMAL LOAD CHASSIS | ABNORMAL LOAD 10,080 x 3,880 x 3,50 - 43985KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02227 | CAT0793DVFDB02227 | EXM00352 | FML2409DSI2599 | COD 2024 307498 | ND754967 | ND654346 / ND526680 | ND61046 | VESSEL: RUBY ACE Voy. 0119A - ETA DURBAN: 19-10-2024 | OFFLOADED 29-11-2024 | 28-11-2024 | 15-10-2024 | BV COMPLETE | 20-10-2024 | 28-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 30-10-2024 | 04-11-2024 | 05-11-2024 | 08-11-2024 | 13-11-2024 | 14-11-2024 | 15-11-2024 | 16-11-2024 | 16-11-2024 | 19-11-2024 | 19-11-2024 | 26-11-2024 | 26-11-2024 | 27-11-2024 | 27-11-2024 | 29-11-2024 | [110 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2024 | VESSEL IN AND WORKING | LOADING FROM PORT LATER TODAY OR TOMORROW MORNING | LOADING TODAY FROM PORT | LOADED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING PERMIT TO DISPATCHED MONDAY | CAMPERDOWN ENROUTE BEIT BRIDGE BORDER | HEIDELBERG ENROUTE BEIT BRIDGE BORDER | BAOBOB TOLL ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | HARARE TO DISPATCH FOR CHIRUNDU | CHENOYI ENROUTE CHURUNDU | LIONSDEN ENROUTE CHURUNDU | DISPATCHING LIONSDEN TODAY FOR CHIRUNDU | APROCHING CHIRUNDU BORDER | CHIRUNDU ZAM SIDE AWAITING RELEASE | CHIRUNDU ZAM SIDE AWAITING RELEASE | CHIRUNDU ZAM SIDE AWAITING PERMIT | DISPATCHING CHIRUNDU FOR KASUMBALESA BORDER | NADUGA ENROUTE KAFUE | KAFUE WEIGHBRIDGE | KASUMBALESA ZAMBIAN SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELESAE | WHISKEY AWAITING RELESAE - DAY 2 - SYDONIA ACCOUNT BLOCKED | WHISKEY AWAITING RELESAE - DAY 3 - SYDONIA ACCOUNT BLOCKED | WHISKEY AWAITING RELESAE - DAY 6 - PLEASE ASSIST WITH RELEASE FROM WHISKEY | WHISKEY AWAITING RELESAE - DAY 7 - PLEASE ASSIST WITH RELEASE FROM WHISKEY | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 29-11-2024 | OFFLOADED 29-11-2024
BA2762 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02229 - ABNORMAL LOAD BANJO BOX INTAKE AIR CLEANER FIRE SUPPRESSION SYSTEM (2PKGS) | ABNORMAL LOAD 7,010 x 3,250 x 1,570 - 24494KGS 2,460 x 1,270 x 1,390 - 548KGS 1,570 x 1,270 x 1,720 - 471KGS 1,00 x 1,00 x 0,990 - 599KGS 0,97 x 0,68 x 1,300 - 135KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02229 | CAT0793DLFDB02229 | EXM00351 | FML2410DSI2602 | COD 2024 307498 | BS34MLZN - PH159 | BB10PCZN | 2410DSI2602-2 | OFFLOADED 18-12-2024 | 16-12-2024 | 11-12-2024 | 15-10-2024 | BV NUMBER RECEIVED | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-2024 | 28-11-2024 | 03-12-2024 | 03-12-2024 | 04-12-2024 | 04-12-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 11-12-2024 | 12-12-2024 | 15-12-2024 | 15-12-2024 | 15-12-2024 | 16-12-2024 | [132 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | MASVINGO ENROUTE HARARE | MAKONDE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER AND WHISKEY | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 18-12-2024 | OFFLOADED 18-12-2024 | OFFLOADED 18-12-2024
BA2763 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02230 - ABNORMAL LOAD BANJO BOX INTAKE AIR CLEANER FIRE SUPPRESSION SYSTEM (2PKGS) | ABNORMAL LOAD 7,010 x 3,250 x 1,570 - 24494KGS 2,460 x 1,270 x 1,390 - 548KGS 1,570 x 1,270 x 1,720 - 471KGS 1,00 x 1,00 x 0,990 - 599KGS 0,97 x 0,68 x 1,300 - 135KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02230 | CAT0793DVFDB02230 | EXM00317 | FML2410DSI2603 | COD 2024 307498 | BS34MZZN - PH157 | BX75ZDZN | 2410DSI2603-2 | OFFLOADED 18-12-2024 | 16-12-2024 | 11-12-2024 | 15-10-2024 | BV NUMBER RECEIVED | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-2024 | 29-11-2024 | 02-12-2024 | 02-12-2024 | 02-12-2024 | 03-12-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 11-12-2024 | 12-12-2024 | 15-12-2024 | 15-12-2024 | 15-12-2024 | 16-12-2024 | [132 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | MOKHADO ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER AND WHISKEY | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 18-12-2024 | OFFLOADED 18-12-2024 | OFFLOADED 18-12-2024
BA2764 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02231 - ABNORMAL LOAD BANJO BOX INTAKE AIR CLEANER FIRE SUPPRESSION SYSTEM (2PKGS) | ABNORMAL LOAD 7,010 x 3,250 x 1,570 - 24494KGS 2,460 x 1,270 x 1,390 - 548KGS 1,570 x 1,270 x 1,720 - 471KGS 1,00 x 1,00 x 0,990 - 599KGS 0,97 x 0,68 x 1,300 - 135KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02231 | CAT0793DAFDB02231 | EXM00353 | FML2410DSI2604 | COD 2024 307498 | BM47VKZN - PH169 | ND133379 | 2410DSI2604-2 | OFFLOADED 18-12-2024 | 16-12-2024 | 11-12-2024 | 15-10-2024 | BV NUMBER RECEIVED | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-2024 | 28-11-2024 | 03-12-2024 | 03-12-2024 | 04-12-2024 | 04-12-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 11-12-2024 | 12-12-2024 | 15-12-2024 | 15-12-2024 | 15-12-2024 | 16-12-2024 | [132 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | MASVINGO ENROUTE HARARE | MAKONDE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER AND WHISKEY | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 18-12-2024 | OFFLOADED 18-12-2024 | OFFLOADED 18-12-2024
BA2764 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02231 - LINK LOAD SKID FUEL TANK SKID RIMS SKID RIMS SKID RIM TOPY SKID FSTRUT RH PLATFORM BOX HARDWARE BOX PIPING | LINK LOAD 2,430 x 1,650 x 2,230 - 1597KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 0,91 - 1950KGS 3,300 x 1,520 x 1,520 - 6506KGS 4,260 x 2,510 x 2,790 - 2676KGS 2,280 x 1,210 x 0,450 - 511KGS 2,180 x 0,700 x 0,500 - 295KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02231 | CAT0793DAFDB02231 | EXM00353 | FML2410DSI2604 | COD 2024 307498 | KB12WDGP - J90 | XML886GP / XML887GP | 2410DSI2604-3 | OFFLOADED 18-12-2024 | 16-12-2024 | 11-12-2021 | 15-10-2024 | BV NUMBER RECEIVED | 19-11-2024 | 26-11-2024 | 27-11-2024 | 29-11-2024 | 30-11-2024 | 30-11-2024 | 04-12-2024 | 05-12-2024 | 05-12-2024 | 06-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | 09-12-2024 | 09-12-2024 | 11-12-2024 | 12-12-2024 | 13-12-2024 | 13-12-2024 | 14-12-2024 | 15-12-2024 | [132 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | JOHANNESBURG TO DISPATCH FOR BEIT BRIDGE BORDER | JOHANNESBURG UNDER ROUTINE MAINTENANCE TO DISPATCH FOR BEIT BRIDGE BORDER ONCE DONE | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE AWAITING RELEASE | KWEKWE ERNOUTE HARARE | CHIRUNDU BORDER ZIM SIDE | KABWE ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAMBIA SIDE CLEARING - ESTIMATED ETA ON SITE 15-12-2024 - IF NO DELAYS AT BORDER AND WHIKSEY | KASUMBALESA BORDER DRC SIDE AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 18-12-2024 | OFFLOADED 18-12-2024 | OFFLOADED 18-12-2024
BA2762 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02229 - ABNORMAL LOAD CHASSIS | ABNORMAL LOAD 10,080 x 3,880 x 3,50 - 43985KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02229 | CAT0793DLFDB02229 | EXM00351 | FML2410DSI2602 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BJ59XNZN - PH208 | BL01DGZN | 2410DSI2602-1 | OFFLOADED 19-12-2024 | 16-12-2024 | 11-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 29-11-2024 | 29-11-2024 | 02-12-2024 | 02-12-2024 | 03-12-2024 | 04-12-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 11-12-2024 | 12-12-2024 | 15-12-2024 | 15-12-2024 | 15-12-2024 | 16-12-2024 | 19-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | BELA BELA ENROUTE BEIT BRIDGE BORDER | POLOKWANE ENORUTE BEIT BRIDGE BORDER | CHIVI ZIM ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | HURUNGWE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE - AWAITING RELEASE | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER AND WHISKEY | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | ON SITE WAITING TO OFFLOAD - DAY 5 – Please assist with offloading | OFFLOADED 19-12-2024
BA2763 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02230 - ABNORMAL LOAD CHASSIS | ABNORMAL LOAD 10,080 x 3,880 x 3,50 - 43985KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02230 | CAT0793DVFDB02230 | EXM00317 | FML2410DSI2603 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BF94MDZN - PH220 | BJ29XJZN / BJ30BBZN | 2410DSI2603-1 | OFFLOADED 19-12-2024 | 16-12-2024 | 11-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-2024 | 28-11-2024 | 02-12-2024 | 02-12-2024 | 03-12-2024 | 03-12-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 12-12-2024 | 12-12-2024 | 16-12-2024 | 16-12-2024 | 16-12-2024 | 16-12-2024 | 19-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | MOOKGOPONG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | CHIVI ZIM ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER AND WHISKEY | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 3 | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 1 | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 3 – Please assist with offloading | OFFLOADED 19-12-2024
BA2764 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02231 - ABNORMAL LOAD CHASSIS | ABNORMAL LOAD 10,080 x 3,880 x 3,50 - 43985KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02231 | CAT0793DAFDB02231 | EXM00353 | FML2410DSI2604 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BL01BKZN - PH165 | BW88SKGP | 2410DSI2604-1 | OFFLOADED 26-12-2024 | 19-12-2024 | 13-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 02-12-2024 | 04-12-2024 | 05-12-2024 | 06-12-2024 | 07-12-2024 | 08-12-2024 | 10-12-2024 | 11-12-2024 | 11-12-2024 | 12-12-2024 | MOKAMBO 12-12-2024 | MOKAMBO 15-12-2024 | 15-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 20-12-2024 | 26-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | PIENAARS RIVIER ENROUTE BEIT BRIDGE BORDER | POLOKWANE ENORUTE BEIT BRIDGE BORDER | POLOKWANE AWAITING ABNORMAL PERMIT BEFORE DSPATCHING FOR BEIT BRIDGE BORDER | DISPATCHED POLOKWANE ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER ZIM SIDE | MWENEZI ENROUTE HARARE | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE AWAITING DOCUMENTS - ESTIMATED ETA ON SITE 16-12-2024 IF NO FURTHER DELAYS AT THE BORDERS | LUSAKA ENROUTE MOKAMBO BORDER | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 1 | WHISKEY AWAITING RELESE - DAY 2 | WHISKEY AWAITING RELESE - DAY 3 | WHISKEY AWAITING RELESE - DAY 4 | DISPATCHED WHISKEY ENROUTE KOLWEZI | ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 26-12-2024 | OFFLOADED 26-12-2024
BA2766 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02233 - ABNORMAL LOAD CHASSIS | ABNORMAL LOAD 10,080 x 3,880 x 3,50 - 43985KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02233 | CAT0793DHFDB02233 | EXM00355 | FML2411DSI2620 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BC01XZZN - PH219 | BJ29WGZN / BJ29YRZN | 2411DSI2620-1 | OFFLOADED 26-12-2024 | 20-12-2024 | 17-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 27-11-2204 | 29-11-2024 | 29-11-2024 | 02-12-2024 | 03-12-2024 | 03-12-2024 | 04-12-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 18-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 20-12-2024 | 26-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | MOOKGOPONG ENROUTE BEIT BRIDGE BORDER | POLOKWANE ENORUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER ZIM SIDE | HARARE ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 3 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 4 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 7 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 8 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 9 | WHISKEY AWAITING RELEASE - DAY 1 | ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 26-12-2024 | OFFLOADED 26-12-2024
BA2766 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02233 - ABNORMAL LOAD BANJO BOX INTAKE AIR CLEANER FIRE SUPPRESSION SYSTEM (2PKGS) | ABNORMAL LOAD 7,010 x 3,250 x 1,570 - 24494KGS 2,460 x 1,270 x 1,390 - 548KGS 1,570 x 1,270 x 1,720 - 471KGS 1,00 x 1,00 x 0,990 - 599KGS 0,97 x 0,68 x 1,300 - 135KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02233 | CAT0793DHFDB02233 | EXM00355 | FML2411DSI2620 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BM47VRGP - PH168 | ND140841 | 2411DSI2620-2 | OFFLOADED 26-12-2024 | 19-12-2024 | 11-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-2024 | 28-11-2024 | 03-12-2024 | 03-12-2024 | 04-12-2024 | 04-12-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 14-12-2024 | 14-12-204 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 20-12-2024 | 26-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE | MASVINGO ENROUTE HARARE | MAKONDE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 3 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 4 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | DISPATCHED WHISKEY ENROUTE KOLWEZI | ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 26-12-2024 | OFFLOADED 26-12-2024
BA2767 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02234 - ABNORMAL LOAD CHASSIS | ABNORMAL LOAD 10,080 x 3,880 x 3,50 - 43985KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02234 | CAT0793DEFDB02234 | EXM00354 | FML2411DSI2621 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | ND673267 - PH184 | ND710695 | 2411DSI2621-1 | OFFLOADED 26-12-2024 | 19-12-2024 | 17-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-20204 | 28-11-2024 | 02-12-2024 | 02-12-2024 | 04-12-2024 | 04-12-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 18-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 20-12-2024 | 26-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | MOOKGOPONG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | CHIVI ZIM ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | HURUNGWE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 3 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 4 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 7 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 8 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 9 | WHISKEY AWAITING RELEASE - DAY 1 | ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 26-12-2024 | OFFLOADED 26-12-2024
BA2767 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02234 - ABNORMAL LOAD BANJO BOX INTAKE AIR CLEANER FIRE SUPPRESSION SYSTEM (2PKGS) | ABNORMAL LOAD 7,010 x 3,250 x 1,570 - 24494KGS 2,460 x 1,270 x 1,390 - 548KGS 1,570 x 1,270 x 1,720 - 471KGS 1,00 x 1,00 x 0,990 - 599KGS 0,97 x 0,68 x 1,300 - 135KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02234 | CAT0793DEFDB02234 | EXM00354 | FML2411DSI2621 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BM47WGZN - PH167 | BB47WBZN | 2411DSI2621-2 | OFFLOADED 26-12-2024 | 19-12-2024 | 11-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-2024 | 28-11-2024 | 02-12-2024 | 02-12-2024 | 02-12-2024 | 03-12-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 14-12-2024 | 14-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 20-12-2024 | 26-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 3 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 4 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | DISPATCHED WHISKEY ENROUTE KOLWEZI | ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | OFFLOADED 26-12-2024 | OFFLOADED 26-12-2024
BA2753 - KCC PO 4500454150 | CAT950-14A WHEEL LOADER |  | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | CM200212 | CAT00950JCM200212 | D7E00756 | FML2405DSI2550 |  | COD 2024 329545 | ND491242 | ND443606 | ND61453 | OFFLOADED 28-12-2024 | 20-12-2024 | 09-12-2024 | 13-11-2024 | BV COMPLETE | 26-06-2024 | 22-11-2024 | MIDDELBURG 25-11-2024 | MIDDELBURG 25-11-2024 | 26-11-2024 | 27-11-2024 | 29-11-2024 | 02-12-2024 | 02-12-2024 | 02-12-2024 | 04-12-2024 | 05-12-2024 | 06-12-2024 | 08-12-2024 | 09-12-2024 | 18-12-2024 | 18-12-2024 | 22-12-2024 | 23-12-2024 | 23-12-2024 | 23-12-2024 | 28-12-2024 | [26 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN TBA | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-06-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-06-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-06-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-06-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-06-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-06-2024 | VESSEL ARRIVED AND CURRENTLY WORKING | VESSEL STILL WORKING | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING BUCKET TO ARRIVE IN DURBAN | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL AND TYRE HANDLER | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED FOR TOMORROW/FRIDAY - BV RSA TO CONFIRM DATE | BV NUMBER RECEIVED - AWAITING VALIDATION OF LISENCE BEFORE BV CAN BE BOOKED - PLEASE ASSIST | BV NUMBER RECEIVED - AWAITING VALIDATION OF LISENCE BEFORE BV CAN BE BOOKED - PLEASE ASSIST | AWAITING CONFIRMATION OF BV INSPECTION DATE FROM BV RSA | BV INSPECTION TO BE DONE TODAY | LOADING TODAY | LOADED, TO DISPATCH DURBAN | MOOIREVIER ENROUTE JOHANNESBURG | HENDRINA ENROUTE BEIT BRIDGE BORDER | ZEBEDIELA ENROUTE BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE | BEIT BRIDGE BORDER CLEARING | LUNDE ENROUTE HARARE | CHEGUTU ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KAFUE WEIGHBRIDGE ENROUTE KASUMBALESA BORDER | KABWE ENROUTE KASUMBALESA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE AWAITING RELEASE TO PROCEED TO WHISKEY | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 2 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 3 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 4 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 7 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 8 | DISPATCHING KASUMBALESA FOR WHISKEY | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD - DAY 1 | ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 28-12-2024
BA2753A - KCC PO 4500454150 | CAT950 WORKTOOL |  | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | 1013494573 / 1013494574 / 1013494575 |  |  | FML2408DSI2573 |  | COD 2024 329545 | ND491242 | ND443606 | ND61453 | OFFLOADED 28-12-2024 | 20-12-2024 | 09-12-2024 | 13-11-2024 | BV COMPLETE | 28-10-2024 | 22-11-2024 | MIDDELBURG 25-11-2024 | MIDDELBURG 25-11-2024 | 26-11-2024 | 27-11-2024 | 29-11-2024 | 02-12-2024 | 02-12-2024 | 02-12-2024 | 04-12-2024 | 05-12-2024 | 06-12-2024 | 08-12-2024 | 09-12-2024 | 18-12-2024 | 18-12-2024 | 22-12-2024 | 23-12-2024 | 23-12-2024 | 23-12-2024 | 28-12-2024 | [84 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 29-09-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 29-09-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 29-09-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 29-09-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 29-09-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 29-09-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 29-09-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 29-09-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 29-09-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 29-09-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 28-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 27-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 27-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 27-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 27-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 27-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 27-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 27-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 27-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 27-10-2024 | AWAITING VESSEL ARRIVAL: NEW ETA DURBAN PORT 27-10-2024 | VESSEL DUE TO ARRIVE TODAY 28-10-2024 | VESSEL IN AND WORKING | TO BE COLLECTED FROM PORT | COLLECTING FROM PORT TODAY | TO BE DELIVERED TO THE BONDED FACILITY | UNITS AT THE BONDED FACILITY - AWAITING BV NUMBER | UNITS AT THE BONDED FACILITY - AWAITING BV NUMBER | UNITS AT THE BONDED FACILITY - AWAITING BV NUMBER | UNITS AT THE BONDED FACILITY - AWAITING BV NUMBER | UNITS AT THE BONDED FACILITY - AWAITING BV NUMBER | UNITS AT THE BONDED FACILITY - AWAITING BV NUMBER | UNITS AT THE BONDED FACILITY - AWAITING BV NUMBER | UNITS AT THE BONDED FACILITY - AWAITING BV NUMBER | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED FOR TOMORROW/FRIDAY - BV RSA TO CONFIRM DATE | BV NUMBER RECEIVED - AWAITING VALIDATION OF LISENCE BEFORE BV CAN BE BOOKED - PLEASE ASSIST | BV NUMBER RECEIVED - AWAITING VALIDATION OF LISENCE BEFORE BV CAN BE BOOKED - PLEASE ASSIST | AWAITING CONFIRMATION OF BV INSPECTION DATE FROM BV RSA | BV INSPECTION TO BE DONE TODAY | LOADING TODAY | LOADED, TO DISPATCH DURBAN | MOOIREVIER ENROUTE JOHANNESBURG | HENDRINA ENROUTE BEIT BRIDGE BORDER | ZEBEDIELA ENROUTE BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE | BEIT BRIDGE BORDER CLEARING | LUNDE ENROUTE HARARE | CHEGUTU ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KAFUE WEIGHBRIDGE ENROUTE KASUMBALESA BORDER | KABWE ENROUTE KASUMBALESA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE AWAITING RELEASE TO PROCEED TO WHISKEY | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 2 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 3 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 4 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 7 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 8 | DISPATCHING KASUMBALESA FOR WHISKEY | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD - DAY 1 | ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 28-12-2024
BA2753B - KCC PO 4500454150 | CAT950-14 TIREHAND-MODEL TH10K135 |  | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | TH10K135241002 |  |  | FML2408DSI2571 |  | COD 2024 329545 | ND491242 | ND443606 | ND61453 | OFFLOADED 28-12-2024 | 20-12-2024 | 09-12-2024 | 13-11-2024 | BV COMPLETE | 11-10-2024 | 22-11-2024 | MIDDELBURG 25-11-2024 | MIDDELBURG 25-11-2024 | 26-11-2024 | 27-11-2024 | 29-11-2024 | 02-12-2024 | 02-12-2024 | 02-12-2024 | 04-12-2024 | 05-12-2024 | 06-12-2024 | 08-12-2024 | 09-12-2024 | 18-12-2024 | 18-12-2024 | 22-12-2024 | 23-12-2024 | 23-12-2024 | 23-12-2024 | 28-12-2024 | [82 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 07-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 09-10-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN PORT 09-10-2024 | VESSEL DUE TO ARRIVA PM TODAY | VESSEL DUE TO BERTH AM TODAY | UNIT TO BE DELIVERED TO FML BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT BONDED FACILITY TODAY - AWAITING WORKTOOL | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | UNIT AT THE BONDED FACILITY - AWAITING BV NUMBER | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED FOR TOMORROW/FRIDAY - BV RSA TO CONFIRM DATE | BV NUMBER RECEIVED - AWAITING VALIDATION OF LISENCE BEFORE BV CAN BE BOOKED - PLEASE ASSIST | BV NUMBER RECEIVED - AWAITING VALIDATION OF LISENCE BEFORE BV CAN BE BOOKED - PLEASE ASSIST | AWAITING CONFIRMATION OF BV INSPECTION DATE FROM BV RSA | BV INSPECTION TO BE DONE TODAY | LOADING TODAY | LOADED, TO DISPATCH DURBAN | MOOIREVIER ENROUTE JOHANNESBURG | HENDRINA ENROUTE BEIT BRIDGE BORDER | ZEBEDIELA ENROUTE BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE | BEIT BRIDGE BORDER CLEARING | LUNDE ENROUTE HARARE | CHEGUTU ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KAFUE WEIGHBRIDGE ENROUTE KASUMBALESA BORDER | KABWE ENROUTE KASUMBALESA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE AWAITING RELEASE TO PROCEED TO WHISKEY | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 2 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 3 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 4 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 7 | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 8 | DISPATCHING KASUMBALESA FOR WHISKEY | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD - DAY 1 | ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 28-12-2024
BA2762 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02229 - LINK LOAD SKID FUEL TANK SKID RIMS SKID RIMS SKID RIM TOPY SKID FSTRUT RH PLATFORM BOX HARDWARE BOX PIPING | LINK LOAD 2,430 x 1,650 x 2,230 - 1597KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 0,91 - 1950KGS 3,300 x 1,520 x 1,520 - 6506KGS 4,260 x 2,510 x 2,790 - 2676KGS 2,280 x 1,210 x 0,450 - 511KGS 2,180 x 0,700 x 0,500 - 295KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02229 | CAT0793DLFDB02229 | EXM00351 | FML2410DSI2602 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | HD10TBGP - J68 | WJD486GP / WJD488GP | 2410DSI2602-3 | OFFLOADED 27-12-2024 | 20-12-2024 | 14-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 29-11-2024 | 29-11-2024 | 30-11-2024 | 04-12-2024 | 10-12-2024 | 10-12-2024 | 10-12-2024 | 11-12-2024 | 12-12-2024 | 12-12-2024 | 13-12-2024 | 13-12-2024 | 18-12-2024 | 18-12-2024 | 22-12-2024 | 24-12-2024 | 25-12-2024 | 26-12-2024 | 27-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | JOHANNESBURG TO DISPATCH FOR BEIT BRIDGE BORDER | MOKOPANE ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE AWAITING RELEASE | GWERU ENROUTE HARARE | GWERU TO DISPATCH FOR HARARE | GWERU TO DISPATCH FOR HARARE TOMORROW | GWERU DISPATCHED FOR HARARE - ESTIMATED ARRIVAL DATE ON SITE 18-12-2024 | CHIRUNDU BORDER CLEARING | KAFUE ENROUTE KASUMBALESA BORDER | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE AWAITING RELEASE | KASUMBALESA DRC SIDE AWAITING RELEASE - DAY 4 | DISPATCHING KASUMBALESA FOR WHISKEY | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KATANGA ENROUTE KOLWEZI | ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-12-2024
BA2762 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02229 - LINK LOAD SKID CAB SKID BODY SKID RIM TROPHY SKID OUTRIGGERS SKID HANDRAILS SKID FSTRUT | LINK LOAD 3,250 x 2,260 x 1,930 - 2514KGS 2,130 x 0,760 x 1,290 - 1125KGS 1,820 x 1,820 x 0,910 - 1950KGS 2,460 x 2,230 x 0,760 - 1288KGS 3,960 x 2,260 x 1,880 - 1515KGS 3,300 x 1,520 x 1,520 - 6505KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02229 | CAT0793DLFDB02229 | EXM00351 | FML2410DSI2602 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | HN28XGGP - J74 | KT53PMGP / KT53PNGP | 2410DSI2602-4 | OFFLOADED 27-12-2024 | 20-12-2024 | 17-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-204 | 28-11-2024 | 04-12-2024 | 05-12-2024 | 06-12-2024 | 06-12-2024 | 06-12-2024 | 06-12-2024 | 09-12-2024 | 10-12-2024 | 10-12-2024 | 19-12-2024 | 20-12-2024 | 24-12-2024 | 24-12-2024 | 25-12-2024 | 26-12-2024 | 27-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | MOKOPANE ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE AWAITING RELEASE | RUNDE ENROUTE HARARE | NYABIRA ENROUTE CHIRUNDU | LUSAKA TO DISPATCH FOR KASUMBALESA | KALOKO ENROUTE KASUMBALESA - ESTIMATED ARRIVAL DATE ON SITE 18-12-2024 - IF NO DELAYS AT THE BORDER AND WHISKEY | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING - DAY 2 | KASUMBALESA ZAM SIDE CLEARING - DAY 3 | KASUMBALESA ZAM SIDE CLEARING - DAY 7 | KASUMBALESA ZAM SIDE CLEARING - DAY 8 | KASUMBALESA ZAM CROSSING TO DRC SIDE - DAY 9 ON THE BORDER | KASUMBALESA DRC SIDE - DAY 10 ON THE BORDER | COLLECTED DOCUMENTS VEHICLE TO DISPATCH FROM KASUMBALESA TO PROCEED TO WHISKEY | KASUMBALESA DRC IN THE QUEUE TO EXIT THE BORDER | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-12-2024
BA2764 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02231 - LINK LOAD SKID CAB SKID BODY SKID RIM TROPHY SKID OUTRIGGERS SKID HANDRAILS SKID FSTRUT | LINK LOAD 3,250 x 2,260 x 1,930 - 2514KGS 2,130 x 0,760 x 1,290 - 1125KGS 1,820 x 1,820 x 0,910 - 1950KGS 2,460 x 2,230 x 0,760 - 1288KGS 3,960 x 2,260 x 1,880 - 1515KGS 3,300 x 1,520 x 1,520 - 6505KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02231 | CAT0793DAFDB02231 | EXM00353 | FML2410DSI2604 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | KT12LHGP - J103 | KT40NYGP / KT40PBGP | 2410DSI2604-4 | OFFLOADED 27-12-2024 | 20-12-2024 | 17-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-2024 | 03-12-2024 | 04-12-2024 | 05-12-2024 | 06-12-2024 | 06-12-2024 | 08-12-2024 | 09-12-2024 | 09-12-2024 | 10-12-2024 | 10-12-2024 | 19-12-2024 | 20-12-2024 | 24-12-2024 | 24-12-2024 | 25-12-2024 | 26-12-2024 | 27-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | JOHANNESBURG TO DISPATCH FOR BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE AWAITING RELEASE | RUNDE ENROUTE HARARE | NYARIBA ENROUTE CHIRUNDU BORDER | LUSAKA TO DISPATCH FOR KASUMBALESA | KALOKO ENROUTE KASUMBALESA - ESTIMATED ARRIVAL DATE ON SITE 18-12-2024 - IF NO DELAYS AT THE BORDER AND WHISKEY | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING - DAY 3 | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING - DAY 7 | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING - DAY 8 | KASUMBALESA ZAM CROSSING TO DRC SIDE - DAY 9 ON THE BORDER | KASUMBALESA DRC SIDE - DAY 10 ON THE BORDER | COLLECTED DOCUMENTS VEHICLE TO DISPATCH FROM KASUMBALESA TO PROCEED TO WHISKEY | KASUMBALESA DRC IN THE QUEUE TO EXIT THE BORDER | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-12-2024
BA2765 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02232 - ABNORMAL LOAD CHASSIS | ABNORMAL LOAD 10,080 x 3,880 x 3,50 - 43985KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02232 | CAT0793DLFDB02232 | EXM00356 | FML2411DSI2619 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BJ60GTZN - PH211 | BN39DMZN / BN54MHZN | 2411DSI2619-1 | OFFLOADED 27-12-2024 | 19-12-2024 | 17-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-2024 | 28-11-2024 | 03-12-2024 | 04-12-2024 | 04-12-2024 | 06-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 18-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 20-12-2024 | 27-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | MOOKGOPONG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BUBI ENROUTE HARARE | CHIKOMBA ENROUTE HARARE | HURUNGWE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAM SIDE | KAPIRI MPOSHI ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 3 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 4 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 7 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 8 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 9 | WHISKEY AWAITING RELEASE - DAY 1 | ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | ON SITE WAITING TO OFFLOAD - DAY 8 | OFFLOADED 27-12-2024
BA2765 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02232 - ABNORMAL LOAD BANJO BOX INTAKE AIR CLEANER FIRE SUPPRESSION SYSTEM (2PKGS) | ABNORMAL LOAD 7,010 x 3,250 x 1,570 - 24494KGS 2,460 x 1,270 x 1,390 - 548KGS 1,570 x 1,270 x 1,720 - 471KGS 1,00 x 1,00 x 0,990 - 599KGS 0,97 x 0,68 x 1,300 - 135KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02232 | CAT0793DLFDB02232 | EXM00356 | FML2411DSI2619 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | ND919947 - PH206 | BL00YBZN | 2411DSI2619-2 | OFFLOADED 27-12-2024 | 19-12-2024 | 11-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-204 | 27-11-2024 | 28-11-2024 | 28-11-2024 | 28-11-2024 | 03-12-2024 | 03-12-2024 | 04-12-2024 | 04-12-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | MOKAMBO 09-12-2024 | MOKAMBO 14-12-2024 | 14-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 20-12-2024 | 27-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | BV COMPLETED ON THIS VEHICLE - DISPATCHED DURBAN ENROUTE ESCORT | VILLIERS ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE | MASVINGO ENROUTE HARARE | MAKONDE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAM SIDE | CHIRUNDU BORDER ZAM SIDE | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - ESTIMATED ETA ON SITE 14-12-2024 IF NO DELAYS AT THE BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 2 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 3 | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 4 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | DISPATCHED WHISKEY ENROUTE KOLWEZI | ENROUTE SITE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 4 | ON SITE WAITING TO OFFLOAD - DAY 5 | ON SITE WAITING TO OFFLOAD - DAY 8 | OFFLOADED 27-12-2024
BA2765 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02232 - LINK LOAD SKID CAB SKID BODY SKID RIM TROPHY SKID OUTRIGGERS SKID HANDRAILS SKID FSTRUT | LINK LOAD 3,250 x 2,260 x 1,930 - 2514KGS 2,130 x 0,760 x 1,290 - 1125KGS 1,820 x 1,820 x 0,910 - 1950KGS 2,460 x 2,230 x 0,760 - 1288KGS 3,960 x 2,260 x 1,880 - 1515KGS 3,300 x 1,520 x 1,520 - 6505KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02232 | CAT0793DLFDB02232 | EXM00356 | FML2411DSI2619 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | KT12NKGP - J108 | YSN353GP / YSN837GP | 2411DSI2619-4 | OFFLOADED 27-12-2024 | 20-12-2024 | 17-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 28-11-2024 | 28-11-2024 | 29-11-2024 | 30-11-2024 | 30-11-2024 | 06-12-2024 | 08-12-2024 | 09-12-2024 | 08-12-2024 | 10-12-2024 | 10-12-2024 | 11-12-2024 | 11-12-2024 | 14-12-2024 | 17-12-2024 | 17-12-2024 | 21-12-2024 | 21-12-2024 | 22-12-2024 | 24-12-2024 | 27-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADING TODAY FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 26-11-2024 - AWAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE THURSDAY 28-11-2024 | LOADED - AWAITING BV INSPECTION. BV TO BE DONE THURSDAY 28-11-2024 | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY 28-11-2024 | JOHANNESBURG UNDER ROUTINE MAINTENANCE TO DISPATCH FOR BEIT BRIDGE BORDER ONCE DONE | BEIT BRIDGE BORDER ZIM SIDE | BEIT BRIDGE BORDER ZIM SIDE | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER ZIM SIDE WAITING RELEASE | HARARE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZIM SIDE CLEARING - ESTIMATED ETA ON SITE 18-12-2024 - IF NO DELAYS AT THE BORDERS | KITWE ENROUTE KASUMBALESA BORDER | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAM SIDE CLEARING - DAY 1 | KASUMBALESA BORDER ZAM SIDE CLEARING - DAY 4 | KASUMBALESA BORDER ZAM SIDE CLEARING - DAY 5 | KASUMBALESA BORDER ZAM SIDE CLEARING - DAY 6 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | LIKASI ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD - DAY 1 | ON SITE WAITING TO OFFLOAD - DAY 4 | OFFLOADED 27-12-2024
BA2765 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02232 - LINK LOAD SKID FUEL TANK SKID RIMS SKID RIMS SKID RIM TOPY SKID FSTRUT RH PLATFORM BOX HARDWARE BOX PIPING | LINK LOAD 2,430 x 1,650 x 2,230 - 1597KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 0,91 - 1950KGS 3,300 x 1,520 x 1,520 - 6506KGS 4,260 x 2,510 x 2,790 - 2676KGS 2,280 x 1,210 x 0,450 - 511KGS 2,180 x 0,700 x 0,500 - 295KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02232 | CAT0793DLFDB02232 | EXM00356 | FML2411DSI2619 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BCF5599ZM | BCF6077ZM / BCF6078ZM | 2411DSI2619-3 | OFFLOADED 30-12-2024 | 20-12-2024 | 17-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 28-11-2024 | 28-11-2024 | 29-11-2024 | 30-11-2024 | 30-11-2024 | 07-12-2024 | 07-12-2024 | 08-12-2024 | 08-12-2024 | 11-12-2024 | 12-12-2024 | 13-12-2024 | 13-12-2024 | MOKAMBO 13-12-2024 | MOKAMOBO 27-12-2024 | 27-12-2024 | 28-12-2024 | 28-12-2024 | 28-12-2024 | 28-12-2024 | 30-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADING TODAY FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 26-11-2024 - AWAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE THURSDAY 28-11-2024 | LOADED - AWAITING BV INSPECTION. BV TO BE DONE THURSDAY 28-11-2024 | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY 28-11-2024 | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER ZIM SIDE | BEIT BRIDGE BORDER ZIM SIDE | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE CLEARING | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER ZIM SIDE CLEARING - ESTIMATED ETA ON SITE 18-12-2024 - IF NO DELAYS AT THE BORDERS | CHIRUNDU BORDER ZAM SIDE CLEARING | LUSAKA ENROUTE MOKAMBO BORDER | LUSAKA TO DISPATCH FOR MOKAMBO BORDER | MOKAMBO BORDER CLEARING - DAY 3 | MOKAMBO BORDER CLEARING - DAY 4 | MOKAMBO BORDER DRC SIDE CLEARING - DAY 5 | MOKAMBO BORDER DRC SIDE CLEARING - DAY 6 | COLLECTED DOCUMENTS VEHICLE TO DISPATCH FROM MOKAMBO TO PROCEED TO WHISKEY | IN THE QUEUE TO EXIT MOKAMBO BORDER | DISPATCHING MOKAMBO | MOKAMBO BORDER - CLEARANCE COMPLETED - TO COLLECT DOCUMENTS | KANYAKA ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 30-12-2024
BA2766 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02233 - LINK LOAD SKID FUEL TANK SKID RIMS SKID RIMS SKID RIM TOPY SKID FSTRUT RH PLATFORM BOX HARDWARE BOX PIPING | LINK LOAD 2,430 x 1,650 x 2,230 - 1597KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 0,91 - 1950KGS 3,300 x 1,520 x 1,520 - 6506KGS 4,260 x 2,510 x 2,790 - 2676KGS 2,280 x 1,210 x 0,450 - 511KGS 2,180 x 0,700 x 0,500 - 295KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02233 | CAT0793DHFDB02233 | EXM00355 | FML2411DSI2620 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BCF5603ZM | BCF6083ZM / BCF6076ZM | 2411DSI2620-3 | OFFLOADED 30-12-2024 | 20-12-2024 | 17-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 28-11-2024 | 28-11-2024 | 29-11-2024 | 30-11-2024 | 30-11-2024 | 06-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | 11-12-2024 | 12-12-2024 | 13-12-2024 | 13-12-2024 | MOKAMBO 14-12-2024 | MOKAMBO 27-12-2024 | 27-12-2024 | 28-12-2024 | 28-12-2024 | 28-12-2024 | 28-12-2024 | 30-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADING TODAY FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 26-11-2024 - AWAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY | LOADED - AWAITING BV INSPECTION. BV TO BE DONE THURSDAY 28-11-2024 | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY 28-11-2024 | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER ZIM SIDE WAITING RELEASE | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER ZIM SIDE CLEARING - ESTIMATED ETA ON SITE 18-12-2024 - IF NO DELAYS AT THE BORDERS | CHIRUNDU BORDER ZAM SIDE CLEARING | LUSAKA ENROUTE MOKAMBO BORDER | LUSAKA TO DISPATCH FOR MOKAMBO BORDER | MOKAMBO BORDER CLEARING - DAY 3 | MOKAMBO BORDER CLEARING - DAY 4 | MOKAMBO BORDER DRC SIDE CLEARING - DAY 5 | MOKAMBO BORDER DRC SIDE CLEARING - DAY 6 | COLLECTED DOCUMENTS VEHICLE TO DISPATCH FROM MOKAMBO TO PROCEED TO WHISKEY | IN THE QUEUE TO EXIT MOKAMBO BORDER | DISPATCHING MOKAMBO | MOKAMBO BORDER - CLEARANCE COMPLETED - TO COLLECT DOCUMENTS | KANYAKA ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 30-12-2024
BA2766 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02233 - LINK LOAD SKID CAB SKID BODY SKID RIM TROPHY SKID OUTRIGGERS SKID HANDRAILS SKID FSTRUT | LINK LOAD 3,250 x 2,260 x 1,930 - 2514KGS 2,130 x 0,760 x 1,290 - 1125KGS 1,820 x 1,820 x 0,910 - 1950KGS 2,460 x 2,230 x 0,760 - 1288KGS 3,960 x 2,260 x 1,880 - 1515KGS 3,300 x 1,520 x 1,520 - 6505KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02233 | CAT0793DHFDB02233 | EXM00355 | FML2411DSI2620 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BCF3922ZM | BCF5389ZM / BCF5390ZM | 2411DSI2620-4 | OFFLOADED 30-12-2024 | 20-12-2024 | 18-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 28-11-2024 | 28-11-2024 | 29-11-2024 | 30-11-2024 | 30-11-2024 | 06-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | 11-12-2024 | 12-12-2024 | 13-12-2024 | 17-12-2024 | MOKAMBO 17-12-2024 | MOKAMBO 27-12-2024 | 27-12-2024 | 27-12-2024 | 27-12-2024 | 28-12-2024 | 28-12-2024 | 30-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADING TODAY FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 26-11-2024 - AWAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY | LOADED - AWAITING BV INSPECTION. BV TO BE DONE THURSDAY 28-11-2024 | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY 28-11-2024 | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER ZIM SIDE WAITING RELEASE | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER ZIM SIDE CLEARING - ESTIMATED ETA ON SITE 18-12-2024 - IF NO DELAYS AT THE BORDERS | CHIRUNDU BORDER ZAM SIDE CLEARING | LUSAKA ENROUTE MOKAMBO BORDER | LUSAKA TO DISPATCH FOR MOKAMBO BORDER | NDOLA ENROUTE MOKAMBO BORDER | DISPATCHING NDOLA FOR MOKAMBO BORDER | MOKAMOBO BORDER ZAM SIDE CLEARING - DAY 1 | MOKAMOBO BORDER ZAM SIDE CLEARING - DAY 2 | COLLECTED DOCUMENTS VEHICLE TO DISPATCH FROM MOKAMBO TO PROCEED TO WHISKEY | IN THE QUEUE TO EXIT MOKAMBO BORDER | DISPATCHING MOKAMBO | MOKAMBO BORDER - WAITING TO REFUEL TO DISPATCH | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 30-12-2024
BA2767 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02234 - LINK LOAD SKID FUEL TANK SKID RIMS SKID RIMS SKID RIM TOPY SKID FSTRUT RH PLATFORM BOX HARDWARE BOX PIPING | LINK LOAD 2,430 x 1,650 x 2,230 - 1597KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 0,91 - 1950KGS 3,300 x 1,520 x 1,520 - 6506KGS 4,260 x 2,510 x 2,790 - 2676KGS 2,280 x 1,210 x 0,450 - 511KGS 2,180 x 0,700 x 0,500 - 295KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02234 | CAT0793DEFDB02234 | EXM00354 | FML2411DSI2621 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | BCF3588ZM | AJF3546ZM / AJF3545ZM | 2411DSI2621-3 | OFFLOADED 30-12-2024 | 20-12-2024 | 17-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 28-11-2024 | 28-11-2024 | 29-11-2024 | 30-11-2024 | 30-11-2024 | 06-12-2024 | 07-12-2024 | 08-12-2024 | 09-12-2024 | 12-12-2024 | 13-12-2024 | 14-12-2024 | 15-12-2024 | MOKAMBO 15-12-2024 | MOKAMBO 27-12-2024 | 27-12-2024 | 28-12-2024 | 28-12-2024 | 28-12-2024 | 28-12-2024 | 30-12-2024 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADING TODAY FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 26-11-2024 - AWAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE THURSDAY 28-11-2024 | LOADED - AWAITING BV INSPECTION. BV TO BE DONE THURSDAY 28-11-2024 | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY 28-11-2024 | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER ZIM SIDE WAITING RELEASE | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER ZIM SIDE CLEARING - ESTIMATED ETA ON SITE 18-12-2024 - IF NO DELAYS AT THE BORDERS | CHIRUNDU BORDER ZAM SIDE CLEARING | MONGA ENROUTE MOKAMBO BORDER | KAFUE ENROUTE MOKAMBO BORDER | NDOLA ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE CLEARING - DAY 1 | MOKAMBO BORDER DRC SIDE CLEARING - DAY 2 | MOKAMBO BORDER DRC SIDE CLEARING - DAY 3 | COLLECTED DOCUMENTS VEHICLE TO DISPATCH FROM MOKAMBO TO PROCEED TO WHISKEY | IN THE QUEUE TO EXIT MOKAMBO BORDER | DISPATCHING MOKAMBO | MOKAMBO BORDER - WAITING TO REFUEL TO DISPATCH | KANYAKA ENROUTE KOLWEZI | ON SITE WAITING TO OFFLOAD | OFFLOADED 30-12-2024
BA2763 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02230 - LINK LOAD SKID FUEL TANK SKID RIMS SKID RIMS SKID RIM TOPY SKID FSTRUT RH PLATFORM BOX HARDWARE BOX PIPING | LINK LOAD 2,430 x 1,650 x 2,230 - 1597KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 1,930 - 3249KGS 1,820 x 1,820 x 0,91 - 1950KGS 3,300 x 1,520 x 1,520 - 6506KGS 4,260 x 2,510 x 2,790 - 2676KGS 2,280 x 1,210 x 0,450 - 511KGS 2,180 x 0,700 x 0,500 - 295KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02230 | CAT0793DVFDB02230 | EXM00317 | FML2410DSI2603 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | KB12VVGP - J86 | SXV103GP / SXV402GP | 2410DSI2603-3 | OFFLOADED 10-01-2025 | 09-01-2025 | 12-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 29-11-2024 | 30-11-2024 | 30-11-2024 | 04-12-2024 | 06-12-2024 | 06-12-2024 | 06-12-2024 | 10-12-2024 | 10-12-2024 | 11-12-2024 | 12-12-2024 | 13-12-2024 | 03-01-2025 | 03-01-2025 | 07-01-2024 | 07-01-2025 | 08-01-2025 | 08-01-2025 | 10-01-2025 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | JOHANNESBURG TO DISPATCH FOR BEIT BRIDGE BORDER | JOHANNESBURG UNDER ROUTINE MAINTENANCE TO DISPATCH FOR BEIT BRIDGE BORDER ONCE DONE | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE AWAITING RELEASE | MWENEZI ENROUTE HARARE | NYABIRA TO DISPATCH TO CHIRUNDU | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING - ESTIMATED ETA ON SITE 17-12-2024 | KABWE ENROUTE KASUMBALESA BORDER | KITWE ENROUTE KASUMBALESA BORDER | KITWE ENROUTE KASUMBALESA BORDER - DAY 2 | KASUMBALESA BORDER DRC SICE AWAITING RELEASE | KASUMBALESA BORDER DRC SICE AWAITING RELEASE - DAY 6 | KASUMBALESA BORDER DRC SICE AWAITING RELEASE - DAY 7 | KASUMBALESA BORDER DRC SICE AWAITING RELEASE - DAY 8 | COLLECTED DOCUMENTS VEHICLE TO DISPATCH FROM KASUMBALESA TO PROCEED TO WHISKEY | KASUMBALESA DRC IN THE QUEUE TO EXIT THE BORDER | KASUMBALESA DRC - THE CHIEF OF CUSTOMS TOOK THE DOCUMENTS AND AWAITING CONNEX AFRICA TO SEE THE CHIEF BEFORE DOCUMENTS CAN BE RELEASED | KASUMBALESA DRC - THE CHIEF OF CUSTOMS TOOK THE DOCUMENTS AND AWAITING CONNEX AFRICA TO SEE THE CHIEF BEFORE DOCUMENTS CAN BE RELEASED | KASUMBALESA DRC - AWAITING DOCUMENTS AND RELEASE - VEHICLE MANIFEST SHOW ENTRY POINT KASUMBALESA - CONNEX CLEARED IT THROUGH MOKAMBO BORDER - PLEASE ASSIST WITH RELEASE | KASUMBALESA DRC - AWAITING DOCUMENTS AND RELEASE - VEHICLE MANIFEST SHOW ENTRY POINT KASUMBALESA - CONNEX CLEARED IT THROUGH MOKAMBO BORDER - PLEASE ASSIST WITH RELEASE - DAY 19 | KASUMBALESA DRC - AWAITING DOCUMENTS AND RELEASE - VEHICLE MANIFEST SHOW ENTRY POINT KASUMBALESA - CONNEX CLEARED IT THROUGH MOKAMBO BORDER - PLEASE ASSIST WITH RELEASE - DAY 22 - PLEASE ASSIST | KASUMBALESA DRC - AWAITING DOCUMENTS AND RELEASE - VEHICLE MANIFEST SHOW ENTRY POINT KASUMBALESA - CONNEX CLEARED IT THROUGH MOKAMBO BORDER - PLEASE ASSIST WITH RELEASE - DAY 23 - PLEASE ASSIST | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE AND EXIT FORMALITIES | KANYAKA TO DISPATCH FOR KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 10-01-2025
BA2763 - KCC PO 4500515148 | CAT793D BC OFF HIGHWAY TRUCK - SERIAL NUMBER: FDB02230 - LINK LOAD SKID CAB SKID BODY SKID RIM TROPHY SKID OUTRIGGERS SKID HANDRAILS SKID FSTRUT | LINK LOAD 3,250 x 2,260 x 1,930 - 2514KGS 2,130 x 0,760 x 1,290 - 1125KGS 1,820 x 1,820 x 0,910 - 1950KGS 2,460 x 2,230 x 0,760 - 1288KGS 3,960 x 2,260 x 1,880 - 1515KGS 3,300 x 1,520 x 1,520 - 6505KGS | BARTRAC EQUIPMENT / KAMOTO COPPER COMPANY | FDB02230 | CAT0793DVFDB02230 | EXM00317 | FML2410DSI2603 | VESSEL: GARNET ACE Voy. 0118A - ETA DURBAN: 19-11-2024 | COD 2024 307498 | KB12WBGP - J87 | YLK221GP / YLK214GP | 2410DSI2603-4 | OFFLOADED 10-01-2025 | 09-01-2025 | 12-12-2024 | 15-10-2024 | BV COMPLETE | 19-11-2024 | 26-11-2024 | 27-11-2024 | 29-11-2024 | 30-11-2024 | 30-11-2024 | 04-12-2024 | 05-12-204 | 05-12-204 | 05-12-2024 | 06-12-2024 | 07-12-2024 | 09-12--2024 | 09-12-2024 | 09-12-2024 | 04-01-2025 | 04-01-2025 | 07-01-2025 | 07-01-2025 | 07-01-2024 | 08-01-2024 | 10-01-2025 | [131 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 18-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 17-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | AWAITING VESSEL ARRIVAL: ETA DURBAN: 19-11-2024 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - LOADING FROM PORT | VESSEL IN AND WORKING - STILL LOADING FROM PORT | VEHICLES STILL LOADING FROM PORT - BV INSPECTION TO BE ARRANGED ONCE ALL CARGO HAVE BEEN LOADED FROM PORT | LOADED - AWAITING BV INSPECTION. BV BOOKED FOR TODAY - WAITING CONFIRMATION FROM BV RSA | LOADED - AWAITING BV INSPECTION. BV TO BE DONE TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | JOHANNESBURG TO DISPATCH FOR BEIT BRIDGE BORDER | MOKOPANE ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE AWAITING RELEASE | KWEKWE ERNOUTE HARARE | CHIRUNDU BORDER ZIM SIDE | KAPIRI ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAMBIA SIDE CLEARING - ESTIMATED ETA ON SITE 15-12-2024 - IF NO DELAYS AT BORDER AND WHIKSEY | KASUMBALESA ZAMBIA SIDE CLEARING | KASUMBALESA DRC SIDE - AWAITNG CLEARANCE AND RELEASE | KASUMBALESA DRC SIDE - AWAITNG CLEARANCE AND RELEASE - DAY 3 | KASUMBALESA DRC SIDE - AWAITNG CLEARANCE AND RELEASE - DAY 7 | KASUMBALESA DRC SIDE - AWAITNG CLEARANCE AND RELEASE - DAY 8 | KASUMBALESA DRC SIDE - AWAITNG CLEARANCE AND RELEASE - DAY 9 | KASUMBALESA DRC SIDE - AWAITNG CLEARANCE AND RELEASE - DAY 10 | COLLECTED DOCUMENTS VEHICLE TO DISPATCH FROM KASUMBALESA TO PROCEED TO WHISKEY | KASUMBALESA DRC IN THE QUEUE TO EXIT THE BORDER | KASUMBALESA DRC - THE CHIEF OF CUSTOMS TOOK THE DOCUMENTS AND AWAITING CONNEX AFRICA TO SEE THE CHIEF BEFORE DOCUMENTS CAN BE RELEASED | KASUMBALESA DRC - THE CHIEF OF CUSTOMS TOOK THE DOCUMENTS AND AWAITING CONNEX AFRICA TO SEE THE CHIEF BEFORE DOCUMENTS CAN BE RELEASED | KASUMBALESA DRC - AWAITING DOCUMENTS AND RELEASE - VEHICLE MANIFEST SHOW ENTRY POINT KASUMBALESA - CONNEX CLEARED IT THROUGH MOKAMBO BORDER - PLEASE ASSIST WITH RELEASE | KASUMBALESA DRC - AWAITING DOCUMENTS AND RELEASE - VEHICLE MANIFEST SHOW ENTRY POINT KASUMBALESA - CONNEX CLEARED IT THROUGH MOKAMBO BORDER - PLEASE ASSIST WITH RELEASE - DAY 21 | KASUMBALESA DRC - AWAITING DOCUMENTS AND RELEASE - VEHICLE MANIFEST SHOW ENTRY POINT KASUMBALESA - CONNEX CLEARED IT THROUGH MOKAMBO BORDER - PLEASE ASSIST WITH RELEASE - DAY 24 - PLEASE ASSIST | KASUMBALESA DRC - AWAITING DOCUMENTS AND RELEASE - VEHICLE MANIFEST SHOW ENTRY POINT KASUMBALESA - CONNEX CLEARED IT THROUGH MOKAMBO BORDER - PLEASE ASSIST WITH RELEASE - DAY 25 - PLEASE ASSIST | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE AND EXIT FORMALITIES | CONNEX KOLWEZI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 10-01-2025