## ENROUTE SITE
CLIENT PO | CARGO DETAILS | CLIENT | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | VESSEL DETAILS & ETA | ACTUAL STATUS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | MUSINA ARR | MUSINA DISP | BEIT BRIDGE ARR | BEIT BRIDGE DSP | HARERE ARR | HARARE DSP | CHIRUNDU ARR | CHIRUNDU DSP | LUSAKA | KABWE | KITWE | KASUMBALESA ARRIVAL | KASUMBALESA DISPATCH | WHISKY | LUBUMBASHI | TENKE | OFFLOADED | COMMENTS 25-07-2022 | COMMENTS 26-07-2022 | COMMENTS 29-07-2022 | COMMENTS 30-07-2022 | COMMENTS 31-07-2022 | COMMENTS 01-08-2022 | COMMENTS 02-08-2022 | COMMENTS 05-08-2022 | COMMENTS 06-08-2022 | COMMENTS 07-08-2022 | COMMENTS 08-08-2022 | COMMENTS 09-08-2022 | COMMENTS 12-08-2022 | COMMENTS 13-08-2022 | COMMENTS 14-08-2022 | COMMENTS 15-08-2022 | COMMENTS 16-08-2022 | COMMENTS 19-08-2022 | COMMENTS 20-08-2022 | COMMENTS 21-08-2022 | COMMENTS 22-08-2022 | COMMENTS 23-08-2022 | COMMENTS 26-08-2022 | COMMENTS 27-08-2022 | COMMENTS 28-08-2022 | COMMENTS 29-08-2022 | COMMENTS 30-08-2022 | COMMENTS 02-09-2022 | COMMENTS 03-09-2022 | COMMENTS 04-09-2022 | COMMENTS 05-09-2022 | COMMENTS 06-09-2022 | COMMENTS 09-09-2022 | COMMENTS 10-09-2022 | COMMENTS 11-09-2022 | COMMENTS 12-09-2022 | COMMENTS 13-09-2022 | COMMENTS 16-09-2022 | COMMENTS 17-09-2022 | COMMENTS 18-09-2022 | COMMENTS 19-09-2022 | COMMENTS 20-09-2022 | COMMENTS 23-09-2022 | COMMENTS 25-09-2022 | COMMENTS 26-09-2022 | COMMENTS 27-09-2022 | COMMENTS 30-09-2022 | COMMENTS 01-10-2022 | COMMENTS 02-10-2022 | COMMENTS 03-10-2022 | COMMENTS 04-10-2022 | COMMENTS 07-10-2022 | COMMENTS 08-10-2022 | COMMENTS 09-10-2022 | COMMENTS 10-10-2022 | COMMENTS 11-10-2022 | COMMENTS 14-10-2022 | COMMENTS 15-10-2022 | COMMENTS 16-10-2022 | COMMENTS 17-10-2022 | COMMENTS 18-10-2022 | COMMENTS 21-10-2022 | COMMENTS 22-10-2022 | COMMENTS 23-10-2022 | COMMENTS 24-10-2022 | COMMENTS 25-10-2022 | COMMENTS 28-10-2022 | COMMENTS 29-10-2022 | COMMENTS 30-10-2022 | COMMENTS 31-10-2022 | COMMENTS 01-11-2022 | COMMENTS 04-11-2022 | COMMENTS 05-11-2022 | COMMENTS 06-11-2022 | COMMENTS 07-11-2022 | COMMENTS 08-11-2022 | COMMENTS 11-11-2022
BA2771 | 1 X CAT988K BUCKET | TENKE FUNGURUME MINING (CMOC) | FML2409DSI2580 | COD 2024 154630 | KY87BVGP | HG94ZBGP / HG94ZKGP | 2409DSI2580 | 28-10-2024 | VESSEL: MORNING CHANT Voy, 101 - ETA DURBAN: 18-10-2024 | OFFLOADED 09-11-2024 | 18-10-2024 | 23-10-2024 | 24-10-2024 | 24-10-2024 | 25-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2024 | 26-10-2024 | 27-10-2024 | 28-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 02-11-2024 | 02-11-2024 | 06-11-2024 | 06-11-2024 | 09-11-2024 | [29 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | ONLY COLLECTING THE BUCKETS THIS MORNING - BV INSPECTION PLANNED FOR THIS AFTERNOON | BV INSPECTION TO BE DONE TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | BEIT BRIDGE BORDER CLEARING | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAIING RELEASE | WHISKEY AWAIING RELEASE | WHISKEY TO DISPATCH SHORTLY | ON SITE WAITING FOR INDUCTION | ON SITE WAITING TO OFFLOAD | OFFLOADED 09-11-2024
BA2772 | 1 X CAT988K BUCKET | TENKE FUNGURUME MINING (CMOC) | FML2409DSI2580 | COD 2024 154630 | KY87BVGP | HG94ZBGP / HG94ZKGP | 2409DSI2580 | 28-10-2024 | VESSEL: MORNING CHANT Voy, 101 - ETA DURBAN: 18-10-2024 | OFFLOADED 09-11-2024 | 18-10-2024 | 23-10-2024 | 24-10-2024 | 24-10-2024 | 25-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2024 | 26-10-2024 | 27-10-2024 | 28-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 02-11-2024 | 02-11-2024 | 06-11-2024 | 06-11-2024 | 09-11-2024 | [29 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | ONLY COLLECTING THE BUCKETS THIS MORNING - BV INSPECTION PLANNED FOR THIS AFTERNOON | BV INSPECTION TO BE DONE TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | BEIT BRIDGE BORDER CLEARING | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAIING RELEASE | WHISKEY AWAIING RELEASE | WHISKEY TO DISPATCH SHORTLY | ON SITE WAITING FOR INDUCTION | ON SITE WAITING TO OFFLOAD | OFFLOADED 09-11-2024
BA2773 | 1 X CAT988K BUCKET | TENKE FUNGURUME MINING (CMOC) | FML2409DSI2580 | COD 2024 154630 | KY87BVGP | HG94ZBGP / HG94ZKGP | 2409DSI2580 | 28-10-2024 | VESSEL: MORNING CHANT Voy, 101 - ETA DURBAN: 18-10-2024 | OFFLOADED 09-11-2024 | 18-10-2024 | 23-10-2024 | 24-10-2024 | 24-10-2024 | 25-10-2024 | 25-10-2024 | 25-10-2024 | 26-10-2024 | 26-10-2024 | 27-10-2024 | 28-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 29-10-2024 | 02-11-2024 | 02-11-2024 | 06-11-2024 | 06-11-2024 | 09-11-2024 | [29 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-10-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | ONLY COLLECTING THE BUCKETS THIS MORNING - BV INSPECTION PLANNED FOR THIS AFTERNOON | BV INSPECTION TO BE DONE TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | BEIT BRIDGE BORDER CLEARING | CHIRUNDU BORDER CLEARING | CHIRUNDU BORDER CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAIING RELEASE | WHISKEY AWAIING RELEASE | WHISKEY TO DISPATCH SHORTLY | ON SITE WAITING FOR INDUCTION | ON SITE WAITING TO OFFLOAD | OFFLOADED 09-11-2024

## OFFLOADED
CLIENT PO | CARGO DETAILS | CLIENT | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | VESSEL DETAILS & ETA | ACTUAL STATUS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | MUSINA ARR | MUSINA DISP | BEIT BRIDGE ARR | BEIT BRIDGE DSP | HARERE ARR | HARARE DSP | CHIRUNDU ARR | CHIRUNDU DSP | LUSAKA | KABWE | KITWE | KASUMBALESA ARRIVAL | KASUMBALESA DISPATCH | WHISKY | LUBUMBASHI | LIKASI | TENKE | OFFLOADED | COMMENTS 25-07-2022
BA2774 | 1 PALLET HAMMER & 1 PALLET LINES GP | TENKE FUNGURUME MINING (CMOC) | FML2407DSI2560 | COD 2024 154630 | XML368GP | N/A | 2407DSI2560 | 11-09-2024 | VESSEL: MSC ABIDJAN Voy. NZ428A - NEW ETA DURBAN: 31-08-2024 | OFFLOADED 06-10-2024 | 31-08-2024 | 13-09-2024 | 14-09-2024 | 16-09-2024 | GRB 16-09-2024 | GRB 17-09-2024 | MARTINS DRIFT 17-09-2024 | MARTINS DRIFT 19-09-2024 | FRANCISTOWN 19-09-2024 | FRANCISTOWN 19-09-2024 | KAZUNGULA 21-09-2024 | KAZUNGULA 22-09-2024 | 22-09-2024 | 22-09-2024 | 23-09-2024 | 23-09-2024 | 30-09-2024 | 30-09-2024 | 04-10-2024 | 04-10-2024 | 04-10-2024 | 06-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 28-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 30-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 31-08-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | VESSEL IN AND WORKING - DISCHARGING CONTAINERS | VESSEL STILL WORKING - CONTAINER TO BE COLLECTED ONCE AVAILABLE | VESSEL STILL WORKING - CONTAINER TO BE COLLECTED ONCE AVAILABLE | CONTAINER ARRIVED AT BONDED FACILITY FOR UNPACK | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - LOADING TOMORROW 12-09-2024 | LOADING TODAY | LOADING TODAY | DISPATCHING JOHANNESBURG FOR GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CROSSING TO BOTSWANA SIDE | MARTINS DRIFT BORDER AWAITING RELEASE | SHERWOOD ENROUTE KAZUNGULA BORDER | PALAPYE ENROUTE KAZUNGULA BORDER | KITWE ENROUTE KASUMBALESA BORDER | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED - CUSTOMS SYSTEM DOWN | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED - CUSTOMS SYSTEM DOWN | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 3 PLEASE ASSIST | WHISKEY AWAITING RELEASE - DAY 3 PLEASE ASSIST | KANYAKA AWAITING RELEASE - DAY 4 PLEASE ASSIST | OFFLOADED 06-10-2024
BA2775 | 1 PALLET HAMMER & 1 PALLET LINES GP | TENKE FUNGURUME MINING (CMOC) | FML2407DSI2560 | COD 2024 154630 | XML368GP | N/A | 2407DSI2560 | 11-09-2024 | VESSEL: MSC ABIDJAN Voy. NZ428A - NEW ETA DURBAN: 31-08-2024 | OFFLOADED 06-10-2024 | 31-08-2024 | 13-09-2024 | 14-09-2024 | 16-09-2024 | GRB 16-09-2024 | GRB 17-09-2024 | MARTINS DRIFT 17-09-2024 | MARTINS DRIFT 19-09-2024 | FRANCISTOWN 19-09-2024 | FRANCISTOWN 19-09-2024 | KAZUNGULA 21-09-2024 | KAZUNGULA 22-09-2024 | 22-09-2024 | 22-09-2024 | 23-09-2024 | 23-09-2024 | 30-09-2024 | 30-09-2024 | 04-10-2024 | 04-10-2024 | 04-10-2024 | 06-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 27-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 28-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 30-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 01-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 31-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 31-08-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | VESSEL IN AND WORKING - DISCHARGING CONTAINERS | VESSEL STILL WORKING - CONTAINER TO BE COLLECTED ONCE AVAILABLE | VESSEL STILL WORKING - CONTAINER TO BE COLLECTED ONCE AVAILABLE | CONTAINER ARRIVED AT BONDED FACILITY FOR UNPACK | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - LOADING TOMORROW 12-09-2024 | LOADING TODAY | LOADING TODAY | DISPATCHING JOHANNESBURG FOR GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CROSSING TO BOTSWANA SIDE | MARTINS DRIFT BORDER AWAITING RELEASE | SHERWOOD ENROUTE KAZUNGULA BORDER | PALAPYE ENROUTE KAZUNGULA BORDER | KITWE ENROUTE KASUMBALESA BORDER | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED - CUSTOMS SYSTEM DOWN | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED - CUSTOMS SYSTEM DOWN | MOKAMBO BORDER AWAITING T1 AND TR8 TO BE RELEASED | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 3 PLEASE ASSIST | WHISKEY AWAITING RELEASE - DAY 3 PLEASE ASSIST | KANYAKA AWAITING RELEASE - DAY 4 PLEASE ASSIST | OFFLOADED 06-10-2024