## CURRENT SHIPMENTS
CLIENT INVOICE NR | CONTAINER # | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | DAR-ES-SALAAM ARR | RELEASE OF CONTAINER FROM CUSTOMS | COLLECTION OF CONTAINER | DAR-ES-SALAAM DISP | TUNDUMA BORDER ARR | TUNDUMA BORDER DSP | NAKONDE ARR | NAKONDE DSP | KASUMBALESA / MOKAMBO ZAM ARR | KASUMBALESA / MOKAMBO ZAM DSP | WHISKEY ARR | WHISKEY DSP | LUBUMBASHI ARR | ON SITE ARRIVE | OFFLOADED | COMMENTS 14-07-2025 | COMMENTS 15-07-2025 | COMMENTS 16-07-2025 | COMMENTS 17-07-2025 | COMMENTS 18-07-2025 | COMMENTS 21-07-2025 | COMMENTS 22-07-2025 | COMMENTS 23-07-2025 | COMMENTS 24-07-2025 | COMMENTS 25-07-2025 | COMMENTS 28-07-2025 | COMMENTS 29-07-2025 | COMMENTS 30-07-2025 | COMMENTS 31-07-2025 | COMMENTS 01-08-2025 | COMMENTS 04-08-2025 | COMMENTS 05-08-2025 | COMMENTS 06-08-2025 | COMMENTS 07-08-2025 | COMMENTS 08-08-2025 | COMMENTS 11-08-2025 | COMMENTS 12-08-2025 | COMMENTS 13-08-2025 | COMMENTS 14-08-2025 | COMMENTS 15-08-2025 | COMMENTS 18-08-2025 | COMMENTS 19-08-2025 | COMMENTS 20-08-2025 | COMMENTS 21-08-2025 | COMMENTS 22-08-2025 | COMMENTS 25-08-2025
FA 25006569 | 40'HC FFAU6123176 | 13 GENERATING SETS | SM HYDRAULICS SARL |  |  |  | FML2506DSI2700 | T809DVH | T645EGK | TRS/SN/VSCARGO/SMH/2025/1171 | VESSEL: SC MONTREUX Voy. 04IKFW1MA - Transhipmnet Vessel: MV CMA CGM MOMBASA Voy. 011W ETA: 11-07-2025 | OFFLOADED 22-08-2025 | 11-07-2025 | 23-07-2025 | 26-07-2025 | 26-07-2025 | 05-08-2025 | 08-08-2025 | 08-08-2025 | 08-08-2025 | 10-08-2025 | 13-08-2025 | 14-08-2025 | 16-08-2025 | 17-08-2025 | 21-08-2025 | 22-08-2025 | VESSEL ARRIVED 11-07-2025 - CONTAINER DISCHARDGED FROM VESSEL 13-07-2025 - WAITING FOR THE CONTAINER TO BE MOVED TO ICD TO START WITH FINAL CLEARANCE | CONTAINER MOVED TO ICD - CUSTOMS CLEARANCE IN PORCESS | CUSTOMS CLEARANCE IN PORCESS | CUSTOMS CLEARANCE IN PORCESS - CONGESTION AT ICD | AWAITING CUSTOMS RELEASE - CUSTOMS CLEARANCE IN PORCESS - CONGESTION AT ICD | AWAITING CUSTOMS RELEASE - CUSTOMS CLEARANCE IN PORCESS - CONGESTION AT ICD | AWAITING FINAL CUSTOMS ASSESSMENT & RELEASE | CONTAINER RELEASED FROM CUSTOMS - TO COLLECT FROM ICD TODAY | VEHICLE IN THE QUEUE TO LOAD CONTAINER FROM ICD | CONTAINER COLLECTED FROM ICD | MWANANCHI ENROUTE TUNDUMA BORDER | MBEZI ENROUTE TUNDUMA BORDER | MBEZI TO DISPATCH FOR TUNDUMA BORDER TOMORROW | KIBAHA ENROUTE TUNDUMA BORDER | CHALINZE ENROUTE TUNDUMA BORDER | IRINGA - WAITING FOR REPLACEMENT DRIVER AS THE DRIVER FELL ILL | MBEYA ENROUTE TUNDUMA | TUNDUMA UNDER CLEARANCE | TUNDUMA IN THE QUEUE TO CROSS | TUNDUMA STILL IN THE QUEUE TO CROSS | KASUMBALESA ZAMBIAN SIDE UNDER CLEARANCE | KASUMBALESA DRC SIDE UNDER CLEARANCE - DAY 1 | KASUMBALESA DRC SIDE UNDER CLEARANCE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 3 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | OFFLOADED 22-08-2025
FA 25006570 | 40' HC OOLU9269404 | 4 GENERATING SETS | SM HYDRAULICS SARL |  |  |  | FML2506DSI2700 | T844EBX | T678DCY | TRS/SN/VSCARGO/SMH/2025/1171 | VESSEL: SC MONTREUX Voy. 04IKFW1MA - Transhipmnet Vessel: MV CMA CGM MOMBASA Voy. 011W ETA: 11-07-2025 | OFFLOADED 22-08-2025 | 11-07-2025 | 23-07-2025 | 25-07-2025 | 25-07-2025 | 25-07-2025 | 04-08-2025 | 04-08-2025 | 04-08-2025 | 05-08-2025 | 11-08-2025 | 11-08-2025 | 13-08-2025 | 14-08-2025 | 22-08-2025 | 22-08-2025 | VESSEL ARRIVED 11-07-2025 - CONTAINER DISCHARDGED FROM VESSEL 13-07-2025 - WAITING FOR THE CONTAINER TO BE MOVED TO ICD TO START WITH FINAL CLEARANCE | CONTAINER MOVED TO ICD - CUSTOMS CLEARANCE IN PORCESS | CUSTOMS CLEARANCE IN PORCESS | CUSTOMS CLEARANCE IN PORCESS - CONGESTION AT ICD | AWAITING CUSTOMS RELEASE - CUSTOMS CLEARANCE IN PORCESS - CONGESTION AT ICD | AWAITING CUSTOMS RELEASE - CUSTOMS CLEARANCE IN PORCESS - CONGESTION AT ICD | AWAITING FINAL CUSTOMS ASSESSMENT & RELEASE | CONTAINER RELEASED FROM CUSTOMS - TO COLLECT FROM ICD TODAY | VEHICLE IN THE QUEUE TO LOAD CONTAINER FROM ICD | VEHICLE STILL IN THE QUEUE TO LOAD CONTAINER FROM ICD | TUNDUMA BORDER CLEARING | TUNDUMA BORDER CLEARING | TUNDUMA BORDER WAITING TO CROSS - CLEARANCE COMPLETED | STILL WAITING TO CROSS TUNDUMA BORDER DUE TO CONGESTION | STILL IN THE QUEUE WAITING TO CROSS TUNDUMA BORDER DUE TO CONGESTION | STILL IN THE QUEUE WAITING TO CROSS TUNDUMA BORDER DUE TO CONGESTION | NDOLA ENROUTE KASUMBALESA | KASUMBALESA UNDER CLEARANCE | KASUMBALESA DRC SIDE UNDER CLEARANCE | KASUMBALESA DRC SIDE UNDER CLEARANCE - DAY 2 | KASUMBALESA DRC SIDE UNDER CLEARANCE - DAY 5 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | KANYAKA ENROUTE LUBUMBASHI | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 5 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 8 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 8 | OFFLOADED 22-08-2025

## OFFLOADED 2025
CLIENT INVOICE NR | CONTAINER # | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | VESSEL DETAILS & ETA | ACTUAL STATUS | DAR-ES-SALAAM ARR | RELEASE OF CONTAINER FROM CUSTOMS | COLLECTION OF CONTAINER | DAR-ES-SALAAM DISP | TUNDUMA BORDER ARR | TUNDUMA BORDER DSP | NAKONDE ARR | NAKONDE DSP | KASUMBALESA / MOKAMBO ZAM ARR | KASUMBALESA / MOKAMBO ZAM DSP | WHISKEY ARR | WHISKEY DSP | LUBUMBASHI ARR | ON SITE ARRIVE | OFFLOADED | COMMENTS 24-12-2024 | COMMENTS 27-12-2024 | COMMENTS 30-12-2024 | COMMENTS 02-01-2025 | COMMENTS 03-01-2025 | COMMENTS 06-01-2025 | COMMENTS 07-01-2025 | COMMENTS 08-01-2025 | COMMENTS 09-01-2025 | COMMENTS 10-01-2025 | COMMENTS 14-01-2025
M092411PRF0001 |  | 1 40' X TEU STC 19 GENERATOR SETS | SM HYDRAULICS |  |  |  | FML2412DRI2645 |  |  |  | VESSEL: LADY JANE Voy. 033W - ETA DAR-ES-SALAAM: 08-12-2024 | OFFLOADED 12-01-2025 | 08-12-2024 |  |  | 23-12-2024 | 26-12-2024 | 28-12-2024 | 29-12-2024 | 29-12-2024 | 31-12-2024 | 03-01-2025 | 03-01-2025 | 10-01-2025 | 10-01-2025 | 10-01-2025 | 12-01-2025 | MIKUMI ENROUTE TUNDUMA BORDER | TUNDUMA BORDER IN THE QUEUE TO CROSS TO NAKONDE | KAPIRI MPOSHI ENROUTE MOKAMBO BORDER | KASUMBALESA BORDER CLEARING | KASUMBALESA BORDER DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | WHISKEY AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE - DAY 7 - EXIT NOTE ISSUED - AWAITING OCC DOCUMENTS TO BE STAMPED BEFORE VEHICLE CAN PROCEED TO LUBUMBAHSI | WHISKEY AWAITING RELEASE - DAY 8 - AWAITING RELEASE | OFFLOADED 12-01-2025 | 27